## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | BMG World, 28 Droste Crescent, JHB
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW |  | TIMELINE REVIEW | 2023 Rev & COS RECOGNISED | PLANNED | ACTUAL
1 | Planned Revenue | 14953088.3 |  | 15251088.3 |  | 15251088.3 |  | START DATE | 1669614.47 | 13581473.83 | 13581473.83
2 | Planned Expenditure | 13282857.6929 |  | 14161975.548 |  | 13983270.2517 |  | 2024-01-08 | 1171761.6 | 12990213.948 | 12990213.948
3 | Planned Profit | 1670230.6071 |  | 1089112.752 |  | 1267818.0483 |  | FINISH DATE | 497852.87 | 591259.882 | 591259.882
4 | Planned Margin | 11.17% |  | 7.141% |  | 8.313% |  | 2024-03-13
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER |  | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 60% | 8971852.98 | 2023-08-31 | 004139 | 2023-06-01 | 2023-08-01 | 2023-08-02
2 | Delivery of Batteries |  | 25% | 3738272.075 | 2023-12-19 | 004274 |  | 2023-12-13 | 2023-12-18
3 | Delivery of Inverters |  | 10% | 1495308.83 | 2023-12-18 | 004274 |  | 2023-12-13 | 2023-12-18
4 | Handover |  | 2.5% | 373827.2075 | 2024-03-21 | 004505 |  | 2024-08-23 | 2024-08-30
4 | Handover |  | 2.5% | 373827.2075 | 2024-03-21 | 004663 |  | 2025-02-03 | 2026-01-30 |  | Wimpie requested invoice to be resent
5 | VO - Increase in Inverter Size |  | 0% | 298000 | 2023-12-18 | 004275 |  | 2023-12-13 | 2023-12-14
6 |  |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 15251088.3
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 5337880.905
2 | Delivery of Panels |  | 30% | 4575326.49
3 | Delivery of Inverters |  | 20% | 3050217.66
4 | Practical Completion |  | 10% | 1525108.83
5 | Handover |  | 5% | 762554.415
| Total |  | 100% | 15251088.3
|  |  | 100% | 15251088.3
Formulas:
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7

## Data (hidden)
Public holidays | Drop down list
2021-01-01 | Approved
2021-03-22 | Pending
2021-04-02 | Declined
2021-04-05 | Abanded
2021-04-27
2021-05-01
2021-06-16
2021-08-09
2021-09-24
2021-12-16
2021-12-25 |  | Manual dates
2021-12-26

## Project Plan
[9 empty] | 2026-02-10 | 2026-02-10
| PROJECT PLAN | BMG World, 28 Droste Crescent, JHB | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 350 | 1800kWh, 500kVA
| SITE ADDRESS | BMG World, 28 Droste Crescent, JHB
| BUSINESS DEVELOPER | Peter
| PROJECT MANAGERS | Lloyd Brown
| INSTALLER | TBC
| CONTRACT VALUE | 14953088.3
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 84 |  |  | 102 |  | 100% | 100%
1 | Project Initiation | 2023-07-31 | 38 | 2023-09-07 | 2023-07-31 | 126 | 2023-12-04 | 100% | 100%
1.1 | BD Handover | 2023-07-31 | 1 | 2023-08-01 | 2023-07-31 | 1 | 2023-08-01 | 100% | 100%
1.2 | Project Introduction | 2023-08-14 | 1 | 2023-08-15 | 2023-08-14 | 1 | 2023-08-15 | 100% | 100%
1.3 | Financial Review | 2023-09-05 | 1 | 2023-09-06 | 2023-12-01 | 1 | 2023-12-04 | 100% | 100%
1.4 | Client kick off | 2023-09-06 | 1 | 2023-09-07 | 2023-12-02 | 1 | 2023-12-04 | 100% | 100%
2 | BESS - Prep Work | 2023-08-14 | 59 | 2023-10-12 | 2023-08-14 | 114 | 2023-12-06 | 100% | 100%
2.1 | Pre-Installation Prepping | 2023-08-14 | 10 | 2023-08-28 | 2023-08-14 | 10 | 2023-08-28 | 100% | 100%
2.2 | Plinth Installation | 2023-08-28 | 10 | 2023-09-11 | 2023-08-28 | 10 | 2023-09-11 | 100% | 100%
2.3 | Housing Prep | 2023-08-14 | 36 | 2023-10-03 | 2023-08-14 | 36 | 2023-10-03 | 100% | 100%
2.4 | Setup of rigger and placement | 2023-10-03 | 3 | 2023-10-06 | 2023-10-03 | 3 | 2023-10-06 | 100% | 100%
2.5 | Housing Completed | 2023-10-06 | 4 | 2023-10-12 | 2023-10-06 | 43 | 2023-12-06 | 100% | 100%
3 | Site Establishment | 2023-12-11 | 1 | 2023-12-12 | 2024-01-08 | 1 | 2024-01-09 | 100% | 100%
3.1 | Installer on site and roof assessment | 2023-12-11 | 1 | 2023-12-12 | 2024-01-08 | 1 | 2024-01-09 | 100% | 100%
4 | AC Installation | 2023-12-11 | 74 | 2024-02-23 | 2024-01-08 | 78 | 2024-03-26 | 100% | 100%
4.1 | Inverters delivered | 2023-12-11 | 1 | 2023-12-12 | 2024-01-08 | 1 | 2024-01-09 | 100% | 100%
4.2 | Inverters Mounted | 2023-12-13 | 1 | 2023-12-14 | 2024-01-12 | 1 | 2024-01-15 | 100% | 100%
4.3 | Solar DB lead time | 2024-01-13 | 30 | 2024-02-23 | 2024-01-08 | 35 | 2024-03-02 | 100% | 100%
4.4 | AC Works | 2024-01-20 | 25 | 2024-02-23 | 2024-01-15 | 30 | 2024-03-25 | 100% | 100%
4.5 | AC Tie - in | 2024-01-31 | 2 | 2024-02-02 | 2024-03-23 | 2 | 2024-03-26 | 100% | 100%
5 | DC Works | 2023-12-11 | 63 | 2024-02-12 | 2023-12-11 | 63 | 2024-02-12 | 100% | 100%
5.1 | Mounting Structure delivered | 2024-01-08 | 1 | 2024-01-09 | 2024-01-10 | 1 | 2024-01-11 | 100% | 100%
5.2 | Mounting Structure installation | 2024-01-09 | 10 | 2024-01-23 | 2024-01-11 | 3 | 2024-01-16 | 100% | 100%
5.3 | Battery Delivery | 2023-12-11 | 1 | 2023-12-12 | 2023-12-11 | 1 | 2023-12-12 | 100% | 100%
5.4 | Battery Installation | 2023-12-12 | 35 | 2024-01-30 | 2023-12-12 | 35 | 2024-01-30 | 100% | 100%
5.5 | DC Cable delivered | 2024-01-17 | 1 | 2024-01-18 | 2024-01-16 | 1 | 2024-01-17 | 100% | 100%
5.6 | DC Cable Trays installation | 2024-01-23 | 7 | 2024-02-01 | 2024-01-16 | 7 | 2024-01-25 | 100% | 100%
5.7 | DC Cabling | 2024-02-01 | 7 | 2024-02-12 | 2024-01-25 | 10 | 2024-02-12 | 100% | 100%
6 | Module installation | 2024-01-23 | 15 | 2024-02-07 | 2024-03-04 | 17 | 2024-03-21 | 100% | 100%
6.1 | Module delivery | 2024-01-23 | 1 | 2024-01-24 | 2024-03-04 | 1 | 2024-03-05 | 100% | 100%
6.2 | Module mounting | 2024-01-24 | 10 | 2024-02-07 | 2024-03-05 | 12 | 2024-03-21 | 100% | 100% | Team prep for hoisting and mounting.
7 | Commissioning | 2024-02-23 | 10 | 2024-03-04 | 2024-04-09 | 10 | 2024-04-19 | 100% | 100%
7.1 | Cold commissioning | 2024-02-23 | 3 | 2024-02-28 | 2024-04-09 | 3 | 2024-04-12 | 100% | 100%
7.2 | Hot commissioning | 2024-02-28 | 3 | 2024-03-04 | 2024-04-12 | 5 | 2024-04-19 | 100% | 100%
7.3 | Final Commissioning |  |  |  | 2024-06-03 | 35 | 2024-07-22 | 100% | 100% | Elum to update the firmware
8 | QA Inspections | 2024-03-09 | 4 | 2024-03-13 | 2024-07-22 | 3 | 2024-07-25 | 100% | 100%
8.1 | Red-Team Inspection | 2024-03-09 | 3 | 2024-03-13 | 2024-07-22 | 3 | 2024-07-25 | 100% | 100%
9 | Project Closure | 2024-02-28 | 26 | 2024-03-25 | 2024-04-12 | 515 | 2025-09-09 | 100% | 100%
9.1 | Equipment serial numbers | 2024-02-28 | 1 | 2024-02-29 | 2024-04-12 | 1 | 2024-04-15 | 100% | 100%
9.2 | Snags completion | 2024-03-13 | 3 | 2024-03-18 | 2024-07-22 | 19 | 2024-08-16 | 100% | 100%
9.3 | System Performance Monitoring | 2024-03-18 | 5 | 2024-03-25 | 2024-08-16 | 5 | 2024-08-23 | 100% | 100%
9.4 | Handover documentation | 2024-03-18 | 3 | 2024-03-21 | 2024-10-21 | 1 | 2024-10-22 | 100% | 100%
9.5 | Handover to Client | 2024-03-21 | 1 | 2024-03-22 | 2024-10-22 | 1 | 2025-09-09 | 100% | 100%
9.6 | Handover to Matriarch | 2024-03-22 | 1 | 2024-03-25 | 2024-08-18 | 1 | 2024-08-19 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = [Planned Start, row above]+14
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = [Actual Start, row above]+14
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Note on K52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kholisa Nyengane are the dates still correct after the meeting with BMG?

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 13282857.6929 |  | 14016971.4517 |  | 14161975.548 | -734113.7588 | -145004.0963
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1502096.4 |  | 1188829.0237 |  | 1165914.24 | 313267.3763 | 22914.7837
| 2 | Inverters | 216000 |  | 253411.455 |  | 243184.47 | -37411.455 | 10226.985
| 3 | Mounting Structures | 132867 |  | 71033.82 |  | 78280 | 61833.18 | -7246.18
| 4 | DC Equipment | 350217.5 |  | 440470.35 |  | 478379.145 | -90252.85 | -37908.795 | KN: Additional 5000m required.
| 5 | Monitoring | 49000 |  | 419120.31 |  | 438053.51 | -370120.31 | -18933.2 | KN: Elum controller- RE: order through Krannich - Forex payment issue to Elum
| 6 | AC Equipment | 250335.4174 |  | 1308958.73 |  | 1186079.85 | -1058623.3126 | 122878.88 | KN: AC cable, Awaiting amended quote from MG
| 7 | Battery Systems | 10380642.3333 |  | 9658092 |  | 9684222 | 722550.3333 | -26130
| 8 | Product Add On | 0 |  | 34671.6 |  | 291094.63 | -34671.6 | -256423.03 | KN: Inverter VO & Trenching
| 9 | AC & DC installation | 209475 |  | 284553.2 |  | 254553.2 | -75078.2 | 30000
| 10 | Site Logistics | 60622.9 |  | 143314.22 |  | 143314.22 | -82691.32 | 0
| 11 | Due Dilligence | 19000 |  | 16500 |  | 11683.16 | 2500 | 4816.84
| 12 | BDP Commission | 0 |  | 0 |  | 0 | 0 | 0
| 13 | Engineering | 109626.1422 |  | 194292.173 |  | 154048.413 | -84666.0308 | 40243.76 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 2975 |  | 3724.57 |  | 33168.71 | -749.57 | -29444.14
| 15 | Service Add On | 0 |  | 0 |  | 0 | 0 | 0
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Financial review.

## Expenditure Breakdown
PLANNED EXPENDITURE BREAKDOWN | [6 empty] | 13282857.6929 | 14953088.675 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 14161975.548
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | 555W Solar Panel | 630 | 2384.28 | 1502096.4 | 2024-02-24 | 1502096.4 | 1675592.1685 |  | 1 | 1. Panels | Jinko 555W | 638 | 973747.5 |  | MENLO DISTRIBUTION INV0001192 | 2024-03-31 | 0 | 0.004414 | 2023-08-10 | 1165914.24 | PO2982-BMG2-20240227 |  | 19
1 | [9 empty] | 1 | 1. Panels |  |  |  |  | MENLO DISTRIBUTION INV0001192 | 2024-03-31 | 0 |  | 2024-04-02 |  |  |  | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels |  | 637 |  | 1165914.24 | Jinko: MCSSRJQ3047 | 2023-08-31 | 1675592.1641 |  | 2024-04-02 |  |  |  | AC Equipment | 250335.4174
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | DC Equipment | 142285.5
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | AC Labour | 0
1 | [9 empty] | 1 | [7 empty] | 0 | [5 empty] | DC Labour | 209475
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 3 |  | 216000 | 2024-01-11 | 216000 | 240948.5226 |  | 2 | 2. Inverters | Kathea- Huawei 100KTL | 3 | 80833 | 29187.7652 | Kathea Inv 516781 | 2023-12-31 | 240948.5226 | -298000 | 2024-02-12 | 243184.47 |  |  | Roof Access | 25122.9
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 213996.7048 | Kathea Inv 516781 | 2023-12-31 | 0 |  | 2024-02-23 |  |  |  | 0% | 0
2 | [9 empty] | 2 | 2. Inverters | [5 empty] | 2024-03-31 | 298000 | [5 empty] | Data Guru (Cost removed) | 0
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 635718.8174
3 | Mounting Structures | Roof Type TBC |  |  | 132867 | 2024-02-08 | 132867 | 148213.46 |  | 3 | 3. Mounting Structures | Schlette IBR |  |  | 54891 | Schletter Inv: INV0005 | 2024-01-31 | 103929.2927 | 0 | 2024-02-29 | 78280 | PO2908-BMGP2-20231213 |  | Less 15% | 540360.9948 | [SM: Target Installation Price]
[10 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 1250 | Schletter Inv: INV0005 | 2024-01-31 | 2366.7198 |  | 2024-02-29 |  |  |  | R/Wp | 1.5439
3 | [9 empty] | 3 | 3. Mounting Structures | Lumax Screws |  |  | 19920 | Lumax Inv: INV0040280 | 2024-01-31 | 37716.0465 |  | 2024-02-29 |  |  |  |  | MG |  | Cosmic Sun - DC Only
[10 empty] | 3 | 3. Mounting Structures | Lumax Screws |  |  | 381 | Lumax Inv: INV0040623 | 2024-01-31 | 721.3762 |  | 2024-02-29
3 | [9 empty] | 3 | 3. Mounting Structures | Lumax - Clamps |  |  | 1838 | lLumax INV0040527 | 2024-01-31 | 3480.0248 |  | 2024-02-29 |  | PO2936-BMGP2-20240118 |  | ACTUAL | Installer Price | ACTUAL | Installer Price
[24 empty] | AC Equipment | 1186079.85 | AC Equipment | 0 | 474431.94
4 | DC Equipment | DC Cable | 10465 | 14.8 | 154882 | 2024-03-02 | 350217.5 | 390668.4686 |  | 4 | 4. DC Equipment | DC Cable Red | 10000 | 14.36 | 143600 | Rubicon Inv: INVWCRE-0052509 | 2024-01-31 | 117270.982 | -0.0016314 | 2024-02-29 | 478379.145 |  |  | DC Equipment | 0 | DC Equipment | 133659.15
[11 empty] | 4. DC Equipment | DC Cable Black | 10000 | 14.3 | 143000 | Rubicon Inv: INVWCRE-0052509 | 2024-01-31 | 116780.9918 |  | 2024-02-29
[11 empty] | 4. DC Equipment | Extra DC cable red (Rubicon) | 2000 | 14.36 | 28720 | Rubicon : Inv INVWCRE-0052851 | 2024-01-31 | 23454.1964 |  | 2024-02-29
[11 empty] | 4. DC Equipment | Extra DC cable black (Rubicon) | 2000 | 14.3 | 28600 | Rubicon : Inv INVWCRE-0052851 | 2024-01-31 | 23356.1984 |  | 2024-02-29
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2024-03-02 |  |  |  | 4 | 4. DC Equipment | Delivery |  |  | 800 | Rubicon Inv: INVWCRE-0052509 | 2024-01-31 | 653.3202 |  | 2024-02-29 |  |  |  | AC Labour | 64553.2 | AC Labour | 0
4 |  | Earth Cable | 10465 | 13.5 | 141277.5 | 2023-12-04 |  |  |  | 4 | 4. DC Equipment | DC Equipment - Deposit | 50% | 133659.15 | 66829.57 | Cosmic Sun Inv: CS_BMG_001 | 2023-12-31 | 62006.0295 |  | 2023-12-21 |  |  |  | DC Labour | 0 | DC Labour | 190000
4 |  | Earth clamp | 63 | 16 | 1008 | 2024-03-01 |  |  |  | 4 | 4. DC Equipment | DC Equipment - Onsite | 40% |  | 53463.66 | Cosmic Sun Inv: CS_BMG_003 | 2024-02-29 | 43661.1136 |  | 2024-02-01 |  |  |  | Offloading | 0 | Offloading | 0
4 |  | DC Cable Tray | 230 | 135 | 31050 | 2024-03-01 |  |  |  | 4 | 4. DC Equipment | DC Equipment - Retention | 10% |  | 13365.915 | Cosmic Sun Inv: CS_BMG_006 | 2024-04-30 | 3485.6384 |  | 2024-04-25 |  |  |  | Roof Access | 0 | Roof Access | 71843.09
[24 empty] | Logistics | 4570 | Anchor Points | 50251.13
5 | Monitoring | Solarlog |  |  | 26000 | 2024-01-11 | 49000 | 54659.6186 |  | 5 | 5. Monitoring | Additional Meter | [5 empty] | 0 | 0.0021697 |  | 438053.51 |  |  | P&G | 12150 | HSE | 4500
5 | [9 empty] | 5 | 5. Monitoring | CTs - To be removed (EE Stock 1000A Rogowski Coils with Integrator kit) |  |  | 11604 | Accuenergy Inv: ASAI-003146 | 2024-05-31 | 1232.3902 |  | 2024-06-30 |  | PO3133-BMG-20240528 | Request Tax Invoice from Accu | DC Busbar DB Not included - Est 94k |  | Other | 0
[10 empty] | 5 | 5. Monitoring | CTs - To be removed (EE Stock 1000A Rogowski Coils with Integrator kit) |  |  | -11604 | Allocated to Nampak | 2024-07-31 | 0 |  | 2024-07-31 |  |  | KN: This was sent to Roedolph
5 |  | Comms DB |  |  | 8000 | 2023-12-04 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 4920 | Accuenergy Inv: ASAI-002374 | 2024-01-31 | 622.6719 |  | 2024-02-29 |  | PO2914-BMGP2-20231218 |  | Other | 0 | Other | 0
5 |  | Revenue Grade Meter |  |  | 15000 | 2023-12-04 |  |  |  | 5 | 5. Monitoring | Ferite Core for Comms Cable |  |  | 125.66 | Tanaka's Exp Claim | 2024-04-30 | 0 |  | 2024-05-09 |  |  | TC: Added cost | Total | 1267353.05 | Total | 450253.37
5 | [9 empty] | 5 | 5. Monitoring | techsitter |  |  | 11169 | Techsitter Inv: MN8940230 | 2024-01-31 | 1413.5411 |  | 2024-02-29 |  |  |  | R/Wp | 3.621 | R/Wp | 1.2864
5 | [9 empty] | 5 | 5. Monitoring | Network Switch |  |  | 2590 | Accuenergy Inv: ASAI-002374 | 2024-01-31 | 327.7887 |  | 2024-02-29 |  | PO2914-BMGP2-20231218
5 | [9 empty] | 5 | 5. Monitoring | Delivery |  |  | 150 | Accuenergy Inv: ASAI-002374 | 2024-01-31 | 18.9839 |  | 2024-02-29 |  | PO2914-BMGP2-20231218
5 | [9 empty] | 5 | 5. Monitoring | Elum Controller- Krannich order |  |  | 403848.42 | Krannich Inv: 15-10009002 | 2024-04-30 | 50730.3303 |  | 2024-05-31 |  | PO3005-BMG-P2-20240314
5 | [9 empty] | 5 | 5. Monitoring | Power Supply |  |  | 2388 | Mantech Inv: SOR947028 | 2023-12-31 | 313.9104 |  | 2023-12-21
[10 empty] | 5 | 5. Monitoring | Additional Meter |  |  |  |  | 2025-02-28 |  |  | 2025-03-28 |  | PO3628-BMG-20250205 - RV Approved
[10 empty] | 5 | 5. Monitoring | Additional CTs and Meter - AccuEnergy |  |  | 7080 | Accuenergy Inv: ASAI-006969 | 2025-11-30 |  |  | 2025-12-31 |  | PO4502-BMGP2-20251127
5 | [9 empty] | 5 | 5. Monitoring | Meter |  |  | 5782.43 | Allocated from Stock | 2024-08-31 |  |  | 2024-08-31 |  |  | This can be removed: KN
6 | AC Equipment | AC Equipment Deposit |  | 50% | 125167.7087 | 2023-12-04 | 250335.4174 | 279249.7638 |  | 6 | 6. AC Equipment | AC Equipment Deposit | 50% | 883467.1 | 441733.55 | Matthews Group: INV-1144 | 2023-12-31 | 104001.4207 | 0 | 2024-01-12 | 1186079.85
6 | 250335.4174 | AC Equipment On site |  | 40% | 100134.167 | 2024-03-01 |  |  |  | 6 | 6. AC Equipment | AC Equipment On site | 40% |  | 353386.84 | Matthews Group: INV-1167 | 2024-03-31 | 83201.1366 |  | 2024-03-22
6 |  | Retention |  | 10% | 25033.5417 | 2024-03-01 |  |  |  | 6 | 6. AC Equipment | Retention | 10% |  | 88346.71 | Matthews Group: INV-1293 | 2024-07-31 | 20800.2841 |  | 2024-09-05
[10 empty] | 6 | 6. AC Equipment | AC Board Deposit |  | 302612.75 | 151306.375 | Matthews Group: INV-1144 | 2023-12-31 | 35623.4612 |  | 2023-12-18
[10 empty] | 6 | 6. AC Equipment | AC Board Balance |  |  | 151306.375 | Matthews Group: INV-1167 | 2024-03-31 | 35623.4612 |  | 2024-03-22
6 | [9 empty] | 6 | 6. AC Equipment | DC Busbar - Removed Cost | [5 empty] | 0
7 | Battery Systems | Battery Inverter + Battery Bank |  |  | 9564809 | 2024-01-29 | 10380642.3333 | 11579631.6386 |  | 7 | 7. Battery Systems | Freedom Won Battery 300/240kWh HV | 6 | 1391200 | 869565.2174 | Herholdt's Inv: INV720872 | 2023-11-30 | 1039087.147 | 0.0022428 | 2023-10-04 | 9684222
[11 empty] | 7. Battery Systems | Freedom Won Battery 300/240kWh HV |  |  | 2012954.7826 | Herholdt's Inv: INV720872 | 2023-11-30 | 2405380.7583 |  | 2023-10-20
[11 empty] | 7. Battery Systems | Freedom Won Battery 300/240kWh HV |  |  | 434782.6087 | Herholdt's Inv: INV720872 | 2023-11-30 | 519543.5735 |  | 2023-11-03
[11 empty] | 7. Battery Systems | Freedom Won Battery 300/240kWh HV |  |  | 3826086.9565 | Herholdt's Inv: INV720872 | 2023-11-30 | 4571983.4466 |  | 2023-11-10
[11 empty] | 7. Battery Systems | Freedom Won Battery 300/240kWh HV |  |  | 1203810.4348 | Herholdt's Inv: INV720872 | 2023-11-30 | 1438493.5427 |  | 2023-11-10
7 | [9 empty] | 7 | 7. Battery Systems | Atess-PCS630 |  |  | 545000 | Herholdt's Inv: INV720872 | 2023-11-30 | 651247.8694 |  | 2023-11-23
7 | [9 empty] | 7 | 7. Battery Systems | Atess 630kW Bypass Cabinet |  |  | 380800 | Herholdt's Inv: INV720872 | 2023-11-30 | 455037.0434 |  | 2023-11-23
7 | [9 empty] | 7 | 7. Battery Systems | Atess 630kW Isolation Transformer |  |  | 311600 | Herholdt's Inv: INV720872 | 2023-11-30 | 372346.4882 |  | 2023-11-23
7 | [9 empty] | 7 | 7. Battery Systems | Atess Enerlog Monitoring Module |  |  | 11900 | Herholdt's Inv: INV720872 | 2023-11-30 | 14219.9076 |  | 2023-11-23
[11 empty] | 7. Battery Systems | Atess Enerlog Monitoring Module - Credit |  |  | -10710 | Herholdt's CN070484 | 2023-12-31 | -12783.9989 |  | 2023-11-30
7 | [9 empty] | 7 | 7. Battery Systems | Atess PV Combiner Box 16 Input 1 Output |  |  | 11900 | Herholdt's Inv: INV720872 | 2023-11-30 | 14219.9076 |  | 2023-11-23
7 | [9 empty] | 7 | 7. Battery Systems | Atess PV Combiner Box 16 Input 1 Output - Credit |  |  | -10710 | Herholdt's CN070484 | 2023-12-31 | -12783.9989 |  | 2023-11-30
7 |  | Installation |  |  | 382500 | 2023-12-04 |  |  |  | 7 | 7. Battery Systems | [6 empty] | 0
7 |  | AC+DC Equipment |  |  | 433333.3333 | 2024-03-06 |  |  |  | 7 | 7. Battery Systems | Data Guru (Cost removed) | [5 empty] | 0
7 | [9 empty] | 7 | 7. Battery Systems | Delivery And Rigging |  |  | 31192 | E&M Plant Inv: IN111028 | 2023-12-31 | 37232.3524 |  | 2023-12-08
[10 empty] | 7 | 7. Battery Systems | Safety File |  |  | 3000 | E&M Plant Inv: IN111028 | 2023-12-31 | 3580.9521 |  | 2023-12-08
[10 empty] | 7 | 7. Battery Systems | Delivery And Rigging - Additional cost |  |  | 15100 | E&M Plant Inv: IN111062 | 2023-12-31 | 18024.1255 |  | 2023-12-22 |  | PO2916-BMGP2-20231219 | Incorrect Dimensions supplied to the Company
[11 empty] | 7. Battery Systems | Delivery And Rigging - Additional cost |  |  | -7550 | E&M Plant Credit Note: IC100085 | 2023-12-31 | 0 |  | 2023-12-11
[11 empty] | 7. Battery Systems | Rigging - shift batteries to install battery cable |  |  | 55500 | E&M Plant - Inv IO103047 | 2024-04-30 | 64802.52 |  | 2024-04-15 |  | PO3045-BMG-P2-20240408
7 | [9 empty] | 7 | 7. Battery Systems | [11 empty] | RV: Removed 60k
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | AC Tie-in breaker |  |  | 32856.48 | MG INV-1232 | 2024-05-31 | 0 | 0 | 2024-06-06 | 291094.63
8 | [9 empty] | 8 | 8. Product Add On | Trenching - Deposit |  |  | 16045.8 | Mkholo Inv: MP /EE/150124 | 2024-01-31 | 0 |  | 2024-02-08
8 | [9 empty] | 8 | 8. Product Add On | Trenching - Balance |  |  | 15045.8 | Mkholo Inv: MP /EE/260224 | 2024-02-29 | 0 |  | 2024-02-29
[10 empty] | 8 | 8. Product Add On | Ring Cores |  |  | 267.15 | Tanaka's Exp Claim | 2024-05-31 | 0 |  | 2024-06-06
[10 empty] | 8 | 8. Product Add On | Steel Covers |  |  | 21890 | Mkholo Projects: InvMP/EE?240724 | 2024-07-31 | 0 |  | 2024-07-24 |  | PO3257-BMGP2-20240724 - RV Approved
[10 empty] | 8 | 8. Product Add On | Re-Routing of cables | 50% | 202189.4 | 101094.7 | MG INV-1291 | 2024-07-31 | 0 |  | 2024-08-01 |  | VO approved by Johannes e-mail 29 July
[10 empty] | 8 | 8. Product Add On | Re-Routing of cables | 50% |  | 101094.7 | MG INV-1291 | 2024-07-31 | 0 |  | 2024-08-29
[11 empty] | 8. Product Add On | Repairs on steel covers
8 | [9 empty] | 8 | 8. Product Add On | Man Hole |  |  | 2800 | Mkholo Inv: MP/EE/080424 | 2024-04-30 | 0 |  | 2024-04-18
Only services to be capture below, products above
9 | AC & DC installation | Installation Deposit |  | 20% | 41895 | 2023-12-04 | 209475 | 261843.75 |  | 9 | 9. AC installation | Deposit | 25% |  | 16138.3 | Matthews Group Inv: 1144 | 2023-12-31 | 16600.5102 | 0 | 2024-01-12 | 254553.2
9 |  | MS Complete |  | 15% | 31421.25 | 2024-03-01 |  |  |  | 9 | 9. AC installation | AC Tie-in | 25% |  | 16138.3 | Matthews Group Inv 1238 | 2024-05-31 | 16600.5102 |  | 2024-06-06
9 | 209475 | AC Tie-in Complete |  | 15% | 31421.25 | 2024-02-19 |  |  |  | 9 | 9. AC installation | Practical Completion | 25% |  | 16138.3 | Matthews Group Inv 1279 | 2024-07-31 | 16600.5102 |  | 2024-07-19
9 | 0 | Panels Complete |  | 15% | 31421.25 | 2024-03-06 |  |  |  | 9 | 9. AC installation | Retention | 25% |  | 16138.3 | Matthews Group: INV-1293 | 2024-07-31 | 16600.5102 |  | 2024-09-05
9 |  | Practical Completion |  | 20% | 41895 | 2024-04-01 |  |  |  | 9 | 9. DC installation | Deposit | 25% |  | 47500 | Cosmic Sun Inv: CS_BMG_001 | 2023-12-31 | 48860.4273 |  | 2023-12-22
9 |  | Retention |  | 15% | 31421.25 | 2024-04-01 |  |  |  | 9 | 9. DC installation | MS Complete | 25% |  | 47500 | Cosmic Sun Inv: CS_BMG_002 | 2024-03-31 | 48860.4273 |  | 2024-04-25
[11 empty] | 9. DC installation | Panels Complete | 25% |  | 47500 | Cosmic Sun Inv. CS_BMG_005 | 2024-03-31 | 48860.4273 |  | 2024-04-04
9 | [9 empty] | 9 | 9. DC installation | Retention | 25% |  | 47500 | Cosmic Sun Inv. CS_BMG_006 | 2024-04-30 | 48860.4273 |  | 2024-04-25
10 | Site Logistics | Scaffolding |  |  | 25122.9 | 2023-12-04 | 60622.9 | 75779 |  | 10 | 10. Site Logistics - AC | Logistics Deposit | 50% | 16720 | 8360 | Matthews Group Inv: 1144 | 2023-12-31 | 4420.4437 | 0 | 2024-01-12 | 143314.22
10 | [9 empty] | 10 | 10. Site Logistics - AC | Logistics - Equipment Onsite | 40% |  | 6688 | Matthews Group Inv: 1167 | 2024-03-31 | 3536.355 |  | 2024-03-22
10 | [9 empty] | 10 | 10. Site Logistics - AC | Logistics - Retention | 10% |  | 1672 | Matthews Group: INV-1293 | 2024-07-31 | 884.0887 |  | 2024-09-05
10 |  | Offloading |  |  | 8500 | 2023-12-04 |  |  |  | 10 | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics - DC | Logistics Deposit | 50% | 126594.22 | 63297.11 | Cosmic Sun Inv: CS_BMG_001 | 2023-12-31 | 33469.0563 |  | 2023-12-22
10 |  | Telehandler |  |  | 27000 | 2023-12-04 |  |  |  | 10 | 10. Site Logistics - DC | Logistics - Equipment Onsite | 40% |  | 50637.688 | Cosmic Sun Inv: CS_BMG_004 | 2024-03-31 | 26775.245 |  | 2024-02-01
10 | [9 empty] | 10 | 10. Site Logistics - DC | Logistics - Retention | 10% |  | 12659.422 | Cosmic Sun Inv. CS_BMG_006 | 2024-04-30 | 6693.8113 |  | 2024-04-25
10 | [9 empty] | 10 | [7 empty] | 0
11 | Due Dilligence | Structural sign off |  |  | 8000 | 2023-12-11 | 19000 | 23750 |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 5500 | L&B INV-1448 | 2023-10-31 | 7916.6667 | -0.0043008 | 2023-10-06 | 11683.16 |  | Changed amount it was 8k -TC
11 |  | Electrical PrEng sign off |  |  | 11000 | 2024-04-01 |  |  |  | 11 | 11. Due Dilligence | Electrical Sign off |  |  | 6183.16 | MJ Bleloch Inv: 1216 | 2024-05-31 | 15833.3376 |  | 2024-06-06
11 | [9 empty] | 11 | [7 empty] | 0
11 | [9 empty] | 11 | [7 empty] | 0
11 | [9 empty] | 11 | [7 empty] | 0
12 | BDP Commission |  |  |  | 0 |  | 0 | 0 |  | 12 | 12. BDP Commission |  |  |  | 0 |  |  | 0 |  |  | 0
13 | Engineering | Matriarch Defects Period |  |  | 27626.1422 | 2024-04-25 | 109626.1422 | 219252.2843 |  | 13 | 13. Engineering | Matriarch Defects Period - 1% because of battery cost |  |  | 149530.883 | MATRIARCH INV-2441 | 2024-04-30 | 213594.7353 | 0.0019992 | 2024-04-30 | 154048.413
13 |  | Management |  |  | 12000 | 2024-04-25 |  |  |  | 13 | 13. Engineering | EPC Cost |  |  | 3761.29 |  | 2023-08-31 | 3721.0132 |  | 2023-08-31
13 |  | Project manager |  |  | 27200 | 2024-04-25 |  |  |  | 13 | 13. Engineering | EPC Cost |  |  | 0 |  | 2023-09-30 | 0 |  | 2023-09-30
13 |  | Planner time |  |  | 15600 | 2024-04-25 |  |  |  | 13 | 13. Engineering | EPC Cost |  |  | 0 |  | 2023-10-31 | 0 |  | 2023-10-31
13 |  | De Snagging |  |  | 27200 | 2024-04-25 |  |  |  | 13 | 13. Engineering | EPC Cost |  |  | 0 |  | 2023-11-30 | 0 |  | 2023-11-30
13 | [9 empty] | 13 | 13. Engineering | EPC Cost |  |  | 0 |  | 2023-12-31 | 0 |  | 2023-12-31
13 | [9 empty] | 13 | 13. Engineering | EPC Cost |  |  | 756.24 |  | 2024-01-31 | 1936.5339 |  | 2024-01-25
13 | [9 empty] | 13 | [7 empty] | 0
14 | General Expenses | Car travel to site |  |  | 2975 | 2024-04-25 | 2975 | 3500 |  | 14 | 14. General Expenses | Car Travel to Site |  |  | 2086.07 |  | 2023-08-31 | 1599.3136 | 0.0008448 | 2023-08-31 | 33168.71
14 | [9 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 0 |  | 2023-09-30 | 0 |  | 2023-09-30
14 | [9 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 151 |  | 2023-10-31 | 141.8956 |  | 2023-10-31
14 | [9 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 0 |  | 2023-11-30 | 0 |  | 2023-11-30
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 2774.58 |  | 2023-12-31 | 1758.79 |  | 2023-12-31
14 | [9 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 1366.01 |  | 2024-01-31 | 0 |  | 2024-02-08
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 679.5 |  | 2024-02-29 | 0 |  | 2024-03-07
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 373.65 |  | 2024-03-31 | 0 |  | 2024-04-05
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 20535.43 |  | 2024-04-30 |  |  | 2024-05-09
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 1573.48 |  | 2024-05-31 |  |  | 2024-06-06
[10 empty] | 14 | 14. General Expenses | Car Travel to Site |  |  | 1339.72 |  | 2024-06-30 |  |  | 2024-07-05
[15 empty] | 1250.66 |  | 2024-07-31 |  |  | 2024-08-06
14 | [9 empty] | 14 |  |  |  |  | 1038.61 |  | 2024-08-31 | 0 |  | 2024-09-05
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On |  |  |  | 0 |  |  | 0 | 0 |  | 0
15 | [9 empty] | 15 |  |  |  |  | 0 |  |  | 0
15 | [9 empty] | 15 |  |  |  |  | 0 |  |  | 0
15 | [9 empty] | 15 |  |  |  |  | 0 |  |  | 0
15251088.6693
Note on R35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be removed. CTs will be allocated to another site. Reply: @Kholisa Nyengane, please give a description of the CTs. Split Core/Rogowski etc. Reply: These are rogowski coils and an integrator kit. Stock is currently sitting in the office. Reply: What size are the CTs? Reply: 1000A
Note on R50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kholisa Nyengane, please request this invoice and load it for payment.
Note on R64: Thami Cambalele: Changed the amt to whats on the credit note - og 11900
Note on R66: Thami Cambalele: Changed the amt to whats on the credit note - og 11900
Note on U74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed 60k
Note on C87: HP: [SM] from costing sheet
Note on N87: HP: [KN]AC Installation
Note on C88: HP: [SM] from costing sheet
Note on R88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kholisa Nyengane, please get MG to invoice this milestone Reply: @Kholisa Nyengane, a reminder to get this and load it on the accounts board.
Note on R89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown @Kholisa Nyengane can we please request the retention invoice from MG?
Note on N90: HP: [KN] DC Installation

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2023-07-31 to 2027-01-25
PLANNED |  | CHECK | CHECK
| Planned Revenue | 14953088.3 | 15251088.3 | 0 | 0 | 0 | 0 | 8971852.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5531580.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747654.415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3
| Planned Expenditure | 13282857.6929 | 13282857.6929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774463.1087 | 8000 | 0 | 0 | 0 | 242000 | 0 | 0 | 9564809 | 132867 | 0 | 1533517.65 | 365528.9587 | 464754.5833 | 0 | 0 | 0 | 84316.25 | 0 | 0 | 112601.1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774463.1087 | 782463.1087 | 782463.1087 | 782463.1087 | 782463.1087 | 1024463.1087 | 1024463.1087 | 1024463.1087 | 10589272.1087 | 10722139.1087 | 10722139.1087 | 12255656.7587 | 12621185.7174 | 13085940.3007 | 13085940.3007 | 13085940.3007 | 13085940.3007 | 13170256.5507 | 13170256.5507 | 13170256.5507 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929 | 13282857.6929
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8197389.8713 | 8189389.8713 | 13720970.7763 | 13720970.7763 | 13720970.7763 | 13478970.7763 | 13478970.7763 | 13478970.7763 | 3914161.7763 | 3781294.7763 | 3781294.7763 | 2247777.1263 | 1882248.1676 | 1417493.5843 | 1417493.5843 | 2165147.9993 | 2165147.9993 | 2080831.7493 | 2080831.7493 | 2080831.7493 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071 | 1968230.6071
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 15251088.3 | 15251088.3 | 8971852.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298000 | 5233580.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373827.2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373827.2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 9269852.98 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14503433.885 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 14877261.0925 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3 | 15251088.3
| Actual + Planned Expenditure | 14161975.548 | 13850081.438 | 0 | 0 | 0 | 0 | 5847.36 | 0 | 0 | 0 | 0 | 875065.2174 | 0 | 2012954.7826 | 0 | 434933.6087 | 5029897.3913 | 0 | 1261200 | -21420 | 34192 | -7550 | 346421.055 | 2774.58 | 0 | 466231.85 | 0 | 756.24 | 104101.348 | 17411.81 | 29187.7652 | 213996.7048 | 456874.8 | 679.5 | 0 | 511381.215 | 0 | 1213787.89 | 0 | 58300 | 121025.337 | 149530.883 | 20661.09 | 0 | 0 | 403848.42 | 57018.57 | 0 | 0 | 11604 | 1339.72 | 0 | 16138.3 | 21890 | 89490.7 | 1250.66 | 0 | 0 | 106877.13 | 107195.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 5847.36 | 5847.36 | 5847.36 | 5847.36 | 5847.36 | 880912.5774 | 880912.5774 | 2893867.36 | 2893867.36 | 3328800.9687 | 8358698.36 | 8358698.36 | 9619898.36 | 9598478.36 | 9632670.36 | 9625120.36 | 9971541.415 | 9974315.995 | 9974315.995 | 10440547.845 | 10440547.845 | 10441304.085 | 10545405.433 | 10562817.243 | 10592005.0082 | 10806001.713 | 11262876.513 | 11263556.013 | 11263556.013 | 11774937.228 | 11774937.228 | 12988725.118 | 12988725.118 | 13047025.118 | 13168050.455 | 13317581.338 | 13338242.428 | 13338242.428 | 13338242.428 | 13742090.848 | 13799109.418 | 13799109.418 | 13799109.418 | 13810713.418 | 13812053.138 | 13812053.138 | 13828191.438 | 13850081.438 | 13939572.138 | 13940822.798 | 13940822.798 | 13940822.798 | 14047699.928 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548 | 14154895.548
| ACTUAL CashFlow |  |  | 8971852.98 | 8971852.98 | 8971852.98 | 8971852.98 | 8966005.62 | 8966005.62 | 8966005.62 | 8966005.62 | 8966005.62 | 8090940.4026 | 8090940.4026 | 6077985.62 | 6077985.62 | 5643052.0113 | 613154.62 | 613154.62 | -648045.38 | -626625.38 | -660817.38 | -355267.38 | 4531892.47 | 4529117.89 | 4529117.89 | 4062886.04 | 4062886.04 | 4062129.8 | 3958028.452 | 3940616.642 | 3911428.8768 | 3697432.172 | 3240557.372 | 3239877.872 | 3239877.872 | 2728496.657 | 2728496.657 | 1514708.767 | 1514708.767 | 1456408.767 | 1335383.43 | 1185852.547 | 1165191.457 | 1165191.457 | 1165191.457 | 761343.037 | 704324.467 | 704324.467 | 704324.467 | 692720.467 | 691380.747 | 691380.747 | 675242.447 | 653352.447 | 563861.747 | 562611.087 | 562611.087 | 562611.087 | 829561.1645 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 722365.5445 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752 | 1096192.752
|  | CHECK | CHECK
| Revenue Recognition | -243114.976 | 15196203.276 | 0 | 0 | 0 | 0 | 1680912.4908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8058.5622 | 0 | 0 | 0 | 11481559.6843 | 0 | 0 | 0 | 581272.004 | 0 | 0 | 0 | 0 | 434048.6682 | 0 | 0 | 0 | 43661.1136 | 0 | 0 | 0 | 544857.0524 | 0 | 0 | 0 | 0 | 388167.4625 | 0 | 0 | 0 | 33666.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 1010351.8665 | 14185851.4095 | 0 | 0 | 0 | 0 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1680912.4908 | 1688971.0531 | 1688971.0531 | 1688971.0531 | 1688971.0531 | 13170530.7373 | 13170530.7373 | 13170530.7373 | 13170530.7373 | 13751802.7413 | 13751802.7413 | 13751802.7413 | 13751802.7413 | 13751802.7413 | 14185851.4095 | 14185851.4095 | 14185851.4095 | 14185851.4095 | 14229512.5231 | 14229512.5231 | 14229512.5231 | 14229512.5231 | 14774369.5754 | 14774369.5754 | 14774369.5754 | 14774369.5754 | 14774369.5754 | 15162537.038 | 15162537.038 | 15162537.038 | 15162537.038 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276 | 15196203.276
| Installer Expenditure |  | 1484855.185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265635.945 | 0 | 0 | 466231.85 | 0 | 0 | 53463.66 | 0 | 0 | 0 | 0 | 0 | 0 | 511381.215 | 0 | 47500 | 0 | 0 | 108365.915 | 0 | 0 | 0 | 0 | 0 | 16138.3 | 0 | 0 | 0 | 0 | 0 | 16138.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265635.945 | 265635.945 | 265635.945 | 731867.795 | 731867.795 | 731867.795 | 785331.455 | 785331.455 | 785331.455 | 785331.455 | 785331.455 | 785331.455 | 785331.455 | 1296712.67 | 1296712.67 | 1344212.67 | 1344212.67 | 1344212.67 | 1452578.585 | 1452578.585 | 1452578.585 | 1452578.585 | 1452578.585 | 1452578.585 | 1468716.885 | 1468716.885 | 1468716.885 | 1468716.885 | 1468716.885 | 1468716.885 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185 | 1484855.185
311894.11

## Finance - Rev
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT
| 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | (blank) | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2025-02-28 | 2025-11-30 | Grand Total
(blank) | [10 empty] | 0 |  |  | 0 |  |  | 0
1. Panels | 1675592.1641 | [6 empty] | 0 |  |  | 0 | [5 empty] | 1675592.1641
2. Inverters |  |  |  |  | 240948.5226 |  |  | 298000 |  |  | 0 | [5 empty] | 538948.5226
3. Mounting Structures | [5 empty] | 148213.46 | [10 empty] | 148213.46
4. DC Equipment |  |  |  |  | 62006.0295 | 281515.6888 | 43661.1136 |  | 3485.6384 | [7 empty] | 390668.4702
5. Monitoring |  |  |  |  | 313.9104 | 2382.9855 |  |  | 50730.3303 | 1232.3902 | 0 |  | 0 |  |  |  | 54659.6164
6. AC Equipment |  |  |  |  | 139624.8819 |  |  | 118824.5977 |  |  | 0 |  | 20800.2841 |  |  |  | 279249.7638
7. Battery Systems |  |  |  | 11481559.6843 | 33269.4321 |  |  |  | 64802.52 |  | 0 | [5 empty] | 11579631.6364
8. Product Add On | [5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  |  | 0
11. Due Dilligence |  |  | 7916.6667 | [6 empty] | 15833.3376 | [6 empty] | 23750.0043
12. BDP Commission | [10 empty] | 0 | [5 empty] | 0
13. Engineering | 3721.0132 | 0 | 0 | 0 | 0 | 1936.5339 |  |  | 213594.7353 | [7 empty] | 219252.2823
14. General Expenses | 1599.3136 | 0 | 141.8956 | 0 | 1758.79 | 0 | 0 | 0 | [8 empty] | 3499.9992
15. Service Add On | [10 empty] | 0 | [5 empty] | 0
10. Site Logistics - AC |  |  |  |  | 4420.4437 |  |  | 3536.355 |  |  |  |  | 884.0887 |  |  |  | 8840.8874
10. Site Logistics - DC |  |  |  |  | 33469.0563 |  |  | 26775.245 | 6693.8113 | [7 empty] | 66938.1126
9. AC installation |  |  |  |  | 16600.5102 |  |  |  |  | 16600.5102 |  |  | 33201.0204 |  |  |  | 66402.0408
9. DC installation |  |  |  |  | 48860.4273 |  |  | 97720.8546 | 48860.4273 | [7 empty] | 195441.7092
Grand Total | 1680912.4908 | 0 | 8058.5622 | 11481559.6843 | 581272.004 | 434048.6682 | 43661.1136 | 544857.0524 | 388167.4625 | 33666.238 | 0 |  | 54885.3933 | 0 |  |  | 15251088.6693
| 1669614.47 |  |  | 11489618.24 | 581272 | 434048.67 | 43661.11
| 11298.0208 | 0 | 8058.5622 | -8058.5557 | 0.0040173 | -0.001834 | 0.0035666
13570176.1784
Inv
13581473.83
13570176.1784
11297.6516

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | (blank) | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2025-02-28 | 2025-11-30 | Grand Total
1. Panels | 1165914.24 | [15 empty] | 1165914.24
10. Site Logistics - AC |  |  |  |  | 8360 |  |  | 6688 |  |  |  |  | 1672 |  |  |  | 16720
10. Site Logistics - DC |  |  |  |  | 63297.11 |  |  | 50637.688 | 12659.422 | [7 empty] | 126594.22
11. Due Dilligence |  |  | 5500 | [6 empty] | 6183.16 | [6 empty] | 11683.16
12. BDP Commission | [10 empty] | 0 | [5 empty] | 0
13. Engineering | 3761.29 | 0 | 0 | 0 | 0 | 756.24 |  |  | 149530.883 | [7 empty] | 154048.413
14. General Expenses | 2086.07 | 0 | 151 | 0 | 2774.58 | 1366.01 | 679.5 | 373.65 | 20535.43 | 1573.48 |  | 1339.72 |  |  |  |  | 30879.44
15. Service Add On | [10 empty] | 0 | [5 empty] | 0
2. Inverters |  |  |  |  | 243184.47 | [11 empty] | 243184.47
3. Mounting Structures | [5 empty] | 78280 | [10 empty] | 78280
4. DC Equipment |  |  |  |  | 66829.57 | 344720 | 53463.66 |  | 13365.915 | [7 empty] | 478379.145
5. Monitoring |  |  |  |  | 2388 | 18829 |  |  | 403974.08 | 11604 |  |  | -11604 | 5782.43 |  | 7080 | 438053.51
6. AC Equipment |  |  |  |  | 593039.925 |  |  | 504693.215 |  |  |  |  | 88346.71 |  |  |  | 1186079.85
7. Battery Systems |  |  |  | 9608400 | 20322 |  |  |  | 55500 | [7 empty] | 9684222
8. Product Add On | [5 empty] | 16045.8 | 15045.8 |  | 2800 | 33123.63 |  |  | 224079.4 |  |  |  | 291094.63
9. AC installation |  |  |  |  | 16138.3 |  |  |  |  | 16138.3 |  |  | 32276.6 |  |  |  | 64553.2
9. DC installation |  |  |  |  | 47500 |  |  | 95000 | 47500 | [7 empty] | 190000
(blank) | [10 empty] | 0 |  | 1250.66 | 1038.61 |  |  | 2289.27
Grand Total | 1171761.6 | 0 | 5651 | 9608400 | 1063833.955 | 459997.05 | 69188.96 | 657392.553 | 705865.73 | 68622.57 | 0 | 1339.72 | 336021.37 | 6821.04 |  | 7080 | 14161975.548

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 216000 | 0 | 216000 | 0 | 216000
Inverters | 216000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 132867 | 0 | 132867 | 0 | 132867
Mounting Structure | 132867
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 154882 | 0 | 154882 | 0 | 154882
DC Cable | 154882
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Solarlog | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | >Installer Name 2< |  | Variance
AC installation | 0 | 0 |  | 0 | 0 |  | 0 | 0
AC equipment | 209475 | 0.5985 |  | 0 | 209475 |  | 0 | 209475
DC installation | 0 | 0 |  | 0 | 0 |  | 0 | 0
DC equipment | 142285.5 | 0.40653 |  | 0 | 142285.5 |  | 0 | 142285.5
Storage | 0 |  |  |  | 0 |  |  | 0
Panel lifting equipment | 60622.9 |  |  |  | 60622.9 |  |  | 60622.9
Offloading | 0 |  |  |  | 0 |  |  | 0
Totals | 412383.4 |  | 0 |  | 412383.4 | 0 |  | 412383.4
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | 0 | 0 |  | 0 | 0 |  | 0 | 0
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 209475
DC installation | 209475 | 0.5985 |  | 0 | 209475 |  | 0 | 0
DC equipment | 142285.5 | 0.40653 |  |  | 142285.5 |  |  | 142285.5
Storage | 0 |  |  |  | 0 |  |  | 0
Panel lifting equipment | 60622.9 |  |  |  | 60622.9 |  |  | 60622.9
Offloading | 0 |  |  |  | 0 |  |  | 0
Totals | 412383.4 |  | 0 |  | 412383.4 | 0 |  | 412383.4
Budget Summary
Budget | 412383.4
Cosmic Sun | 0
>Installer Name 2< | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 412383.4
All amounts are exc VAT
|  |  | LR | JKM | LR
|  |  | Aarden | Menlo | Krannich
|  |  | 3.3 | 2.6398 | 2.68

## Project Plan-Volvo (hidden)
[9 empty] | 2026-02-10 | 2026-02-10
| PROJECT PLAN | Warne House | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 350 | 1800kWh, 500kVA
| SITE ADDRESS | BMG World, 28 Droste Crescent, JHB
| BUSINESS DEVELOPER | Peter
| PROJECT MANAGERS | Kerusha/ Kholisa
| INSTALLER | TBC
| CONTRACT VALUE | 14953088.3
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 25 |  |  | 102 |  | 90.48%
1 | Project Initiation | 2023-07-31 | 38 | 2023-09-07 | 2023-07-31 | 126 | 2023-12-04 | 100% | 126
1.1 | BD Handover | 2023-07-31 | 1 | 2023-08-01 | 2023-07-31 | 1 | 2023-08-01 | 100%
1.2 | Project Introduction | 2023-08-14 | 1 | 2023-08-15 | 2023-08-14 | 1 | 2023-08-15 | 100%
1.3 | Financial Review | 2023-09-05 | 1 | 2023-09-06 | 2023-12-01 | 1 | 2023-12-04 | 100%
1.4 | Client kick off | 2023-09-06 | 1 | 2023-09-07 | 2023-12-02 | 1 | 2023-12-04 | 100%
2 | BESS - Prep Work (If Applicable) | 2024-07-01 | 9 | 2024-07-10 | 2023-08-14 | 114 | 2023-12-06 | 100% | 114
2.1 | Pre-Installation Prepping | 2024-07-01 | 2 | 2024-07-03 | 2023-08-14 | 10 | 2023-08-28 | 100%
2.2 | Plinth Installation | 2024-07-03 | 5 | 2024-07-10 | 2023-08-28 | 10 | 2023-09-11 | 100%
2.3 | Housing Prep | 2024-07-01 | 7 | 2024-07-10 | 2023-08-14 | 36 | 2023-10-03 | 100%
2.4 | Setup of rigger and placement | 2024-07-08 | 1 | 2024-07-09 | 2023-10-03 | 3 | 2023-10-06 | 100%
2.5 | Housing Completed | 2024-07-09 | 1 | 2024-07-10 | 2023-10-06 | 43 | 2023-12-06 | 100%
3 | Site Establishment | 2024-07-01 | 1 | 2024-07-02 | 2024-01-08 | 1 | 2024-01-09 | 100% | 1
3.1 | Installer on site and roof assessment | 2024-07-01 | 1 | 2024-07-02 | 2024-01-08 | 1 | 2024-01-09 | 100%
4 | AC Installation | 2024-06-24 | 30 | 2024-07-24 | 2024-01-08 | 78 | 2024-03-26 | 100% | 78
4.1 | Inverters delivered | 2024-07-01 | 1 | 2024-07-02 | 2024-01-08 | 1 | 2024-01-09 | 100%
4.2 | Inverters Mounted | 2024-07-02 | 1 | 2024-07-03 | 2024-01-12 | 1 | 2024-01-15 | 100%
4.3 | Solar DB lead time | 2024-06-24 | 20 | 2024-07-22 | 2024-01-08 | 35 | 2024-03-02 | 100%
4.4 | AC Works | 2024-07-15 | 5 | 2024-07-22 | 2024-01-15 | 30 | 2024-03-25 | 100%
4.5 | AC Tie - in | 2024-07-22 | 2 | 2024-07-24 | 2024-03-23 | 2 | 2024-03-26 | 100%
5 | DC Works | 2024-07-01 | 18 | 2024-07-19 | 2023-12-11 | 63 | 2024-02-12 | 100% | 63
5.1 | Mounting Structure delivered | 2024-07-01 | 1 | 2024-07-02 | 2024-01-10 | 1 | 2024-01-11 | 100%
5.2 | Mounting Structure installation | 2024-07-02 | 6 | 2024-07-10 | 2024-01-11 | 3 | 2024-01-16 | 100%
5.3 | Battery Delivery | 2024-07-10 | 1 | 2024-07-11 | 2023-12-11 | 1 | 2023-12-12 | 100%
5.4 | Battery Installation | 2024-07-11 | 5 | 2024-07-18 | 2023-12-12 | 35 | 2024-01-30 | 100%
5.5 | DC Cable delivered | 2024-07-01 | 1 | 2024-07-02 | 2024-01-16 | 1 | 2024-01-17 | 100%
5.6 | DC Cable Trays installation | 2024-07-02 | 6 | 2024-07-10 | 2024-01-16 | 7 | 2024-01-25 | 100%
5.7 | DC Cabling | 2024-07-10 | 7 | 2024-07-19 | 2024-01-25 | 10 | 2024-02-12 | 100%
6 | Module installation | 2024-07-08 | 10 | 2024-07-18 | 2024-03-04 | 17 | 2024-03-21 | 100% | 17
6.1 | Module delivery | 2024-07-08 | 1 | 2024-07-09 | 2024-03-04 | 1 | 2024-03-05 | 100%
6.2 | Module mounting | 2024-07-09 | 7 | 2024-07-18 | 2024-03-05 | 12 | 2024-03-21 | 100% |  | Team prep for hoisting and mounting.
7 | Commissioning | 2024-07-24 | 2 | 2024-07-26 | 2024-04-09 | 10 | 2024-04-19 | 100% | 10
7.1 | Cold commissioning | 2024-07-24 | 1 | 2024-07-25 | 2024-04-09 | 3 | 2024-04-12 | 100%
7.2 | Hot commissioning | 2024-07-25 | 1 | 2024-07-26 | 2024-04-12 | 5 | 2024-04-19 | 100%
7.3 | Final Commissioning | 2024-07-26 | 2 | 2024-07-30 | 2024-06-03 | 15 | 2024-06-24 | 80% |  | Awaiting Atess Technician
8 | QA Inspections | 2024-07-31 | 5 | 2024-08-05 | 2024-06-24 | 3 | 2024-06-27 | 90% | 2.7
8.1 | Red-Team Inspection | 2024-07-31 | 3 | 2024-08-05 | 2024-06-24 | 3 | 2024-06-27 | 90%
9 | Project Closure | 2024-07-25 | 26 | 2024-08-20 | 2024-04-12 | 83 | 2024-07-04 | 24.29% | 20.1571
9.1 | Equipment serial numbers | 2024-07-25 | 1 | 2024-07-26 | 2024-04-12 | 1 | 2024-04-15 | 100%
9.2 | Snags completion | 2024-08-05 | 5 | 2024-08-12 | 2024-06-24 | 3 | 2024-06-27 | 80%
9.3 | System Performance Monitoring | 2024-08-12 | 4 | 2024-08-16 | 2024-06-24 | 5 | 2024-07-01 | 0%
9.4 | Handover documentation | 2024-08-12 | 5 | 2024-08-19 | 2024-06-27 | 3 | 2024-07-02 | 0%
9.5 | Handover to Client | 2024-08-19 | 1 | 2024-08-20 | 2024-07-02 | 1 | 2024-07-03 | 0%
9.6 | Handover to Matriarch | 2024-08-12 | 1 | 2024-08-13 | 2024-07-03 | 1 | 2024-07-04 | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = [Planned Start, row above]+14
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = [Actual Start, row above]+14
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Decision Register (hidden)
BMG World, 28 Droste Crescent, JHB |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | BMG World, 28 Droste Crescent, JHB | 0 | 0 | 0