## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Shoprite Mini_Citrusdal
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Shoprite Mini_Citrusdal
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Peet Verreynne
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
DC Cable Red & Black
Inverters
Mounting Structure
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Project Plan
[9 empty] | 2026-02-09 | 2026-02-09
| PROJECT PLAN | Shoprite Mini_Citrusdal | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 250 | [6 empty] | 27 | Net Work Days
| PROJECT DEVELOPER | Peet Verreynne | [6 empty] | 5.4 | Total Weeks
| PROJECT MANAGERS | Peet Verreynne | [6 empty] | 46.2963 | kW/Week Installation Rate
| CONTRACT VALUE | 2034295.7254
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 34 |  |  | 36 |  | 99.11% | 100%
1 | Project Initiation | 2025-09-09 | 57 | 2025-11-05 | 2025-09-09 | 57 | 2025-11-05 | 100% | 100%
1.1 | BD Handover | 2025-09-09 | 1 | 2025-09-10 | 2025-09-09 | 1 | 2025-09-10 | 100% | 100% |  | Milestone | Start Date | Duration | End Date | 2026-02-09 | 2026-02-09
1.2 | Project Introduction | 2025-10-15 | 1 | 2025-10-16 | 2025-10-15 | 1 | 2025-10-16 | 100% | 100% | Delayed due to EPC Contracts | Project Initiation | 2025-09-09 | 57 | 2025-11-05 | 1 | 0
1.3 | HSE | 2025-10-15 | 15 | 2025-11-05 | 2025-10-15 | 15 | 2025-11-05 | 100% | 100% |  | Site Establishment | 2025-11-06 | 1 | 2025-11-07
1.4 | Installer Kick Off | 2025-10-22 | 1 | 2025-10-23 | 2025-10-23 | 1 | 2025-10-24 | 100% | 100% |  | AC Installation | 2025-10-05 | 58 | 2025-12-02
1.5 | Project Review | 2025-10-29 | 1 | 2025-10-30 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100% |  | DC Works | 2025-11-06 | 28 | 2025-12-04
[11 empty] | Module installation | 2025-11-10 | 15 | 2025-11-25
2 | Site Establishment | 2025-11-05 | 1 | 2025-11-06 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100% |  | Commissioning | 2025-12-05 | 7 | 2025-12-12
2.1 | Solar Contractor Establishment | 2025-11-05 | 1 | 2025-11-06 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100% |  | QA Inspections | 2025-12-08 | 1 | 2025-12-09
[11 empty] | Project Closure | 2025-12-09 | 52 | 2026-01-30
3 | AC Installation | 2025-10-05 | 44 | 2025-11-18 | 2025-10-05 | 58 | 2025-12-02 | 100% | 100%
3.1 | Inverters delivered | 2025-11-06 | 1 | 2025-11-07 | 2025-11-11 | 1 | 2025-11-12 | 100% | 100%
3.2 | Inverters Mounted | 2025-11-14 | 2 | 2025-11-18 | 2025-11-29 | 2 | 2025-12-02 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-10-05 | 25 | 2025-11-07 | 2025-10-05 | 31 | 2025-11-17 | 100% | 100%
3.4 | AC Works | 2025-11-07 | 5 | 2025-11-14 | 2025-11-19 | 2 | 2025-11-21 | 100% | 100%
3.5 | AC Tie-In | 2025-11-07 | 1 | 2025-11-10 | 2025-11-21 | 1 | 2025-11-24 | 100% | 100% | Tie in breaker provided
4 | DC Works | 2025-11-05 | 30 | 2025-12-05 | 2025-11-06 | 28 | 2025-12-04 | 92.86% | 100%
4.1 | Mounting Structure delivered | 2025-11-05 | 1 | 2025-11-06 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100%
4.2 | Mounting Structure installation | 2025-11-06 | 6 | 2025-11-14 | 2025-11-07 | 4 | 2025-11-13 | 100% | 100%
4.3 | DC Cable delivered | 2025-11-05 | 1 | 2025-11-06 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100%
4.4 | DC Stringing | 2025-11-22 | 10 | 2025-12-05 | 2025-11-24 | 8 | 2025-12-04 | 100% | 100%
5 | Module installation | 2025-11-05 | 20 | 2025-11-25 | 2025-11-10 | 15 | 2025-11-25 | 100% | 100%
5.1 | Module delivery | 2025-11-05 | 1 | 2025-11-06 | 2025-11-10 | 1 | 2025-11-11 | 100% | 100%
5.2 | Module mounting | 2025-11-14 | 7 | 2025-11-25 | 2025-11-16 | 7 | 2025-11-25 | 100% | 100%
6 | Commissioning | 2025-12-05 | 4 | 2025-12-09 | 2025-12-05 | 7 | 2025-12-12 | 100% | 100%
6.1 | Commissioning | 2025-12-05 | 1 | 2025-12-08 | 2025-12-05 | 4 | 2025-12-11 | 100% | 100%
6.2 | Practical Completion | 2025-12-08 | 1 | 2025-12-09 | 2025-12-11 | 1 | 2025-12-12 | 100% | 100%
7 | QA Inspections | 2025-12-05 | 5 | 2025-12-10 | 2025-12-08 | 1 | 2025-12-09 | 100% | 100%
7.1 | Red-Team Inspection | 2025-12-05 | 3 | 2025-12-10 | 2025-12-08 | 1 | 2025-12-09 | 100% | 100% | booked for 8th
8 | Project Closure | 2025-12-09 | 20 | 2025-12-29 | 2025-12-09 | 52 | 2026-01-30 | 100% | 100%
8.1 | Equipment serial numbers | 2025-12-10 | 1 | 2025-12-11 | 2025-12-09 | 1 | 2025-12-10 | 100% | 100%
8.2 | Snags completion | 2025-12-10 | 5 | 2025-12-18 | 2025-12-09 | 3 | 2025-12-12 | 100% | 100%
8.3 | System Performance Monitoring | 2025-12-09 | 5 | 2025-12-17 | 2025-12-12 | 18 | 2026-01-09 | 100% | 100%
8.4 | Handover documentation | 2025-12-18 | 1 | 2025-12-19 | 2026-01-08 | 3 | 2026-01-13 | 100% | 100%
8.5 | Handover to Client | 2025-12-19 | 1 | 2025-12-22 | 2026-01-29 | 1 | 2026-01-30 | 100% | 100%
8.6 | Handover to Matriarch | 2025-12-19 | 5 | 2025-12-29 | 2026-01-23 | 1 | 2026-01-26 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)+35
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)+35
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2034295.7254 |  | 2004738.5754 |  |  | Start Date |  |  | 0 | 0 | 2004738.5544 | 1378273.664 | 2034295.7044 | 1378273.664
2 | Planned Expenditure | 1676320.9561 |  | 1378273.664
3 | Planned Profit | 357974.7694 |  | 626464.9114 |  |  | End Date - PC
4 | Planned Margin | 17.6% |  | 31.25%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 1017147.8627 | 2025-09-30 | 004847 + CN004888 + 004889 | 2025-10-01 | 2025-11-11 | [7 empty] | 1900-01-06
2 | Delivery of Panels |  | 25% | 508573.9314 | 2025-11-12 | 004847 + CN004888 + 004889 | 2025-10-01 | 2025-11-14
3 | Delivery of Inverters |  | 10% | 203429.5725 | 2025-11-13 | 004847 + CN004888 + 004889 | 2025-10-01 | 2025-11-14
4 | Practical Completion |  | 10% | 203429.5725 | 2025-12-16 | 004847 + CN004888 + 004889 | 2025-10-01 | 2025-12-11
5 | Handover |  | 5% | 101714.7863 | 2025-12-26 | 004847 + CN004888 + 004889 | 2025-10-01 | 2025-12-11
6 | Reduced size CAPEX |  | 0% | -29557.15 |  | CN004888 + 004889 | 2025-12-02 | 2025-12-11
7 | - |  | 0% | 0
|  |  | 100% | 2004738.5754
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 701658.5014
2 | Delivery of Panels |  | 30% | 601421.5726
3 | Delivery of Inverters |  | 20% | 400947.7151
4 | Practical Completion |  | 10% | 200473.8575
5 | Handover |  | 5% | 100236.9288
| Total |  | 100% | 2004738.5754
|  |  | 100% | 2004738.5754
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 1676320.9561 |  | 1378273.664 | 298047.2921
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 568406.775 |  | 460381.54 | 108025.235
2 | 2. Inverters | 140000 |  | 130492 | 9508
3 | 3. Mounting Structures | 100040 |  | 58518 | 41522
4 | 4. DC Equipment | 196743.5 |  | 87564.99 | 109178.51
5 | 5. Monitoring | 49000 |  | 59282.42 | -10282.42
6 | 6. AC Equipment | 251986.3826 |  | 144396.22 | 107590.1626
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 52000 |  | 23900 | 28100
9 | 9. AC & DC installation | 198850 |  | 272012.964 | -73162.964
10 | 10. Site Logistics | 56854.4444 |  | 77414.6 | -20560.1556
11 | 11. Due Dilligence | 29000 |  | 15565 | 13435
12 | 12. BDP Commission | 9178.8402 |  | 0 | 9178.8402
13 | 13. Engineering | 19886.0138 |  | 25059.23 | -5173.2162
14 | 14. General Expenses | 4375 |  | 1886.7 | 2488.3
15 | 15. Service Add On | 0 |  | 21800 | -21800
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1676320.9561 | 2034295.7254 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1378273.664
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Expected Payment Date | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 568406.775 | 2025-12-19 | 568406.775 | 710508.4688 |  | 1 | 1. Panels | Longi 610W - hi-MO 7 LR8-66HGD610M | 409.8361 | 1128.9514 | 462685 |  | Krannich Inv 15-10014211 | 2025-10-31 | 695754.3591 | 29557.15 | 2025-12-18 | 460381.54
1 | [9 empty] | 1 | 1. Panels |  |  | 1.8507 |  |  |  |  | 0
1 | [9 empty] | 1 | 1. Panels | EPR Fees |  |  | 9811.66 |  | Krannich Inv 15-10014211 | 2025-10-31 | 14754.1096 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | Reduction in size | -20 | 1128.95 | -22579 |  | Allocated to Cpt Storeroom | 2025-11-30 | 0 |  | 2025-11-30
1 | [9 empty] | 1 | 1. Panels | Delivery Fee |  |  | 10463.88 |  | Krannich Inv: 17010001217 | 2025-11-30 | 0 |  | 2025-12-18
[10 empty] | 1 | 1. Panels | [6 empty] | 2025-12-31 | -29557.15
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 251986.3826
2 | Inverters | Inverter Budget |  |  | 140000 | 2025-12-20 | 140000 | 175000 |  | 2 | 2. Inverters | Huawei 100KTL | 2 | 65246 | 130492 |  | Krannich Inv 15-10014211 | 2025-10-31 | 175000 | 0 | 2025-12-18 | 130492 | DC Equipment | 123593.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 62525
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 136325
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 17326.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1027.7778
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 100040 | 2025-11-19 | 100040 | 125050 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 47705 | PO4424-SMCD-20251030 - RV Approved | Schletter - INV2382 | 2025-11-30 | 101943.1671 | 0 | 2025-12-30 | 58518 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Nuts and Bolts - Trunking |  |  | 10813 | PO4467-SMCD-20251111 - RV Approved | Schletter - INV2410 | 2025-11-30 | 23106.8329 |  | 2025-12-30 |  | Total | 601284.3271
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 511091.678
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0444
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | JASolar |  |  | Cosmic Sun
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 64385.5 |  | AC Equipment | 57950
4 | DC Equipment | DC Cable Budget | 6008.75 |  | 73150 | 2025-12-20 | 196743.5 | 245929.375 |  | 4 | 4. DC Equipment | DC Cable - red from CPT stock | 2000 | 13.5 | 27000 |  | Allocated from Cpt Storeroom | 2025-10-31 | 75830.4474 | 0.023241 | 2025-10-31 | 87564.99 | DC Equipment | 33565 |  | DC Equipment | 78834.25
4 |  | DC Equipment Budget |  |  | 123593.5 | 2025-12-20 |  |  |  | 4 | 4. DC Equipment | DC Cable - black from CPT stock | 2000 | 13.5 | 27000 |  | Allocated from Cpt Storeroom | 2025-10-31 | 75830.4474 |  | 2025-10-31 |  | AC Labour | 43349.5 | 0.1734 | AC Labour | 101500 | 0.406
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 228663.46 | 0.91465 | DC Labour | 199000 | 0.796
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 11410 |  | Lifelines | 0
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 33565 | 10% | 3356.5 | PO4380-SMCD-20251017 - RV Approved | JA Electrical INV 1109 | 2025-10-31 | 9426.848 |  | 2025-11-06 |  | Geda, scaffholding | 23643 |  | Geda, scaffholding | 8250
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 5034.75 |  | JA Electrical INV 1119 | 2025-11-30 | 14140.272 |  | 2025-11-28 |  | Storage | 17963.5 |  | Geda | 0
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete - Partial |  | 10% | 3356.5 |  | JA Electrical INV 1124 | 2025-11-30 | 9426.848 |  | 2025-11-28 |  | Site Ablutions | 0 |  | Logistics | 11550
[10 empty] | 4 | 4. DC Equipment | AC Installation Complete - Partial |  | 10% | 3356.5 |  | JA Electrical INV 1151 | 2026-01-31 | 9426.8491 |  | 2026-01-29
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete - Partial |  | 20% | 6713 |  | JA Electrical INV 1124 | 2025-11-30 | 18853.696 |  | 2025-11-28 |  | P&G's | 8913.5 |  | HSE | 4500
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete - Partial |  | 5% | 1678.25 |  | JA Electrical INV 1151 | 2026-01-31 | 4713.4246 |  | 2026-01-29
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 3356.5 |  | JA Electrical INV 1151 | 2026-01-31 | 9426.8491 |  | 2026-01-29 |  | Shuffle boards | 12929.5 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 3356.5 |  | JA Electrical INV 1154 | 2026-01-31 | 9426.8491 |  | 2026-02-05 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 1678.25 |  | JA Electrical INV 1154 | 2026-01-31 | 4713.4246 |  | 2026-02-05 |  | Total | 444822.96 |  | Total | 461584.25
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 1678.24 |  | JA Electrical INV 1154 | 2026-01-31 | 4713.3965 |  | 2026-03-07 |  | R/Wp | 1.7793 |  | R/Wp | 1.8463
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
Portfolio SUMMARY
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-12-20 | 49000 | 61250 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8698.34 |  | Menlo - INV0003384 | 2025-11-30 | 9080.9395 | 0.002944 | 2026-01-09 | 59282.42 |  | JA Solar
5 |  | Revenue Metering |  |  | 15000 | 2025-11-30 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 25321 | PO4373-SMCD-20251015 - RV approved | Accuenergy Inv: ASAI-006652 | 2025-10-31 | 26936.9206 |  | 2025-11-28 |  | Shoprite Mini Citrusdal (250kW) | 444822.96
5 | [9 empty] | 5 | 5. Monitoring | Techsitter | 2 | 11169 | 22338 |  | Matriarch - INV-5366 | 2025-10-31 | 23763.5533 |  | 2025-11-28 |  | Shoprite Mini Bredarsdorp (250 Kw) | 0
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 343.33 |  | DSV Inv: 180153158 | 2025-10-31 | 365.2404 |  | 2025-11-28
5 | [9 empty] | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole - SO-35912 | 2025-10-31 | 1037.222 |  | 2025-10-09 |  | Hungry Lion Citrusdal (140 kw) | 0
5 | [9 empty] | 5 | 5. Monitoring | Delivery of Comms Equip |  |  | 21.33 |  | Uber | 2025-11-30 | 22.6274 |  | 2025-11-12 |  | R/W | 0.70607
5 | [9 empty] | 5 | 5. Monitoring | Delivery of Comms Equip |  |  | 41 |  | Uber | 2025-11-30 | 43.4939 |  | 2025-11-29
[10 empty] | 5 | 5. Monitoring | Power Supply |  |  | 1300 |  | Allocated from Cpt Storeroom | 2025-12-31 | 0 |  | 2025-12-31
5 | [9 empty] | 5 | 5. Monitoring | Courier of Comms Equip |  |  | 244.42 |  | DSV Inv: 180157893 | 2025-12-31 | 0 |  | 2026-01-31
6 | AC Equipment | AC Equipment Budget |  |  | 251986.3826 | 2025-11-30 | 251986.3826 | 314982.9783 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 144396.22
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 80010.72 | PO4328-SMCD-20250925 - RV Approved | Switchboard - 2-SOI002606 | 2025-11-30 | 174533.7577 |  | 2025-12-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 64385.5 | 10% | 6438.55 | PO4380-SMCD-20251017 - RV Approved | JA Electrical INV 1109 | 2025-10-31 | 14044.9221 |  | 2025-11-06
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 9657.825 |  | JA Electrical INV 1119 | 2025-11-30 | 21067.3831 |  | 2025-11-28
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete - Partial |  | 10% | 6438.55 |  | JA Electrical INV 1124 | 2025-11-30 | 14044.9221 |  | 2025-11-28
[10 empty] | 6 | 6. AC Equipment | AC Installation Complete - Partial |  | 10% | 6438.55 |  | JA Electrical INV 1151 | 2026-01-31 | 14044.9221 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete - Partial |  | 20% | 12877.1 |  | JA Electrical INV 1124 | 2025-11-30 | 28089.8441 |  | 2025-11-28
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete - Partial |  | 5% | 3219.275 |  | JA Electrical INV 1151 | 2026-01-31 | 7022.461 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 6438.55 |  | JA Electrical INV 1151 | 2026-01-31 | 14044.9221 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 6438.55 |  | JA Electrical INV 1154 | 2026-01-31 | 14044.9221 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 3219.275 |  | JA Electrical INV 1154 | 2026-01-31 | 7022.461 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 3219.275 |  | JA Electrical INV 1154 | 2026-01-31 | 7022.461 |  | 2026-03-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 52000 | 57777.7778 |  | 8 | 8. Product Add On | [7 empty] | 0 | 0 |  | 23900
8 |  | Inverter Awning |  |  | 40000 | 2025-10-16 |  |  |  | 8 | 8. Product Add On | Inverter Awning | 15800 | 70% | 11060 | PO4360-SMCD-20251007 - RV Approved | Barrier Projects INV508 | 2025-10-31 | 26737.3315 |  | 2025-10-24
8 | [9 empty] | 8 | 8. Product Add On |  |  | 30% | 4740 |  | Barrier Projects INV508 | 2025-10-31 | 11458.8563 |  | 2025-12-04
8 |  | Walk-way |  |  | 12000 | 2025-10-31 |  |  |  | 8 | 8. Product Add On | Custom Walkway Landing |  |  | 2430 | PO4441-SMCD-20251104 - RV Approved | Barrier Projects INV527 | 2025-11-30 | 5874.477 |  | 2025-11-13
8 | [9 empty] | 8 | 8. Product Add On |  |  |  | 5670 |  | Barrier Projects INV527 | 2025-11-30 | 13707.113 |  | 2025-12-04
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 62525 | 2025-10-20 | 198850 | 220944.4444 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.001787 |  | 272012.964
9 |  | DC Installation Budget |  |  | 136325 | 2025-10-20 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 272012.96 | 10% | 27201.296 | PO4380-SMCD-20251017 - RV Approved | JA Electrical INV 1109 | 2025-10-31 | 22094.4444 |  | 2025-11-06
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 40801.944 |  | JA Electrical INV 1119 | 2025-11-30 | 33141.6667 |  | 2025-11-28
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete - Partial |  | 10% | 27201.296 |  | JA Electrical INV 1124 | 2025-11-30 | 22094.4444 |  | 2025-11-28
[10 empty] | 9 | 9. AC & DC installation | AC Installation Complete - Partial |  | 10% | 27201.296 |  | JA Electrical INV 1151 | 2026-01-31 | 22094.4441 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete - Partial |  | 20% | 54402.592 |  | JA Electrical INV 1124 | 2025-11-30 | 44188.8889 |  | 2025-11-28
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete - Partial |  | 5% | 13600.648 |  | JA Electrical INV 1151 | 2026-01-31 | 11047.2221 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 27201.296 |  | JA Electrical INV 1151 | 2026-01-31 | 22094.4441 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 27201.3 |  | JA Electrical INV 1154 | 2026-01-31 | 22094.4474 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 13600.648 |  | JA Electrical INV 1154 | 2026-01-31 | 11047.2221 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 13600.648 |  | JA Electrical INV 1154 | 2026-01-31 | 11047.2221 |  | 2026-03-07
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-11-25 | 56854.4444 | 63171.6049 |  | 10 | 10. Site Logistics | Security |  |  | 2555.1 | PO4468-SMCD-20251111 - RV Approved | HP Private Security - 3946 | 2025-11-30 | 1876.5042 | -0.00042211 | 2025-11-13 | 77414.6
10 |  | Scaffolding |  |  | 17326.6667 | 2025-11-27 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 30000 | 2025-12-05 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 1027.7778 | 2025-12-05 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 74859.5 | 10% | 7485.95 | PO4380-SMCD-20251017 - RV Approved | JA Electrical INV 1109 | 2025-10-31 | 6317.1605 |  | 2025-11-06
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 11228.925 |  | JA Electrical INV 1119 | 2025-11-30 | 9162.9901 |  | 2025-11-28
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete - Partial |  | 10% | 7485.95 |  | JA Electrical INV 1124 | 2025-11-30 | 6108.6601 |  | 2025-11-28
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete - Partial |  | 10% | 7485.95 |  | JA Electrical INV 1151 | 2026-01-31 | 6108.6601 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete - Partial |  | 20% | 14971.9 |  | JA Electrical INV 1124 | 2025-11-30 | 12217.3201 |  | 2025-11-28
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete - Partial |  | 5% | 3742.975 |  | JA Electrical INV 1151 | 2026-01-31 | 3054.33 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 7485.95 |  | JA Electrical INV 1151 | 2026-01-31 | 6108.6601 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 7485.95 |  | JA Electrical INV 1154 | 2026-01-31 | 6108.6601 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 3742.975 |  | JA Electrical INV 1154 | 2026-01-31 | 3054.33 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 3742.975 |  | JA Electrical INV 1154 | 2026-01-31 | 3054.33 |  | 2026-03-07
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-12-07 | 29000 | 32222.2222 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 9565 |  | SunSpot - E034 | 2025-12-31 | 19801.1921 | 0 | 2026-01-23 | 15565
11 |  | Structural sign off |  |  | 18000 | 2025-11-30 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5975 | 2025-12-31 | 12421.0301 |  | 2026-01-30
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | PD Fee |  |  | 9178.8402 | 2025-11-30 | 9178.8402 | 0 |  | 12 | 12. BDP Commission | PD Fee | [5 empty] | 2025-11-30 |  |  | 2025-11-30 | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 19886.0138 | 2025-11-30 | 19886.0138 | 22597.7429 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 25059.23 |  | Matriarch - INV-6234 | 2026-01-31 | 22597.7429 | 0 | 2026-02-27 | 25059.23
13 | [9 empty] | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 4375 | 2025-09-30 | 4375 | 4861.1111 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 | -0.0029763 | 2025-10-31 | 1886.7
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 863.3 |  | Expense Claim | 2025-11-30 | 2144.3485 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1023.4 |  | Expense Claim | 2025-12-31 | 2716.7656 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 21800
15 | [9 empty] | 15 | 15. Service Add On | Domestic Transport |  |  | 7000 | PO4437-GEN-20251103 - RV Approved | ABL Transport Inv 0205 | 2025-11-30 |  |  | 2025-11-06
15 | [9 empty] | 15 | 15. Service Add On | Domestic Transport - Return of panels |  |  | 14800 | PO4515-GEN-20251203 - RV Approved | ABL Transport Inv 0231 | 2025-12-31 |  |  | 2025-12-04
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 568406.775 |  | 710508.4688
| Inverter Procurement Budget | 140000 |  | 175000
| Mounting Structure Budget | 100040 |  | 125050
| DC Equipment Budget | 196743.5 |  | 245929.375
| AC Equipment Budget | 251986.3826 |  | 314982.9783
| Monitoring Budget | 49000 |  | 61250
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 52000 |  | 57777.7778
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 62525 |  | 69472.2222
| DC Installer Budget | 136325 |  | 151472.2222
| In-House Expense Budget | 19886.0138 |  | 22597.7429
| Compliance Budget | 29000 |  | 32222.2222
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 1027.7778 |  | 1141.9753
| On Site Security | 30000 |  | 33333.3333
| Roof Access Budget for Installers | 17326.6667 |  | 19251.8519
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 4375 |  | 4861.1111

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-07-07 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2034295.7254 | 2034295.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017147.8627 | 0 | 0 | 0 | 0 | 0 | 712003.5039 | 0 | 0 | 0 | 0 | 203429.5725 | 101714.7863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017147.8627 | 1017147.8627 | 1017147.8627 | 1017147.8627 | 1017147.8627 | 1017147.8627 | 1729151.3666 | 1729151.3666 | 1729151.3666 | 1729151.3666 | 1729151.3666 | 1932580.9392 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254 | 2034295.7254
| Planned Expenditure | 1676320.9561 | 1676320.9561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375 | 0 | 40000 | 198850 | 12000 | 0 | 0 | 100040 | 339877.9033 | 42027.7778 | 0 | 939150.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375 | 4375 | 44375 | 243225 | 255225 | 255225 | 255225 | 355265 | 695142.9033 | 737170.6811 | 737170.6811 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561 | 1676320.9561
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012772.8627 | 1012772.8627 | 972772.8627 | 773922.8627 | 761922.8627 | 761922.8627 | 1473926.3666 | 1373886.3666 | 1034008.4633 | 991980.6855 | 991980.6855 | 256259.9831 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694 | 357974.7694
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2004738.5754 | 2004738.5754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1729151.3666 | 0 | 0 | 0 | 275587.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1729151.3666 | 1729151.3666 | 1729151.3666 | 1729151.3666 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754 | 2004738.5754
| Actual + Planned Expenditure | 1378273.664 | 1378273.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 0 | 11060 | 54000 | 51482.296 | 5006.43 | 0 | 225634.662 | 26073.3 | 0 | 613452.54 | 0 | 139828.72 | 9721.74 | 0 | 9565 | 117450.16 | 66723.448 | 0 | 0 | 25059.23 | 22241.138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 975 | 12035 | 66035 | 117517.296 | 122523.726 | 122523.726 | 348158.388 | 374231.688 | 374231.688 | 987684.228 | 987684.228 | 1127512.948 | 1137234.688 | 1137234.688 | 1146799.688 | 1264249.848 | 1330973.296 | 1330973.296 | 1330973.296 | 1356032.526 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664 | 1378273.664
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -975 | -975 | -12035 | -66035 | -117517.296 | 1606627.6406 | 1606627.6406 | 1380992.9786 | 1354919.6786 | 1630506.8874 | 1017054.3474 | 1017054.3474 | 877225.6274 | 867503.8874 | 867503.8874 | 857938.8874 | 740488.7274 | 673765.2794 | 673765.2794 | 673765.2794 | 648706.0494 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114 | 626464.9114
|  | CHECK | CHECK
| Revenue Recognition | 29557.171 | 2004738.5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179351.8626 | 0 | 0 | 0 | 564870.1969 | 0 | 0 | 0 | 0 | 5381.8378 | 0 | 0 | 0 | 255134.6571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2004738.5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179351.8626 | 1179351.8626 | 1179351.8626 | 1179351.8626 | 1744222.0595 | 1744222.0595 | 1744222.0595 | 1744222.0595 | 1744222.0595 | 1749603.8973 | 1749603.8973 | 1749603.8973 | 1749603.8973 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544 | 2004738.5544

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 710508.4688 | 0 | -29557.15 | 0 |  |  | 680951.3187
2. Inverters |  | 175000 |  |  | 0 |  |  | 175000
3. Mounting Structures |  |  | 125050 |  | 0 |  |  | 125050
4. DC Equipment |  | 161087.7428 | 42420.8161 |  | 0 | 37707.3921 | 4713.424 | 245929.375
5. Monitoring |  | 52102.9362 | 9147.0608 | 0 |  |  |  | 61249.9971
6. AC Equipment |  | 14044.9221 | 237735.907 |  | 0 | 56179.6882 | 7022.461 | 314982.9783
8. Product Add On | 0 | 38196.1878 | 19581.59 |  |  |  |  | 57777.7778
9. AC & DC installation | 0 | 22094.4444 | 99425 |  | 0 | 88377.7778 | 11047.2222 | 220944.4444
10. Site Logistics |  | 6317.1605 | 29365.4745 |  | 0 | 24434.6403 | 3054.33 | 63171.6054
11. Due Dilligence | 0 |  |  | 32222.2222 | 0 |  |  | 32222.2222
13. Engineering | 0 |  |  |  |  | 22597.7429 |  | 22597.7429
14. General Expenses |  | 0 | 2144.3485 | 2716.7656 | 0 |  |  | 4861.1141
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 1179351.8626 | 564870.1969 | 5381.8378 | 0 | 229297.2413 | 25837.4373 | 2004738.5759

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 472496.66 | -12115.12 |  |  |  | 460381.54
2. Inverters |  | 130492 |  |  |  |  | 130492
3. Mounting Structures |  |  | 58518 |  |  |  | 58518
4. DC Equipment |  | 57356.5 | 15104.25 |  | 13426 | 1678.25 | 87565
5. Monitoring |  | 48977.33 | 8760.67 | 1544.42 |  |  | 59282.42
6. AC Equipment |  | 6438.55 | 108984.195 |  | 25754.2 | 3219.275 | 144396.22
8. Product Add On |  | 15800 | 8100 |  |  |  | 23900
9. AC & DC installation |  | 27201.296 | 122405.832 |  | 108805.184 | 13600.648 | 272012.96
10. Site Logistics |  | 7485.95 | 36241.875 |  | 29943.8 | 3742.975 | 77414.6
11. Due Dilligence |  |  |  | 15565 |  |  | 15565
13. Engineering | 0 |  |  |  | 25428.6966 |  | 25428.6966
14. General Expenses |  | 0 | 863.3 | 1023.4 |  |  | 1886.7
15. Service Add On |  |  | 7000 | 14800 |  |  | 21800
12. BDP Commission
7.BESS
Grand Total | 0 | 766248.286 | 353863.002 | 32932.82 | 203357.8806 | 22241.148 | 1378643.1366

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.1116 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.56863 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.3847 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.92064 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Shoprite Mini_Citrusdal |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Shoprite Mini_Citrusdal | 0 | 0 | 0