## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | China Town Remove and Refit | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | N/A
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 312229.88
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
[8 empty] | 92.31% | 93.41%
1 | Project Activities | 0 | 45876 | 2025-08-07 | 2025-05-08 | 285 | 2026-02-17 | 92.31% | 93.41%
1.1 | PD Handover | 2025-05-08 | 1 | 2025-05-09 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
1.2 | HSE | 2025-05-09 | 24 | 2025-06-12 | 2025-05-09 | 24 | 2025-06-12 | 100% | 100%
1.3 | Material Procurement | 2025-06-12 | 1 | 2025-06-13 | 2025-06-12 | 1 | 2025-06-13 | 100% | 100%
1.4 | Site Establishment | 2025-06-13 | 1 | 2025-06-17 | 2025-06-13 | 1 | 2025-06-17 | 100% | 100%
1.5 | Material Delivery | 2025-07-21 | 1 | 2025-07-22 | 2025-06-17 | 1 | 2025-06-18 | 100% | 100%
1.6 | Roof Remedial Work | 2025-06-13 | 25 | 2025-07-21 | 2025-06-13 | 124 | 2025-12-08 | 100% | 100%
1.7 | Construction | 2025-07-21 | 1 | 2025-07-22 | 2025-12-08 | 5 | 2025-12-15 | 100% | 100%
1.8 | System Energised | 2025-07-22 | 5 | 2025-07-29 | 2025-12-17 | 1 | 2026-01-12 | 100% | 100%
1.9 | O&M Monitoring | 2025-07-22 | 2 | 2025-07-24 | 2025-12-17 | 2 | 2026-01-13 | 100% | 100%
1.10 | Red Team Inspection | 2025-07-24 | 3 | 2025-07-29 | 2026-01-13 | 3 | 2026-01-16 | 100% | 100%
1.11 | Snag Completion | 2025-07-29 | 2 | 2025-07-31 | 2026-01-16 | 2 | 2026-01-20 | 100% | 100%
1.18 | Handover Documentation | 2025-07-31 | 5 | 2025-08-07 | 2026-01-20 | 5 | 2026-01-27 | 100% | 100% | Not docs required
1.19 | [9 empty] | Not required
1.20 | Client Handover | 0 | 1 | 1900-01-01 | 2026-02-10 | 5 | 2026-02-17 | 0% | 14.29% | Walk-through only
Formulas:
Planned Start = MIN([Planned Start, row below]:E25)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C39)
Planned End = MAX([Planned End, row below]:G25)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C39)
Actual Start = MIN([Actual Start, row below]:I25)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C39)
Actual End = MAX([Actual End, row below]:K25)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C39)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 312229.88 |  | 377145.79 |  |  | Start Date
2 | Planned Expenditure | 302966 |  | 311634.11
3 | Planned Profit | 9263.88 |  | 65511.68 |  |  | End Date - PC
4 | Planned Margin | 2.967% |  | 17.37%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 50% | 199239.94 | 2025-06-03 | 004751 | 2025-05-26 | 2025-05-31
2 | Handover |  | 50% | 112989.94 | 1900-01-06 | 004938 | 2026-02-05 | 2026-02-12 | there is not Formal Handover, just walk-through
3 | Contigency Fund |  | 0% | 64915.91 | 1900-01-06 | 004938 | 2026-02-05 | 2026-02-12
4 | - |  | 0% | 0
5 | - |  | 0% | 0
6 | - |  | 0%
7 | - |  | 0% | 0
|  |  | 100% | 377145.79
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 132001.0265
2 | Delivery of Panels |  | 30% | 113143.737
3 | Delivery of Inverters |  | 20% | 75429.158
4 | Practical Completion |  | 10% | 37714.579
5 | Handover |  | 5% | 18857.2895
| Total |  | 100% | 377145.79
|  |  | 100% | 377145.79
Formulas:
PLANNED PAYMENT DATE = [PLANNED PAYMENT DATE, row above]
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 302966 |  | 311634.11 | -8668.11
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 0 |  | 0 | 0
2 | 2. Inverters | 0 |  | 0 | 0
3 | 3. Mounting Structures | 0 |  | 0 | 0
4 | 4. DC Equipment | 60000 |  | 19732 | 40268
5 | 5. Monitoring | 0 |  | 0 | 0
6 | 6. AC Equipment | 0 |  | 0 | 0
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 1 |  | 64915.91 | -64914.91
9 | 9. AC & DC installation | 219090 |  | 219492 | -402
10 | 10. Site Logistics | 23000 |  | 7280 | 15720
11 | 11. Due Dilligence | 0 |  | 0 | 0
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 0 |  | 0 | 0
14 | 14. General Expenses | 875 |  | 214.2 | 660.8
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 302966 | 398479.88 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 311634.11
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | [5 empty] | 0 |  |  | 1 | 1. Panels | [8 empty] | 0 |  | 0
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels | [11 empty] | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 0
2 | Inverters | [5 empty] | 0 |  |  | 2 | 2. Inverters | [8 empty] | 0 |  | 0 | DC Equipment | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | AC Labour | 219090
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | DC Labour | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Offloading | 23000
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Scaffolding | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Telehandler | 0
3 | Mounting Structures | [5 empty] | 0 | 0 |  | 3 | 3. Mounting Structures | [8 empty] | 0 |  | 0 | Other | 0
3 | [5 empty] | 1900-01-29 |  |  |  | 3 | 3. Mounting Structures | [11 empty] | Total | 242090
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | Less 15% | 205776.5
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | R/Wp | 0
3 | [9 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | ACTUAL | Installer Price
[23 empty] | AC Equipment | 0
4 | DC Equipment | DC Equipment |  |  | 60000 | 2025-06-30 | 60000 | 72000 |  | 4 | 4. DC Equipment | [7 empty] | 0 | 0 |  | 19732 | DC Equipment | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 321657.25
4 | [5 empty] | 2025-06-12 |  |  |  | 4 | 4. DC Equipment | Removal and Refit - Deposit | 19732 | 50% | 9866 | PO3891-CTOP1-20250604 - RV Approved | Happy Solar INV-0317 | 2025-06-30 | 36000 |  | 2025-06-12 |  | DC Labour | 0
4 | [5 empty] | 2025-07-03 |  |  |  | 4 | 4. DC Equipment | Removal and Refit - Balance |  | 25% | 4933 |  | Happy Solar INV-0317 | 2025-06-30 | 18000 |  | 2025-07-03 |  | Offloading | 5600
4 | [5 empty] | 2025-10-30 |  |  |  |  | 4. DC Equipment | Removal and Refit - Signoff |  | 25% | 4933 |  | Happy Solar INV-0317 | 2025-06-30 | 18000 |  | 2025-12-24
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Scaffolding | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Storage | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Telehandler | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Total | 327257.25
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | R/Wp | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | [5 empty] | 0 |  |  | 5 | 5. Monitoring | [8 empty] | 0 |  | 0
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
6 | AC Equipment | [5 empty] | 0 |  |  | 6 | 6. AC Equipment | [8 empty] | 0 |  | 0
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
7 | BESS | [5 empty] | 0 |  |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 1 | 86250 |  | 8 | 8. Product Add On | [7 empty] | 0 | 21334.09 | 2025-12-24 | 64915.91
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Contigency Fund |  |  | 1 | 2025-06-30 |  |  |  | 8 | 8. Product Add On | Contigency Fund |  |  | 0 |  |  | 2026-02-28 | 0 |  | 2026-02-27
[10 empty] | 8 | 8. Product Add On | Replacement Mounting Structure |  |  | 46645.91 | PO4230-CTOP1-20250818 - RV Approved | Schletter INV2117 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 8 | 8. Product Add On | Replacement Mounting Structure | [5 empty] | 2025-12-31 | 46645.91
[10 empty] | 8 | 8. Product Add On | Additional MS |  |  | 3850 | PO4527-CTOP1-20251208 - RV Approved | Solarworld - SASIV-25-00724 | 2025-12-31 | 3850 |  | 2026-01-07
[10 empty] | 8 | 8. Product Add On | Optimizer Plates + Installation |  |  | 14420 | PO4545-CTOP1-20251218 - RV Approved | Happy Solar INV-0347 | 2025-12-31 | 14420 |  | 2025-12-24
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | Installation Budget |  |  | 219090 | 2025-06-30 | 219090 | 212629.88 |  | 9 | 9. AC & DC installation | [8 empty] | 0 |  | 219492
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [5 empty] | 2025-06-12 |  |  |  | 9 | 9. AC & DC installation | Removal and Refit - Deposit | 219492 | 50% | 109746 | PO3891-CTOP1-20250604 - RV Approved | Happy Solar INV-0317 | 2025-06-30 | 106314.94 |  | 2025-06-12
9 | [5 empty] | 2025-07-03 |  |  |  | 9 | 9. AC & DC installation | Removal and Refit - Balance |  | 25% | 54873 |  | Happy Solar INV-0317 | 2025-06-30 | 53157.47 |  | 2025-07-03
9 | [5 empty] | 2025-10-30 |  |  |  |  | 9. AC & DC installation | Removal and Refit - Signoff |  | 25% | 54873 |  | Happy Solar INV-0317 | 2025-06-30 | 53157.47 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
10 | Site Logistics | Logistics Budget |  |  | 23000 | 2025-06-30 | 23000 | 27600 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 7280
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-06-12 |  |  |  | 10 | 10. Site Logistics | Removal and Refit - Deposit | 7280 | 50% | 3640 | PO3891-CTOP1-20250604 - RV Approved | Happy solar INV-0317 | 2025-06-30 | 13800 |  | 2025-06-12
10 | [5 empty] | 2025-07-03 |  |  |  | 10 | 10. Site Logistics | Removal and Refit - Balance |  | 25% | 1820 |  | Happy Solar INV-0317 | 2025-06-30 | 6900 |  | 2025-07-03
[6 empty] | 2025-10-30 |  |  |  |  | 10. Site Logistics | Removal and Refit - Signoff |  | 25% | 1820 |  | Happy Solar INV-0317 | 2025-06-30 | 6900 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | [5 empty] | 0 |  |  | 11 | 11. Due Dilligence | [8 empty] | 0 |  | 0
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
12 | BDP Commission | [5 empty] | 0 |  |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | [5 empty] | 0 |  |  | 13 | 13. Engineering | [8 empty] | 0 |  | 0
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Travel Budget |  |  | 875 | 2025-07-04 | 875 | 0 |  | 14 | 14. General Expenses | Travel |  |  | 214.2 |  | Expense Claim | 2025-06-30 |  | 0 | 2025-07-04 | 214.2
14 | [5 empty] | 1900-01-06 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 |  |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 |  |  | 2025-08-31
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 |  |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 136107.277 | [16 empty] | 377145.79
| Inverter Procurement Budget | 51963.0691
| Mounting Structure Budget | 70380.5311
| DC Equipment Budget | 96448.2696
| AC Equipment Budget | 150576.8264
| Monitoring Budget | 44852.3333
| Optional Extras Budget | 0
| MV Metering Budget | 0
| ADD ON | 0
| Battery System | 0
| Generator | 0
Services
| AC Installer Budget | 13711.7647
| DC Installer Budget | 32858.8235
| In-House Expense Budget | 50016.3994
| Compliance Budget | 34117.6471
| Offloading Budget | 10000
| Roof Access Budget for Equipment | 0
| Site storage | 0
| On Site Security | 14117.6471
| Roof Access Budget for Installers | 20010
| EPC Management Fee | 0
| ADD ON | 0
Expenses
| Total EE Expense Budget | 1029.4118
Note on W96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date to align with the project plan

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 312229.88 | 199239.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94
| Planned Expenditure | 302966 | 302966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966 | 302966
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06 | -103726.06
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 377145.79 | 377145.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177905.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 199239.94 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79
| Actual + Planned Expenditure | 311634.11 | 311634.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123252 | 0 | 0 | 61840.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46645.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76046 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123252 | 123252 | 123252 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 185092.2 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 231738.11 | 307784.11 | 307784.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11 | 311634.11
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199239.94 | 199239.94 | 75987.94 | 75987.94 | 75987.94 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | 14147.74 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -32498.17 | -108544.17 | -108544.17 | -112394.17 | -112394.17 | -112394.17 | -112394.17 | -112394.17 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68 | 65511.68
|  | CHECK | CHECK
| Revenue Recognition | -64915.91 | 377145.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312229.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64915.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 377145.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 312229.88 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79 | 377145.79

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-12-31 | 2026-02-28 | Grand Total
(blank)
1. Panels
2. Inverters
3. Mounting Structures
4. DC Equipment | 0 | 72000 |  |  |  |  | 72000
5. Monitoring
6. AC Equipment
8. Product Add On | 0 |  |  | 0 | 64915.91 | 0 | 64915.91
9. AC & DC installation |  | 212629.88 |  |  |  |  | 212629.88
10. Site Logistics | 0 | 27600 |  |  |  |  | 27600
11. Due Dilligence
13. Engineering
14. General Expenses
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 312229.88 |  | 0 | 64915.91 | 0 | 377145.79

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-12-31 | 2026-02-28 | Grand Total
(blank)
1. Panels
2. Inverters
3. Mounting Structures
4. DC Equipment |  | 19732 |  |  |  |  | 19732
5. Monitoring
6. AC Equipment
8. Product Add On |  |  |  | 46645.91 | 18270 | 0 | 64915.91
9. AC & DC installation |  | 219492 |  |  |  |  | 219492
10. Site Logistics |  | 7280 |  |  |  |  | 7280
11. Due Dilligence
13. Engineering
14. General Expenses |  | 214.2 | 0 | 0 |  |  | 214.2
15. Service Add On
12. BDP Commission
7.BESS
Grand Total |  | 246718.2 | 0 | 46645.91 | 18270 | 0 | 311634.11

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | China Town Remove and Refit
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | #VALUE! | #REF! |  | #VALUE! | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | #VALUE! | #REF! |  | #VALUE! | #REF!
AC Labour | #REF! | #REF! | 96174 | #VALUE! | #REF! |  | #VALUE! | #REF!
DC Labour | #REF! | #REF! | 230160 | #VALUE! | #REF! |  | #VALUE! | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | #VALUE! | #REF! |  | #VALUE! | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | #VALUE! | #REF!
DC installation | #REF! | #REF! |  | #VALUE! | #REF! |  | #VALUE! | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
China Town Remove and Refit |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | China Town Remove and Refit | 0 | 0 | 0