## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Marikana Old Church
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2037106 |  | 2037106 |  |  |  | Start Date | 1497994.1187 | 1163550.53 | 217893.4614 | 449374.315 | 217893.4614 | 449374.315
2 | Planned Expenditure | 1814310.4741 |  | 1612924.845 | VO PM Limit | Current VO Total
3 | Planned Profit | 222795.5259 |  | 424181.155 | 11139.7763 | 12449 |  | End Date - PC
4 | Planned Margin | 10.94% |  | 20.82%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 407421.2 |  | 2025-06-23 | 004732 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 407421.2 |  | 2025-07-24 | 004732 | 2025-05-01 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 305565.9 |  | 2025-07-24 | 004732 | 2025-05-01 | 2025-07-04
4 | Commissioning Complete |  | 15% | 305565.9 |  | 2025-08-25 | 004732 | 2025-05-01 | 2025-10-24
5 | Final Completion Issued |  | 25% | 509276.5 |  | 2025-08-25 | 004732 | 2025-05-01 | 2025-10-24
6 | Handover |  | 5% | 101855.3 |  | 2025-12-08 | 004732 | 2025-05-01 | 2025-11-14
7 | - |  | 0% | 0
|  |  | 100% | 2037106
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 712987.1
2 | Delivery of Panels |  | 30% | 611131.8
3 | Delivery of Inverters |  | 20% | 407421.2
4 | Practical Completion |  | 10% | 203710.6
5 | Handover |  | 5% | 101855.3
| Total |  | 100% | 2037106
|  |  | 100% | 2037106

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Marikana Old Church | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 175
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 2037106
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 33 |  |  | 77 |  | 97.69% | 100%
1 | Project Initiation | 2025-04-22 | 79 | 2025-07-10 | 2025-04-22 | 97 | 2025-07-28 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-04-22 | 1 | 2025-04-23 | 100% | 100%
1.2 | Project Introduction | 2025-07-09 | 1 | 2025-07-10 | 2025-07-25 | 1 | 2025-07-28 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-22 | 10 | 2025-05-07 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-02 | 1 | 2025-07-03 | 2025-07-18 | 1 | 2025-07-21 | 100% | 100%
1.5 | Project Review | 2025-07-02 | 1 | 2025-07-03 | 2025-07-18 | 1 | 2025-07-21 | 100% | 100%
2 | Site Establishment | 2025-07-16 | 1 | 2025-07-17 | 2025-08-01 | 1 | 2025-08-02 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-07-16 | 1 | 2025-07-17 | 2025-08-01 | 1 | 2025-08-02 | 100% | 100% |  | 55 | Net Work Days
3 | AC Installation | 2025-06-25 | 50 | 2025-08-14 | 2025-06-15 | 80 | 2025-09-03 | 100% | 100% |  | 11 | Total Weeks
3.1 | Inverters delivered | 2025-07-17 | 1 | 2025-07-18 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100% |  | 15.9091 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-07-18 | 5 | 2025-07-25 | 2025-08-25 | 5 | 2025-09-01 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-25 | 25 | 2025-07-30 | 2025-06-15 | 20 | 2025-07-14 | 100% | 100%
3.4 | AC Works | 2025-07-30 | 11 | 2025-08-14 | 2025-08-25 | 5 | 2025-09-01 | 100% | 100%
3.5 | AC Tie-In | 2025-07-30 | 3 | 2025-08-04 | 2025-09-03 | 0 | 2025-09-03 | 100% | 100%
4 | DC Works | 2025-07-16 | 21 | 2025-08-06 | 2025-06-23 | 114 | 2025-10-15 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-07-16 | 1 | 2025-07-17 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
4.2 | Mounting Structure installation | 2025-07-17 | 5 | 2025-07-24 | 2025-09-26 | 5 | 2025-10-03 | 100% | 100%
4.3 | DC Cable delivered | 2025-07-16 | 1 | 2025-07-17 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
4.3 | DC Stringing | 2025-07-29 | 6 | 2025-08-06 | 2025-10-11 | 3 | 2025-10-15 | 100% | 100%
5 | Module installation | 2025-07-17 | 15 | 2025-08-01 | 2025-06-23 | 113 | 2025-10-14 | 100% | 100%
5.1 | Module delivery | 2025-07-17 | 1 | 2025-07-18 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
5.2 | Module mounting | 2025-07-18 | 10 | 2025-08-01 | 2025-10-03 | 7 | 2025-10-14 | 100% | 100%
6 | Commissioning | 2025-08-14 | 4 | 2025-08-18 | 2025-10-15 | 2 | 2025-10-17 | 100% | 100%
6.1 | Commissioning | 2025-08-14 | 1 | 2025-08-15 | 2025-10-15 | 1 | 2025-10-16 | 100% | 100%
6.2 | Practical Completion | 2025-08-15 | 1 | 2025-08-18 | 2025-10-16 | 1 | 2025-10-17 | 100% | 100%
7 | QA Inspections | 2025-08-18 | 1 | 2025-08-19 | 2025-10-20 | 1 | 2025-10-21 | 100% | 100%
7.1 | Red-Team Inspection | 2025-08-18 | 1 | 2025-08-19 | 2025-10-20 | 1 | 2025-10-21 | 100% | 100%
8 | Project Closure | 2025-08-18 | 15 | 2025-09-02 | 2025-10-20 | 42 | 2025-12-01 | 81.48% | 100%
8.1 | Equipment serial numbers | 2025-08-19 | 2 | 2025-08-21 | 2025-10-21 | 2 | 2025-10-23 | 100% | 100%
8.2 | Snags completion | 2025-08-19 | 5 | 2025-08-26 | 2025-10-21 | 5 | 2025-10-28 | 100% | 100%
8.3 | System Performance Monitoring | 2025-08-26 | 5 | 2025-09-02 | 2025-10-28 | 5 | 2025-11-04 | 100% | 100%
8.4 | Handover documentation | 2025-08-18 | 5 | 2025-08-25 | 2025-10-20 | 5 | 2025-10-27 | 100% | 100%
8.5 | Handover to Client | 2025-08-25 | 1 | 2025-08-26 | 2025-11-24 | 5 | 2025-12-01 | 0% | 100% | Redo Handover Documentation
8.6 | Handover to Matriarch | 2025-08-21 | 5 | 2025-08-28 | 2025-10-23 | 5 | 2025-10-30 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 1814310.4741 |  | 1612924.845 | 201385.6291
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 388725.5 |  | 349165.4 | 39560.1
2 | 2. Inverters | 160000 |  | 137740.7 | 22259.3
3 | 3. Mounting Structures | 142681.5 |  | 43754.2 | 98927.3
4 | 4. DC Equipment | 145542.5 |  | 92034.13 | 53508.37
5 | 5. Monitoring | 49000 |  | 35927.14 | 13072.86
6 | 6. AC Equipment | 282181.8174 |  | 277348.89 | 4832.9274
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 144450.33 | -144450.33
9 | 9. AC & DC installation | 138375 |  | 206171.2 | -67796.2
10 | 10. Site Logistics | 45648.6 |  | 251918 | -206269.4
11 | 11. Due Dilligence | 29000 |  | 18617.53 | 10382.47
12 | 12. BDP Commission | 48906.2631 |  | 0 | 48906.2631
13 | 13. Engineering | 81274.2936 |  | 25463.825 | 55810.4686
14 | 14. General Expenses | 2975 |  | 5435.5 | -2460.5
15 | 15. Service Add On | 300000 |  | 24898 | 275102
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1814310.4741 | 2037105.6725 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1612924.845
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 388725.5 | 2025-07-29 | 388725.5 | 462768.4524 |  | 1 | 1. Panels | Jinko 620W - Menlo | 283 | 1233.8 | 349165.4 | PO3910-DIP-PH2-OLDCHUR-20250514 | Menlo Inv0003030 | 2025-06-30 | 462768.4524 | 0 | 2025-07-29 | 349165.4
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 282181.8174
2 | Inverters | Inverter Budget |  |  | 160000 | 2025-07-29 | 160000 | 190476.1905 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 2 | 68870 | 137740.7 | PO3910-DIP-PH2-OLDCHUR-20250514 | Menlo Inv0003030 | 2025-06-30 | 190476.1905 | 0 | 2025-07-29 | 137740.7 | DC Equipment | 86252.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 43875
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 94500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 16748.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 142681.5 | 2025-07-29 | 142681.5 | 169858.9286 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 43754.2 | PO3980-MAROC-20250604 - RV Approved | Schletter Inv: 1851 | 2025-06-30 | 148640.8306 | -0.0020786 | 2025-07-29 | 43754.2 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [6 empty] | 2025-07-31 | 21218.1 |  |  |  | Total | 532057.9174
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 452249.2298
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.5843
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 178056.12
4 | DC Equipment | DC Cable Budget | 4870.25 |  | 59290 | 2025-07-29 | 145542.5 | 173264.881 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 4000 | 13.4 | 53600 | PO3910-DIP-PH2-OLDCHUR-20250514 | Menlo Inv0003030 | 2025-06-30 | 100908.1915 | 0 | 2025-07-29 | 92034.13 | DC Equipment | 38434.13
4 |  | DC Equipment Budget |  |  | 86252.5 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 33167.2
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 173004
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Roof Access | 6572.5
4 | [5 empty] | 2025-06-05 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 38434.13 | 10% | 3843.413 | PO3938-DIP-Ph2OldChurch-20250520 - RV Approved | Greenway Solar - INV0001378 | 2025-05-31 | 7235.6689 |  | 2025-06-05 |  | Offloading & Rigging | 7106
4 | [5 empty] | 2025-07-31 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 5765.1195 |  | Greenway Solar - INV0001390 | 2025-06-30 | 10853.5034 |  | 2025-07-31 |  | P&G | 28919.5
4 | [5 empty] | 2025-10-17 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 7686.826 |  | Greenway Solar - INV0001424 | 2025-07-31 | 14471.3379 |  | 2025-10-24 |  | Telehandler | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 9608.5325 |  | Greenway Solar - INV0001424 | 2025-07-31 | 18089.1724 |  | 2025-10-24 |  | HSE | 4500
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 3843.413 |  | Greenway Solar - INV0001424 | 2025-07-31 | 7235.6689 |  | 2025-10-30 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 3843.413 |  | Greenway Solar - INV0001424 | 2025-07-31 | 7235.6689 |  | 2026-01-29 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 1921.7065 |  | Greenway Solar - INV0001424 | 2025-07-31 | 3617.8345 |  | 2026-02-05 |  | Total | 469759.45
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 1921.7065 |  | Greenway Solar - INV0001424 | 2025-07-31 | 3617.8345 |  | 2026-03-07 |  | R/Wp | 2.6843
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 58333.3333 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3910-DIP-PH2-OLDCHUR-20250514 | Menlo INV0002937 | 2025-05-31 | 12861.7245 | -0.00054447 | 2025-07-17 | 35927.14
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3840-DIP-Ph2-Mari-Chu-20250429 - RV Approved | Accuenergy Inv: ASAI-005366 | 2025-04-30 | 20024.4392 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 4340.6433 |  | 2025-07-29
5 | [5 empty] | 0 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 17786.6891 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3319.8378 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 282181.8174 | 2025-08-29 | 282181.8174 | 335930.735 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.00024397 |  | 277348.89
6 | [5 empty] | 2025-08-30 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 99292.77 | PO3929-DIP-Ph2-OldChurch-20250519 - RV Approved | Switchboard Inv:2-SOI002192 | 2025-07-31 | 119778.5449 |  | 2025-08-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-06-05 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 178056.12 | 10% | 17805.612 | PO3938-DIP-Ph2OldChurch-20250520 - RV Approved | Greenway Solar - INV0001378 | 2025-05-31 | 21761.2951 |  | 2025-06-05
6 | [5 empty] | 2025-07-31 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 26708.418 |  | Greenway Solar - INV0001390 | 2025-06-30 | 32641.9427 |  | 2025-07-31
6 | [5 empty] | 2025-10-17 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 35611.224 |  | Greenway Solar - INV0001424 | 2025-07-31 | 43133.054 |  | 2025-10-24
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 44514.03 |  | Greenway Solar - INV0001424 | 2025-07-31 | 53916.3175 |  | 2025-10-24
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 17805.612 |  | Greenway Solar - INV0001424 | 2025-07-31 | 21566.527 |  | 2025-10-30
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 17805.612 |  | Greenway Solar - INV0001424 | 2025-07-31 | 21566.527 |  | 2026-01-29
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 8902.806 |  | Greenway Solar - INV0001424 | 2025-07-31 | 10783.2635 |  | 2026-02-05
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 8902.806 |  | Greenway Solar - INV0001424 | 2025-07-31 | 10783.2635 |  | 2026-03-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | Estop |  |  | 695 | PO4397-MAROC-20251023 - RV Approved | The Greenway - INV0001511 | 2025-10-31 |  | 0 | 2025-10-31 | 144450.33
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Inverter Cage with Roof |  |  | 69652 | PO4024-MAR-OC-20250623 - RV Approved | The Engineering Hub INV/2025/06/0577 | 2025-06-30 |  |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | Inverter room Budget | 75% | 59495 | 44621.25 | PO4321-MAR-OC-20250919 - RV Approved | Van Staden Three INV3000 | 2025-09-30 |  |  | 2025-10-02
8 | [5 empty] | 2025-10-31 |  |  |  | 8 | 8. Product Add On |  | 25% |  | 14873.75 |  | Van Staden Three INV3038 | 2025-10-31 |  |  | 2025-10-31
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | Waterpoints |  |  | 6483.33 | PO4326-MAR-OC-20250929 - RV Approved | Van Staden Group Inv: 1655 | 2025-09-30 |  |  | 2025-10-13
8 | [9 empty] | 8 | 8. Product Add On | Strapping of Trays |  |  | 2036 | PO4412-MAROC-20251027 - RV Approved | The Greenway INV0001525 | 2025-10-31 |  |  | 2025-10-31
8 | [9 empty] | 8 | 8. Product Add On | Modification of inverter cage |  |  | 6089 | PO4574-MAROC-20260126 - RV Approved | The Engineering Hub INV/2026/01/0253 | 2026-01-31 |  |  | 2026-02-28
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 43875 | 2025-06-04 | 138375 | 162794.1176 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 206171.2
9 |  | DC Installation Budget |  |  | 94500 | 2025-06-05 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 206171.2 | 10% | 20617.12 | PO3938-DIP-Ph2OldChurch-20250520 - RV Approved | Greenway Solar - INV0001378 | 2025-05-31 | 16279.4118 |  | 2025-06-05
9 | [5 empty] | 2025-07-31 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 30925.68 |  | Greenway Solar - INV0001390 | 2025-06-30 | 24419.1176 |  | 2025-07-31
9 | [5 empty] | 2025-10-17 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 41234.24 |  | Greenway Solar - INV0001424 | 2025-08-31 | 32558.8235 |  | 2025-10-24
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 51542.8 |  | Greenway Solar - INV0001424 | 2025-10-31 | 40698.5294 |  | 2025-10-24
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 20617.12 |  | Greenway Solar - INV0001424 | 2025-10-31 | 16279.4118 |  | 2025-10-30
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 20617.12 |  | Greenway Solar - INV0001424 | 2025-10-31 | 16279.4118 |  | 2026-01-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 10308.56 |  | Greenway Solar - INV0001424 | 2025-10-31 | 8139.7059 |  | 2026-02-05
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 10308.56 |  | Greenway Solar - INV0001424 | 2025-10-31 | 8139.7059 |  | 2026-03-07
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-09-28 | 45648.6 | 53704.2353 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0014691 |  | 251918
[6 empty] | 2025-09-29 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-10-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | Security - August |  |  | 48560 | PO4256-MAROC-20250831 - RV Approved | JerryG & Sons INV12 | 2025-09-30 | 23508.1851 |  | 2025-10-02
10 |  | Scaffolding |  |  | 16748.6 | 2025-10-03 |  |  |  | 10 | 10. Site Logistics | Security - October |  |  | 41230 |  | JerryG & Sons INV15 | 2025-10-31 | 0 |  | 2025-11-06
10 |  | Security |  |  | 20400 | 2025-10-04 |  |  |  | 10 | 10. Site Logistics | Security - November |  |  | 39900 |  | JerryG& Sons INV19 | 2025-11-30 |  |  | 2025-11-28
10 |  | Storage |  |  | 0 | 2025-10-05 |  |  |  | 10 | 10. Site Logistics | Security - December |  |  | 41230 |  | JerryG& Sons INV23 | 2025-12-31 |  |  | 2026-01-09
[10 empty] | 10 | 10. Site Logistics | Security - January |  |  | 33900 |  | JerryG & Sons INV25 | 2026-01-31 |  |  | 2026-01-29
[10 empty] | 10 | 10. Site Logistics
10 | [5 empty] | 2025-06-05 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 47098 | 10% | 4709.8 | PO3938-DIP-Ph2OldChurch-20250520 - RV Approved | Greenway Solar - INV0001378 | 2025-05-31 | 1610.0536 |  | 2025-06-05
10 | [5 empty] | 2025-07-31 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 7064.7 |  | Greenway Solar - INV0001390 | 2025-06-30 | 5938.9575 |  | 2025-07-31
10 | [5 empty] | 2025-10-17 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 9419.6 |  | Greenway Solar - INV0001424 | 2025-07-31 | 6039.21 |  | 2025-10-24
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 11774.5 |  | Greenway Solar - INV0001424 | 2025-07-31 | 7549.0125 |  | 2025-10-24
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4709.8 |  | Greenway Solar - INV0001424 | 2025-07-31 | 3019.605 |  | 2025-10-30
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4709.8 |  | Greenway Solar - INV0001424 | 2025-07-31 | 3019.605 |  | 2026-01-29
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2354.9 |  | Greenway Solar - INV0001424 | 2025-07-31 | 1509.8025 |  | 2026-02-05
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2354.9 |  | Greenway Solar - INV0001424 | 2025-07-31 | 1509.8025 |  | 2026-03-07
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-04-09 | 29000 | 34117.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 4805.78 |  | Sunspot E027 | 2025-07-31 | 12380.696 | -0.0043606 | 2025-11-30 | 18617.53
11 |  | Structural Sign Off |  |  | 18000 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7811.75 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 10741.6256 |  | 2025-04-10
11 | [5 empty] | 2025-04-11 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5370 | 2025-10-31 | 10995.3298 |  | 2025-11-28
11 | [5 empty] | 2025-04-12 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-04-13 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-04-14
12 | BDP Commission | Referral Fee |  |  | 40755.2192 | 2025-04-15 | 48906.2631 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 8151.0438 | 2025-04-16 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-04-17
13 | Engineering | Matriarch Defects Period |  |  | 17264.4365 | 2025-04-18 | 81274.2936 | 92357.1518 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 25463.825 |  | Matriarch - INV-5369 | 2025-10-31 | 92357.1518 | 0 | 2025-11-28 | 25463.825
13 |  | Management |  |  | 9714.2857 | 2025-04-19 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 28900 | 2025-04-20 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 12628.5714 | 2025-04-21 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 12767 | 2025-04-22 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2975 | 2025-03-31 | 2975 | 3500 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | -0.0018094 | 2025-03-31 | 5435.5
14 | [5 empty] | 2025-04-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-05-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-05-31 | 0 |  | 2025-05-31
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3959.01 |  | Expense Claim | 2025-06-30 | 1391.3567 |  | 2025-07-04
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1476.49 |  | Expense Claim | 2025-08-31 | 612.6151 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-31
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 1496.03 |  | 2025-12-05
14 | [5 empty] | 2025-12-01 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [5 empty] | 2025-12-02 |  |  |  | 14 | 14. General Expenses | [7 empty] | 0
14 | [5 empty] | 2025-12-03 |  |  |  | 14 | 14. General Expenses | [7 empty] | 0
2025-12-04
15 | Service Add On | Welcome Bonus |  |  | 300000 | 2025-12-05 | 300000 | 300000 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 24898
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  | 2025-08-31 | 300000
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | New Installer Contigency Fund |  |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Delays and standing time - VO | 24898 | 50% | 12449 | PO4433-MAROC-20251031 - RV Approved | The Greenway Soalr - INV0001516 | 2025-10-31 |  |  | 2025-11-06
15 | [9 empty] | 15 | 15. Service Add On |  |  | 50% | 12449 |  | The Greenway Soalr - INV0001516 | 2025-10-31 |  |  | 2026-03-07
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 388725.5 |  | 462768.4524 | [14 empty] | 2037105.6801
| Inverter Procurement Budget | 160000 |  | 190476.1905
| Mounting Structure Budget | 142681.5 |  | 169858.9286
| DC Equipment Budget | 145542.5 |  | 173264.881
| AC Equipment Budget | 282181.8174 |  | 335930.735
| Monitoring Budget | 49000 |  | 58333.3333
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 43875 |  | 51617.6471
| DC Installer Budget | 94500 |  | 111176.4706
| In-House Expense Budget | 81274.2936 |  | 92357.1518
| Compliance Budget | 29000 |  | 34117.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 20400 |  | 24000
| Roof Access Budget for Installers | 16748.6 |  | 19704.2353
| EPC Management Fee | 0 |  | 0
| ADD ON | 300000 |  | 300000
Expenses
| Total EE Expense Budget | 2975 |  | 3500

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2037106 | 2037106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407421.2 | 0 | 0 | 0 | 712987.1 | 0 | 0 | 0 | 0 | 814842.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101855.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 1935250.7 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106
| Planned Expenditure | 1814310.4741 | 1814310.4741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2975 | 29000 | 104784.9853 | 25395.5714 | 0 | 0 | 0 | 0 | 15000 | 138375 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 836949.5 | 0 | 0 | 0 | 282181.8174 | 0 | 0 | 0 | 8500 | 37148.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2975 | 31975 | 136759.9853 | 162155.5567 | 162155.5567 | 162155.5567 | 162155.5567 | 162155.5567 | 177155.5567 | 315530.5567 | 315530.5567 | 315530.5567 | 315530.5567 | 315530.5567 | 315530.5567 | 349530.5567 | 349530.5567 | 1186480.0567 | 1186480.0567 | 1186480.0567 | 1186480.0567 | 1468661.8741 | 1468661.8741 | 1468661.8741 | 1468661.8741 | 1477161.8741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1514310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741 | 1814310.4741
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2975 | -31975 | -136759.9853 | -162155.5567 | -162155.5567 | -162155.5567 | -162155.5567 | -162155.5567 | -177155.5567 | -315530.5567 | -315530.5567 | -315530.5567 | 91890.6433 | 91890.6433 | 91890.6433 | 57890.6433 | 770877.7433 | -66071.7567 | -66071.7567 | -66071.7567 | -66071.7567 | 466588.8259 | 466588.8259 | 466588.8259 | 466588.8259 | 458088.8259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 420940.2259 | 120940.2259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259 | 222795.5259
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2037106 | 2037106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407421.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712987.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814842.4 | 0 | 0 | 101855.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 407421.2 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1120408.3 | 1935250.7 | 1935250.7 | 1935250.7 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106 | 2037106
| Actual + Planned Expenditure | 1612924.845 | 1612924.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 0 | 0 | 0 | 0 | 0 | 2250.5 | 13695 | 46975.945 | 0 | 0 | 0 | 15128.01 | 0 | 8598.35 | 0 | 724590.5075 | 0 | 0 | 0 | 99292.77 | 1476.49 | 0 | 0 | 0 | 93181.25 | 0 | 6483.33 | 211391.7525 | 64580.695 | 53679 | 0 | 0 | 76169.605 | 0 | 0 | 0 | 0 | 0 | 41230 | 0 | 0 | 80875.945 | 23487.9725 | 0 | 0 | 6089 | 35936.9725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 10062.25 | 23757.25 | 70733.195 | 70733.195 | 70733.195 | 70733.195 | 85861.205 | 85861.205 | 94459.555 | 94459.555 | 819050.0625 | 819050.0625 | 819050.0625 | 819050.0625 | 918342.8325 | 919819.3225 | 919819.3225 | 919819.3225 | 919819.3225 | 1013000.5725 | 1013000.5725 | 1019483.9025 | 1230875.655 | 1295456.35 | 1349135.35 | 1349135.35 | 1349135.35 | 1425304.955 | 1425304.955 | 1425304.955 | 1425304.955 | 1425304.955 | 1425304.955 | 1466534.955 | 1466534.955 | 1466534.955 | 1547410.9 | 1570898.8725 | 1570898.8725 | 1570898.8725 | 1576987.8725 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845 | 1612924.845
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7811.75 | -7811.75 | -7811.75 | 399609.45 | 399609.45 | 399609.45 | 397358.95 | 383663.95 | 336688.005 | 336688.005 | 336688.005 | 336688.005 | 1034547.095 | 1034547.095 | 1025948.745 | 1025948.745 | 301358.2375 | 301358.2375 | 301358.2375 | 301358.2375 | 202065.4675 | 200588.9775 | 200588.9775 | 200588.9775 | 200588.9775 | 107407.7275 | 107407.7275 | 100924.3975 | 704375.045 | 639794.35 | 586115.35 | 687970.65 | 687970.65 | 611801.045 | 611801.045 | 611801.045 | 611801.045 | 611801.045 | 611801.045 | 570571.045 | 570571.045 | 570571.045 | 489695.1 | 466207.1275 | 466207.1275 | 466207.1275 | 460118.1275 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155 | 424181.155
|  | CHECK | CHECK
| Revenue Recognition | 0.3199 | 2037105.6801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30766.0648 | 0 | 0 | 0 | 63067.9917 | 0 | 0 | 0 | 0 | 1000165.8754 | 0 | 0 | 0 | 392040.8481 | 0 | 0 | 0 | 333171.4387 | 0 | 0 | 0 | 0 | 23508.1851 | 0 | 0 | 0 | 192889.2463 | 0 | 0 | 0 | 1496.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2037105.6801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30766.0648 | 30766.0648 | 30766.0648 | 30766.0648 | 93834.0565 | 93834.0565 | 93834.0565 | 93834.0565 | 93834.0565 | 1093999.9319 | 1093999.9319 | 1093999.9319 | 1093999.9319 | 1486040.78 | 1486040.78 | 1486040.78 | 1486040.78 | 1819212.2187 | 1819212.2187 | 1819212.2187 | 1819212.2187 | 1819212.2187 | 1842720.4038 | 1842720.4038 | 1842720.4038 | 1842720.4038 | 2035609.6501 | 2035609.6501 | 2035609.6501 | 2035609.6501 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801 | 2037105.6801

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  |  | 462768.4524 | [6 empty] | 0 |  | 462768.4524
2. Inverters |  |  |  | 190476.1905 | [6 empty] | 0 |  | 190476.1905
3. Mounting Structures | 0 |  |  | 148640.8306 | 21218.1 | [5 empty] | 0 |  | 169858.9306
4. DC Equipment |  |  | 7235.6689 | 111761.695 | 54267.5171 | [5 empty] | 0 |  | 173264.881
5. Monitoring |  | 20024.4392 | 16181.5623 | 22127.3325 | [6 empty] | 0 |  | 58333.3339
6. AC Equipment |  |  | 21761.2951 | 32641.9427 | 281527.4975 | [5 empty] | 0 |  | 335930.7352
8. Product Add On
9. AC & DC installation |  |  | 16279.4118 | 24419.1176 |  | 32558.8235 |  | 89536.7647 |  |  | 0 |  | 162794.1176
10. Site Logistics | 0 |  | 1610.0536 | 5938.9575 | 22647.0376 |  | 23508.1851 | 0 |  |  | 0 |  | 53704.2338
11. Due Dilligence |  | 10741.6256 |  |  | 12380.696 |  |  | 10995.3298 |  |  | 0 |  | 34117.6514
13. Engineering | 0 | [6 empty] | 92357.1518 |  |  | 0 |  | 92357.1518
14. General Expenses | 0 | 0 | 0 | 1391.3567 | 0 | 612.6151 | 0 | 0 | 1496.03 |  | 0 |  | 3500.0018
15. Service Add On | [5 empty] | 300000 | [6 empty] | 300000
12. BDP Commission
7.BESS
Grand Total | 0 | 30766.0648 | 63067.9917 | 1000165.8754 | 392040.8481 | 333171.4387 | 23508.1851 | 192889.2463 | 1496.03 |  | 0 |  | 2037105.6801
[6 empty] | 1819212.22 | 23508.19 |  |  |  |  | 1842720.41
-1842720.41

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  |  | 349165.4 | [7 empty] | 349165.4
2. Inverters |  |  |  | 137740.7 | [7 empty] | 137740.7
3. Mounting Structures |  |  |  | 43754.2 | [7 empty] | 43754.2
4. DC Equipment |  |  | 3843.413 | 59365.1195 | 28825.5975 | [6 empty] | 92034.13
5. Monitoring |  | 13695 | 10848.85 | 11383.29 | [7 empty] | 35927.14
6. AC Equipment |  |  | 17805.612 | 26708.418 | 232834.86 | [6 empty] | 277348.89
8. Product Add On |  |  |  | 69652 |  |  | 51104.58 | 17604.75 |  |  | 6089 | 144450.33
9. AC & DC installation |  |  | 20617.12 | 30925.68 |  | 41234.24 |  | 113394.16 |  |  |  | 206171.2
10. Site Logistics |  |  | 4709.8 | 7064.7 | 35323.5 |  | 48560 | 41230 | 39900 | 41230 | 33900 | 251918
11. Due Dilligence |  | 7811.75 |  |  | 4805.78 |  |  | 6000 |  |  |  | 18617.53
13. Engineering | 0 | [6 empty] | 25463.825 |  |  |  | 25463.825
14. General Expenses | 0 | 0 | 0 | 3959.01 | 0 | 1476.49 | 0 | 0 | 0 |  |  | 5435.5
15. Service Add On | 0 |  |  |  |  | 0 |  | 24898 |  |  |  | 24898
12. BDP Commission
7.BESS
Grand Total | 0 | 21506.75 | 57824.795 | 739718.5175 | 301789.7375 | 42710.73 | 99664.58 | 228590.735 | 39900 | 41230 | 39989 | 1612924.845

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.588 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.81233 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.54957 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 1.3152 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Marikana Old Church |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Marikana Old Church | 0 | 0 | 0