## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-03-03 | 2026-03-03
| PROJECT PLAN | Waterside | [7 empty] | 0 | 1
| PROJECT SIZE (kWp) | 55
| PROJECT DEVELOPER | Natasha Watkins-Baker |  |  |  | Target Month | 2025-08-31
| PROJECT MANAGERS | Amanda Gadla
| CONTRACT VALUE | 828367.2456
| Phase: | Commercial Close out
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status |  | Comment
|  |  | 17 |  |  | 47 |  | 100% | 100%
1 | Project Initiation | 2025-08-04 | 72 | 2025-10-15 | 2025-08-04 | 63 | 2025-10-06 | 100% | 100% | 63
1.1 | BD Handover | 2025-08-04 | 1 | 2025-08-05 | 2025-08-04 | 1 | 2025-08-05 | 100% | 100%
1.2 | Project Introduction | 2025-10-03 | 1 | 2025-10-06 | 2025-10-03 | 1 | 2025-10-06 | 100% | 100%
1.3 | HSE | 2025-10-03 | 8 | 2025-10-15 | 2025-09-15 | 8 | 2025-09-26 | 100% | 100%
1.4 | Installer Kick Off | 2025-10-03 | 1 | 2025-10-06 | 2025-10-03 | 1 | 2025-10-06 | 100% | 100%
1.5 | Project Review | 2025-09-26 | 1 | 2025-09-29 | 2025-09-26 | 1 | 2025-09-29 | 100% | 100%
2 | Site Establishment | 2025-10-17 | 1 | 2025-10-18 | 2025-10-17 | 1 | 2025-10-18 | 100% | 100% | 1
2.1 | Solar Contractor Establishment | 2025-10-17 | 1 | 2025-10-18 | 2025-10-17 | 1 | 2025-10-18 | 100% | 100% | 1 |  | 34 | Net Work Days
3 | AC Installation | 2025-09-19 | 38 | 2025-10-27 | 2025-09-19 | 59 | 2025-11-17 | 100% | 100% | 59 |  | 6.8 | Total Weeks
3.1 | Inverters delivered | 2025-10-17 | 1 | 2025-10-20 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100% |  |  | 8.0882 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-10-20 | 2 | 2025-10-22 | 2025-10-20 | 2 | 2025-10-22 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-09-19 | 20 | 2025-10-20 | 2025-09-19 | 20 | 2025-10-20 | 100% | 100%
3.4 | AC Works | 2025-10-20 | 5 | 2025-10-27 | 2025-10-20 | 19 | 2025-11-14 | 100% | 100%
3.5 | AC Tie-In | 2025-10-20 | 1 | 2025-10-21 | 2025-11-14 | 1 | 2025-11-17 | 100% | 100%
4 | DC Works | 2025-10-17 | 13 | 2025-10-30 | 2025-10-17 | 45 | 2025-12-01 | 100% | 100% | 45
4.1 | Lifeline Installation | 2025-08-25 | 2 | 2025-08-27 | 2025-10-14 | 4 | 2025-10-20 | 100% | 100%
4.1 | Mounting Structure delivered | 2025-10-17 | 1 | 2025-10-20 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
4.2 | Mounting Structure installation | 2025-10-20 | 3 | 2025-10-23 | 2025-10-17 | 15 | 2025-11-07 | 100% | 100%
4.7 | DC Cable delivered | 2025-10-17 | 1 | 2025-10-20 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
4.8 | DC Stringing | 2025-10-26 | 4 | 2025-10-30 | 2025-11-25 | 4 | 2025-12-01 | 100% | 100%
5 | Module installation | 2025-10-17 | 12 | 2025-10-29 | 2025-10-17 | 42 | 2025-11-28 | 100% | 100% | 1900-02-10
5.1 | Module delivery | 2025-10-17 | 1 | 2025-10-20 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
5.2 | Module mounting | 2025-10-23 | 4 | 2025-10-29 | 2025-11-07 | 15 | 2025-11-28 | 100% | 100%
6 | Commissioning | 2025-10-30 | 4 | 2025-11-03 | 2025-12-01 | 2 | 2025-12-03 | 100% | 100% | 2
6.1 | Commissioning | 2025-10-30 | 1 | 2025-10-31 | 2025-12-01 | 1 | 2025-12-02 | 100% | 100%
6.2 | Practical Completion | 2025-10-31 | 1 | 2025-11-03 | 2025-12-02 | 1 | 2025-12-03 | 100% | 100%
7 | QA Inspections | 2025-10-30 | 1 | 2025-10-31 | 2025-12-01 | 1 | 2025-12-02 | 100% | 100% | 1899-12-31
7.1 | Red-Team Inspection | 2025-10-30 | 1 | 2025-10-31 | 2025-12-01 | 1 | 2025-12-02 | 100% | 100%
8 | Project Closure | 2025-10-31 | 19 | 2025-11-19 | 2025-12-03 | 78 | 2026-02-19 | 100% | 100% | 1900-03-18
8.1 | Equipment serial numbers | 2025-10-31 | 1 | 2025-11-03 | 2026-01-12 | 1 | 2026-01-13 | 100% | 100%
8.2 | Snags completion | 2025-10-31 | 5 | 2025-11-07 | 2026-01-14 | 5 | 2026-01-21 | 100% | 100%
8.3 | System Performance Monitoring | 2025-11-03 | 5 | 2025-11-10 | 2025-12-03 | 26 | 2026-01-12 | 100% | 100%
8.4 | Handover documentation | 2025-11-07 | 1 | 2025-11-10 | 2026-01-21 | 15 | 2026-02-11 | 100% | 100%
8.5 | Handover to Client | 2025-11-10 | 1 | 2025-11-11 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100%
8.6 | Handover to Matriarch | 2025-11-12 | 5 | 2025-11-19 | 2026-02-16 | 3 | 2026-02-19 | 100% | 100%
Formulas:
Natasha Watkins-Baker = MIN([Natasha Watkins-Baker, row below]:E16)
Natasha Watkins-Baker = [Natasha Watkins-Baker, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Natasha Watkins-Baker],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C14)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 828367.2456 |  | 828367.2456 |  | 828367.2456 | Start Date | 199028.1323 | 126955.22 | 627398.7135 | 500552.2306 | 627398.7135 | 496567.2306
2 | Planned Expenditure | 686839.1931 |  | 617007.4506 |  | 646679.6606 | 2025-09-29
3 | Planned Profit | 141528.0524 |  | 211359.795 |  | 181687.585 | End Date - PC
4 | Planned Margin | 17.09% |  | 25.52% |  | 21.93% | 2025-11-04
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 414183.6228 | 2025-08-21 | 004814 | 2025-08-13 | 2025-08-15 | [5 empty] | 1900-01-06
2 | Delivery of Panels |  | 10% | 82836.7246 | 2025-10-24 | 004875 | 2025-11-07 | 2025-11-25
3 | Delivery of Inverters |  | 25% | 207091.8114 | 2025-10-24 | 004875 | 2025-11-07 | 2025-11-25
4 | Practical Completion |  | 10% | 82836.7246 | 2025-11-10 | 004915 | 2026-01-16 | 2026-01-30
5 | Handover |  | 5% | 41418.3623 | 2025-11-17 | 004950 | 2026-02-25 | 2026-03-04
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 828367.2456
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 289928.536
2 | Delivery of Panels |  | 30% | 248510.1737
3 | Delivery of Inverters |  | 20% | 165673.4491
4 | Practical Completion |  | 10% | 82836.7246
5 | Handover |  | 5% | 41418.3623
| Total |  | 100% | 828367.2456
|  |  | 100% | 828367.2456
Formulas:
PAYMENT RECEIVED DATE = [INVOICE RAISED DATE]+7
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 686839.1931 |  | 617007.4506 | 69831.7426
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 167702.96 |  | 109496.5 | 58206.46
2 | 2. Inverters | 47500 |  | 45062.94 | 2437.06
3 | 3. Mounting Structures | 47059.2 |  | 46570.22 | 488.98
4 | 4. DC Equipment | 87218.6 |  | 96597 | -9378.4
5 | 5. Monitoring | 41000 |  | 36624.44 | 4375.56
6 | 6. AC Equipment | 131329.9826 |  | 79639.74 | 51690.2426
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 4000 |  | 49945.96 | -45945.96
9 | 9. AC & DC installation | 45600 |  | 88732 | -43132
10 | 10. Site Logistics | 37508.5 |  | 35568 | 1940.5
11 | 11. Due Dilligence | 29000 |  | 13690.9 | 15309.1
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 48044.9505 |  | 10354.5906 | 37690.36
14 | 14. General Expenses | 875 |  | 740.16 | 134.84
15 | 15. Service Add On | 0 |  | 3985 | -3985
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 686839.1931 | 828367.2456 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 617007.4506
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 167702.96 | 2025-10-31 | 167702.96 | 204515.8049 |  | 1 | 1. Panels | Jinko 590 modules - Menlo | 93 | 1150.5 | 106996.5 |  | Menlo - INV0003286 | 2025-09-30 | 199846.345 | 0 | 2025-11-28 | 109496.5
1 |  | Delivery Budget |  |  |  | 2025-11-29 |  |  |  | 1 | 1. Panels |  |  |  | 2500 |  | Menlo - INV0003286 | 2025-09-30 | 4669.4599 |  | 2025-11-28
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 131329.9826
2 | Inverters | Inverter Budget |  |  | 47500 | 2025-08-31 | 47500 | 57926.8293 |  | 2 | 2. Inverters | Huawei 50KTL (Boundary stock to move - CPT store) | 1 | 43606.08 | 45062.94 |  | Allocated from Boundary Terraces | 2025-08-31 | 57926.8293 | 0 | 2025-08-31 | 45062.94 | DC Equipment | 67198.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 13680
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 31920
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 17008.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 47059.2 | 2025-08-31 | 47059.2 | 57389.2683 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 41240.97 | PO4258-WATER-20250831 - RV Approved | Schletter - INV2213 | 2025-09-30 | 57389.2683 | 0 | 2025-10-30 | 46570.22 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 269637.0826
3 | [9 empty] | 3 | 3. Mounting Structures | Additional Rails |  |  | 5329.25 | PO4427-WATER-20251030 - RV Approved | Schletter - INV2374 | 2025-10-31 | 0 |  | 2025-11-28 |  | Less 15% | 229191.5202
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 4.1671
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 25836
4 | DC Equipment | DC Cable Budget | 1644.5 |  | 20020 | 2025-08-31 | 87218.6 | 106364.1463 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 4000 | 14 | 54600 |  | Menlo - INV0003286 | 2025-09-30 | 60125.0895 | -6.7026 | 2025-11-28 | 96597 | DC Equipment | 41990
4 |  | DC Equipment Budget |  |  | 67198.6 | 2025-08-31 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 29332
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 59400
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Roof Access | 29818
4 | [5 empty] | 2025-09-18 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 41990 | 10% | 4199 | PO4309-WATER-20250915 - RV Approved | Matthews Group - INV1533 | 2025-09-30 | 4623.9057 |  | 2025-09-18 |  | HSE | 5750
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 6298.5 |  | Matthews Group - INV1548 | 2025-10-31 | 6935.8585 |  | 2025-10-24 |  | Geda
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 8398 |  | Matthews Group - INV1564 | 2025-11-30 | 9247.8114 |  | 2025-12-04 |  | Logistics | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 10497.5 |  | Matthews Group - INV1565 | 2025-11-30 | 11559.7642 |  | 2025-11-28 |  | HSE | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 4206 |  | Matthews Group - INV-1572 | 2025-12-31 | 4631.2784 |  | 2026-02-12 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 4199 |  | Matthews Group - INV-1573 | 2025-12-31 | 4623.5706 |  | 2026-02-12 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 2099.5 |  | Matthews Group - INV-1574 | 2025-12-31 | 2311.7853 |  | 2026-02-12 |  | Total | 192126
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 2099.5 |  | Matthews Group - INV-1575 | 2025-12-31 | 2311.7853 |  | 2026-03-14 |  | R/Wp | 3.4932
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 26000 | 2025-09-26 | 41000 | 50000 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo - INV0003286 | 2025-09-30 | 11738.5276 | 1947.1052 | 2025-09-26 | 36624.44
5 |  | Revenue Metering |  |  | 15000 | 2025-09-26 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14668 |  | Accuenergy - ASAI-006135 | 2025-08-31 | 18293.2274 |  | 2025-09-30
5 | [5 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch INV-5207 | 2025-10-31 | 15248.0147 |  | 2025-11-13
5 | [5 empty] | 2025-08-30 |  |  |  | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole Energy: SO-35689 | 2025-08-31 | 1215.9733 |  | 2025-08-30
5 | [5 empty] | 2025-08-30 |  |  |  | 5 | 5. Monitoring | Powersupply |  |  | 850 |  | Mantech-SOR1007853 | 2025-08-31 | 1060.0793 |  | 2025-08-30
5 | [5 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring |  |  |  | -850 |  | Mantech - CRN949171 | 2025-09-30 | -1160.4273 |  | 2025-09-30
5 | [5 empty] | 2025-09-10 |  |  |  | 5 | 5. Monitoring | Battery |  |  | 1214.1 |  | Current Automotion - SOQ324142 | 2025-09-30 | 1657.4997 |  | 2025-09-10
6 | AC Equipment | AC Equipment Budget |  |  | 131329.9826 | 2025-09-10 | 131329.9826 | 160158.5154 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 79639.74
6 | [5 empty] | 1900-01-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 53803.74 |  | Switchboard Group 2-SOI0011237 | 2025-08-31 | 108201.3467 |  | 2025-09-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-09-18 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 25836 | 10% | 2583.6 | PO4309-WATER-20250915 - RV Approved | Matthews Group - INV1533 | 2025-09-30 | 5195.7169 |  | 2025-09-18
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 3875.4 |  | Matthews Group - INV1548 | 2025-10-31 | 7793.5753 |  | 2025-10-24
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 5167.2 |  | Matthews Group - INV1564 | 2025-11-30 | 10391.4337 |  | 2025-12-04
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 6459 |  | Matthews Group - INV1565 | 2025-11-30 | 12989.2922 |  | 2025-11-28
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 2583.6 |  | Matthews Group - INV-1572 | 2025-12-31 | 5195.7169 |  | 2026-02-12
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 2583.6 |  | Matthews Group - INV-1573 | 2025-12-31 | 5195.7169 |  | 2026-02-12
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 1291.8 |  | Matthews Group - INV-1574 | 2025-12-31 | 2597.8584 |  | 2026-02-12
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 1291.8 |  | Matthews Group - INV-1575 | 2025-12-31 | 2597.8584 |  | 2026-03-14
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 4000 | 4494.382 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 49945.96
8 | [9 empty] | 8 | 8. Product Add On
8 |  | Check Meter |  |  | 4000 | 2025-09-11 |  |  |  | 8 | 8. Product Add On | Check Meter |  |  | 3600 | PO4240-ARIM-20250819 - RV Approved | CBB - CBB-5722 | 2025-08-31 | 323.9456 |  | 2025-09-11
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | -14 |  |  |  | 8 | 8. Product Add On | Anchor Points - Deposit | 46345.96 | 50% | 23172.98 | PO4278-WSD-20250826 - RV Approved | Accend Rope Access - INV-4926 | 2025-10-31 | 2085.2182 |  | 2025-10-24
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Anchor Points - Balance |  | 50% | 23172.98 |  | Accend Rope Access - INV-4926 | 2025-10-31 | 2085.2182 |  | 2026-01-29
8 | [5 empty] | 2025-08-31 |  |  |  | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 13680 | 2025-09-18 | 45600 | 53647.0588 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 88732
9 |  | DC Installation Budget |  |  | 31920 | 2025-09-18 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 88732 | 10% | 8873.2 | PO4309-WATER-20250915 - RV Approved | Matthews Group - INV1533 | 2025-09-30 | 5364.7059 |  | 2025-09-18
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 13309.8 |  | Matthews Group - INV1548 | 2025-10-31 | 8047.0588 |  | 2025-10-24
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 17746.4 |  | Matthews Group - INV1564 | 2025-11-30 | 10729.4118 |  | 2025-12-04
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 22183 |  | Matthews Group - INV1565 | 2025-11-30 | 13411.7647 |  | 2025-11-28
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 8873.2 |  | Matthews Group - INV-1572 | 2026-02-28 | 5364.7059 |  | 2026-02-12
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 8873.2 |  | Matthews Group - INV-1573 | 2025-12-31 | 5364.7059 |  | 2026-02-12
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 4436.6 |  | Matthews Group - INV-1574 | 2025-12-31 | 2682.3529 |  | 2026-02-12
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 4436.6 |  | Matthews Group - INV-1575 | 2025-12-31 | 2682.3529 |  | 2026-03-14
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-09-18 | 37508.5 | 44127.6471 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 35568
10 |  | Scaffolding |  |  | 17008.5 | 2025-09-18 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 12000 | 2025-09-18 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 |  |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-09-18 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 35568 | 10% | 3556.8 | PO4309-WATER-20250915 - RV Approved | Matthews Group - INV1533 | 2025-09-30 | 4412.7647 |  | 2025-09-18
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 5335.2 |  | Matthews Group - INV1548 | 2025-10-31 | 6619.1471 |  | 2025-10-24
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 7113.6 |  | Matthews Group - INV1564 | 2025-11-30 | 8825.5294 |  | 2025-12-04
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 8892 |  | Matthews Group - INV1565 | 2025-11-30 | 11031.9118 |  | 2025-11-28
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 3556.8 |  | Matthews Group - INV-1572 | 2025-12-31 | 4412.7647 |  | 2026-02-12
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 3556.8 |  | Matthews Group - INV-1573 | 2025-12-31 | 4412.7647 |  | 2026-02-12
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1778.4 |  | Matthews Group - INV-1574 | 2025-12-31 | 2206.3824 |  | 2026-02-12
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1778.4 |  | Matthews Group - INV-1575 | 2025-12-31 | 2206.3824 |  | 2026-03-14
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-18 | 29000 | 34117.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 10500 |  | SunSpot - E038 | 2026-01-31 | 13185.1925 | -0.0029208 | 2026-02-12 | 13690.9
11 |  | Structural sign off |  |  | 18000 | 2024-08-22 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7690.9 |  | L&B Inv: 1701 | 2025-08-31 | 11584.1689 |  | 2024-08-22
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-12-31 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5975 | 2025-12-31 | 9348.2886 |  | 2026-01-29
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 7923.9905 | 2025-12-31 | 48044.9505 | 54596.5347 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 10354.5906 |  | Matriarch - INV-6570 | 2026-02-28 | 54596.5347 | 0 | 2026-03-31 | 10354.5906
13 |  |  |  |  | 4000 | 2025-12-31 |  |  |  | 13 | 13. Engineering | Management | [6 empty] | 0
13 |  |  |  |  | 13600 | 2025-12-31 |  |  |  | 13 | 13. Engineering | Project manager | [6 empty] | 0
13 |  |  |  |  | 5200 | 2025-12-31 |  |  |  | 13 | 13. Engineering | Planner time | [6 empty] | 0
13 |  |  |  |  | 17320.96 | 2025-12-31 |  |  |  | 13 | 13. Engineering | De Snagging | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 875 | 2025-09-05 | 875 | 1029.4118 |  | 14 | 14. General Expenses | Travel |  |  | 304.64 |  | Expense Claim | 2025-08-31 | 422.5618 | -1.609e-05 | 2025-09-05 | 740.16
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 435.52 |  | Expense Claim | 2025-10-31 | 202.27 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2025-12-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 404.58 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 3985
15 | [9 empty] | 15 | 15. Service Add On | Equipment delivery |  |  | 3985 | PO4536-WSD-20251212 - RV Approved |  | 2026-03-31 |  |  | 2026-03-31
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 167702.96 |  | 204515.8049
| Inverter Procurement Budget | 47500 |  | 57926.8293
| Mounting Structure Budget | 47059.2 |  | 57389.2683
| DC Equipment Budget | 87218.6 |  | 106364.1463
| AC Equipment Budget | 131329.9826 |  | 160158.5154
| Monitoring Budget | 41000 |  | 50000
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 4000 |  | 4494.382
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 13680 |  | 16094.1176
| DC Installer Budget | 31920 |  | 37552.9412
| In-House Expense Budget | 48044.9505 |  | 54596.5347
| Compliance Budget | 29000 |  | 34117.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 12000 |  | 14117.6471
| Roof Access Budget for Installers | 17008.5 |  | 20010
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 875 |  | 1029.4118

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 828367.2456 | 828367.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289928.536 | 0 | 0 | 82836.7246 | 41418.3623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 704112.1587 | 704112.1587 | 704112.1587 | 786948.8833 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456
| Planned Expenditure | 686839.1931 | 668839.1931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181777.8 | 875 | 135329.9826 | 94108.5 | 41000 | 0 | 0 | 0 | 0 | 167702.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48044.9505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181777.8 | 182652.8 | 317982.7826 | 412091.2826 | 453091.2826 | 453091.2826 | 453091.2826 | 453091.2826 | 453091.2826 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 620794.2426 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931 | 668839.1931
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 232405.8228 | 231530.8228 | 96200.8402 | 2092.3402 | -38907.6598 | -38907.6598 | -38907.6598 | -38907.6598 | 251020.8761 | 83317.9161 | 83317.9161 | 166154.6407 | 207573.003 | 207573.003 | 207573.003 | 207573.003 | 207573.003 | 207573.003 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524 | 159528.0524
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 828367.2456 | 828367.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289928.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82836.7246 | 0 | 0 | 0 | 0 | 41418.3623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 414183.6228 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 704112.1587 | 786948.8833 | 786948.8833 | 786948.8833 | 786948.8833 | 786948.8833 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456 | 828367.2456
| Actual + Planned Expenditure | 617007.4506 | 619816.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46887.94 | 304.64 | 4814.1 | 19212.6 | 8598.34 | 67621.74 | 0 | 0 | 51991.88 | 41240.97 | 435.52 | 11169 | 0 | 217457.25 | 38425.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29172.98 | 0 | 58538.5 | 0 | 0 | 0 | 9606.3 | 0 | 0 | 14339.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46887.94 | 47192.58 | 52006.68 | 71219.28 | 79817.62 | 147439.36 | 147439.36 | 147439.36 | 199431.24 | 240672.21 | 241107.73 | 252276.73 | 252276.73 | 469733.98 | 508159.18 | 508159.18 | 508159.18 | 508159.18 | 508159.18 | 508159.18 | 508159.18 | 508159.18 | 537332.16 | 537332.16 | 595870.66 | 595870.66 | 595870.66 | 595870.66 | 605476.96 | 605476.96 | 605476.96 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506 | 619816.5506
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414183.6228 | 414183.6228 | 367295.6828 | 366991.0428 | 362176.9428 | 342964.3428 | 334366.0028 | 266744.2628 | 266744.2628 | 266744.2628 | 214752.3828 | 173511.4128 | 173075.8928 | 161906.8928 | 161906.8928 | 234378.1787 | 195952.9787 | 195952.9787 | 195952.9787 | 195952.9787 | 195952.9787 | 195952.9787 | 195952.9787 | 195952.9787 | 249616.7233 | 249616.7233 | 191078.2233 | 191078.2233 | 191078.2233 | 232496.5856 | 222890.2856 | 222890.2856 | 222890.2856 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695 | 208550.695
|  | CHECK | CHECK
| Revenue Recognition | 1940.3997 | 826426.8459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199028.1323 | 0 | 0 | 0 | 0 | 353862.8558 | 0 | 0 | 0 | 49016.3608 | 0 | 0 | 0 | 88186.9191 | 0 | 0 | 0 | 0 | 62781.5647 | 0 | 0 | 0 | 13589.7725 | 0 | 0 | 0 | 59961.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 826426.8459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199028.1323 | 199028.1323 | 199028.1323 | 199028.1323 | 199028.1323 | 552890.9882 | 552890.9882 | 552890.9882 | 552890.9882 | 601907.349 | 601907.349 | 601907.349 | 601907.349 | 690094.2681 | 690094.2681 | 690094.2681 | 690094.2681 | 690094.2681 | 752875.8328 | 752875.8328 | 752875.8328 | 752875.8328 | 766465.6053 | 766465.6053 | 766465.6053 | 766465.6053 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459 | 826426.8459

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 204515.8049 |  |  |  | 0 |  |  | 204515.8049
2. Inverters | 0 | 57926.8293 |  |  |  |  | 0 |  |  | 57926.8293
3. Mounting Structures | 0 |  | 57389.2683 | 0 |  |  | 0 |  |  | 57389.2683
4. DC Equipment |  |  | 64748.9951 | 6935.8585 | 20807.5756 | 13878.4196 | 0 |  |  | 106370.8489
5. Monitoring |  | 20569.28 | 12235.6001 | 15248.0147 | [5 empty] | 48052.8948
6. AC Equipment |  | 108201.3467 | 5195.7169 | 7793.5753 | 23380.7259 | 15587.1506 | 0 |  |  | 160158.5154
8. Product Add On |  | 323.9456 |  | 4170.4364 | [5 empty] | 4494.382
9. AC & DC installation | 0 |  | 5364.7059 | 8047.0588 | 24141.1765 | 10729.4118 | 0 |  | 5364.7059 | 53647.0588
10. Site Logistics | 0 |  | 4412.7647 | 6619.1471 | 19857.4412 | 13238.2941 | 0 |  |  | 44127.6471
11. Due Dilligence |  | 11584.1689 |  |  |  | 9348.2886 | 0 | 13185.1925 |  | 34117.65
13. Engineering | 0 | [5 empty] | 0 |  | 54596.5347 | 54596.5347
14. General Expenses |  | 422.5618 | 0 | 202.27 | 0 | 0 | 0 | 404.58 |  | 1029.4118
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 199028.1323 | 353862.8558 | 49016.3608 | 88186.9191 | 62781.5647 | 0 | 13589.7725 | 59961.2406 | 826426.8459

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 109496.5 | [5 empty] | 109496.5
2. Inverters |  | 45062.94 | [6 empty] | 45062.94
3. Mounting Structures |  |  | 41240.97 | 5329.25 |  |  |  |  | 46570.22
4. DC Equipment |  |  | 58799 | 6298.5 | 18895.5 | 12604 |  |  | 96597
5. Monitoring |  | 16493 | 8962.44 | 11169 |  |  |  |  | 36624.44
6. AC Equipment |  | 53803.74 | 2583.6 | 3875.4 | 11626.2 | 7750.8 |  |  | 79639.74
8. Product Add On |  | 3600 |  | 46345.96 |  |  |  |  | 49945.96
9. AC & DC installation |  |  | 8873.2 | 13309.8 | 39929.4 | 17746.4 |  | 8873.2 | 88732
10. Site Logistics |  |  | 3556.8 | 5335.2 | 16005.6 | 10670.4 |  |  | 35568
11. Due Dilligence |  | 7690.9 |  |  |  | 6000 | 10500 |  | 24190.9
13. Engineering | [7 empty] | 10354.5906 | 10354.5906
14. General Expenses |  | 304.64 | 0 | 435.52 | 0 | 0 | 0 |  | 740.16
15. Service Add On | [7 empty] | 3985 | 3985
12. BDP Commission
7.BESS
Grand Total |  | 126955.22 | 233512.51 | 92098.63 | 86456.7 | 54771.6 | 10500 | 23212.7906 | 627507.4506

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Waterside
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 5.0526 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 2.5847 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 1.7486 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 4.1847 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Waterside |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Waterside | 0 | 0 | 0