## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 12364058.4067 |  | 12392594.0424 |  |  |  | Start Date | 12392594.0424 | 6961407.9225 | 1203406.5043 | 1273261.3914 | 1238696.9003 | 1226321.6414
2 | Planned Expenditure | 10416339.814 |  | 8234669.3139 | VO PM Limit | Current VO Total
3 | Planned Profit | 1947718.5927 |  | 4157924.7285 | 97385.9296 | 183011.8639 |  | End Date - PC
4 | Planned Margin | 15.75% |  | 33.55%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 4327420.4423 |  | 2025-06-27 | 004770 | 2025-06-18 | 2025-07-11
2 | Delivery of Panels |  | 30% | 3709217.522 |  | 2025-08-15 | 004815 | 2025-08-14 | 2025-08-28
3 | Delivery of Inverters |  | 20% | 2472811.6813 |  | 2025-07-07 | 004815 | 2025-08-14 | 2025-08-28
4 | Practical Completion |  | 10% | 1236405.8407 |  | 2025-10-17 | 004865 | 2025-10-28 | 2025-11-07
5 | Handover |  | 5% | 618202.9203 |  | 2025-10-28 | 004892 | 2025-12-08 | 2026-01-09
6 | Reduced CAPEX |  | 0% | -42222.1643 |  | 2025-10-28 | 004892 | 2025-12-08 | 2026-01-09
7 | Installation of Meters |  | 0% | 70757.8 |  |  | 004892 | 2025-12-08 | 2026-01-09
|  |  | 100% | 12392594.0424
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
| Red Font - IF NUMBER: Negative value | [5 empty] | Contract | 682000
| Anything in yellow is a concern or risk for noting or action | [5 empty] | Installed | 669120
| confirmed | [6 empty] | 12880
| [ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important] | [5 empty] | DC Rate | 3.2781
| [RT: When adding rows into sheet, ensure you insert between first and last row of each category] | [5 empty] | Reduced CAPEX | 42222.1643
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | %
1 | Deposit - Project commencement |  | 35%
2 | Delivery of Panels |  | 30%
3 | Delivery of Inverters |  | 20%
4 | Practical Completion |  | 10%
5 | Handover |  | 5%
| Total |  | 100%
100%
Formulas:
PAYMENT RECEIVED DATE = [PAYMENT RECEIVED DATE, row above]

## Project Plan
[9 empty] | 2026-02-23 | 2026-02-23
| PROJECT PLAN | Red Rocket | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 682
| PROJECT DEVELOPER | Peet Verenney |  |  |  | Target Month | 2025-07-31
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 12364058.4067
| Phase: | DLP
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 89 |  |  | 105 |  | 93.24% | 94.49% |  | HIGH LEVEL PROGRAMME | Actual Start | Duration (days) | Actual End | Status
1 | Project Initiation | 2025-06-23 | 73 | 2025-09-04 | 2025-06-23 | 73 | 2025-09-04 | 100% | 100% |  | Project Initiation | 2025-06-23 | 73 | 2025-09-04 | 100% | 1
1.1 | BD Handover | 2025-06-23 | 5 | 2025-06-30 | 2025-06-23 | 5 | 2025-06-30 | 100% | 100% |  | Site Establishment | 2025-08-14 | 1 | 2025-08-15 | 100% | 1 |  | Commencement Date | 2025-07-11
1.2 | Project Introduction | 2025-07-17 | 1 | 2025-07-18 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100% |  | AC Installation - Tie In 1 (Right) | 2025-08-18 | 65 | 2025-10-22 | 100% | 1
1.3 | HSE - JA Electrical | 2025-07-03 | 28 | 2025-08-12 | 2025-07-03 | 28 | 2025-08-12 | 100% | 100% |  | AC Installation - Tie In 2 (Left) | 2025-08-14 | 63 | 2025-10-16 | 100% | 1 | 63
1.4 | HSE - Ask Fritz | 2025-09-02 | 2 | 2025-09-04 | 2025-09-02 | 2 | 2025-09-04 | 100% | 100% |  | DC Works | 2025-09-26 | 24 | 2025-10-20 | 100%
1.5 | Installer Kick Off | 2025-07-17 | 1 | 2025-07-18 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100% |  | Soft Commissioning (Energy Flowing) | 2025-10-06 | 11 | 2025-10-21 | 100% | 1 | 10.7143
1.6 | Project Review | 2025-07-17 | 1 | 2025-07-18 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100% |  | Full Commissioning Monitoring | 2025-10-21 | 5 | 2025-10-28 | 100% | 1 |  | 87
[11 empty] | Higeco Commissioning | 2025-10-22 | 1 | 2025-11-26 | 100% | 1
2 | Site Establishment | 2025-08-14 | 1 | 2025-08-15 | 2025-08-14 | 1 | 2025-08-15 | 100% | 100% |  | QA Inspections | 2025-10-29 | 1 | 2025-10-30 | 100% | 0.55932
2.1 | Solar Contractor Establishment | 2025-08-14 | 1 | 2025-08-15 | 2025-08-14 | 1 | 2025-08-15 | 100% | 100% |  | Project Closure | 2025-10-23 | 43 | 2025-12-05 | 55.93%
3 | AC Installation - Tie In 1 (Right) | 2025-06-30 | 142 | 2025-11-19 | 2025-06-30 | 114 | 2025-10-22 | 100% | 100%
3.1 | Inverters delivered | 2025-06-30 | 1 | 2025-07-01 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
3.2 | Inverters Mounted | 2025-10-13 | 1 | 2025-10-14 | 2025-10-01 | 1 | 2025-10-02 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-08-11 | 25 | 2025-09-15 | 2025-08-11 | 25 | 2025-09-15 | 100% | 100%
3.4 | Civil Works - Tie In 1 | 2025-10-11 | 28 | 2025-11-19 | 2025-10-01 | 15 | 2025-10-22 | 100% | 100% | Adding 7 days as float. Set up meeting with Fritz
3.5 | Rigging of Batteries | 2025-09-22 | 1 | 2025-10-10 | 2025-09-22 | 1 | 2025-10-10 | 100% | 100%
3.6 | AC Works Tie In 1 | 2025-10-13 | 10 | 2025-10-27 | 2025-10-01 | 10 | 2025-10-15 | 100% | 100%
3.7 | AC Tie-In 1 | 2025-10-01 | 1 | 2025-10-02 | 2025-10-01 | 1 | 2025-10-02 | 100% | 100%
4 | AC Installation - Tie In 2 (Left) | 2025-06-30 | 133 | 2025-11-10 | 2025-06-30 | 108 | 2025-10-16 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Inverters delivered | 2025-06-30 | 1 | 2025-07-01 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
4.2 | Inverters Mounted | 2025-10-13 | 1 | 2025-10-14 | 2025-10-01 | 1 | 2025-10-02 | 100% | 100%
4.3 | Solar DB Lead Time | 2025-08-11 | 45 | 2025-10-14 | 2025-08-11 | 45 | 2025-10-14 | 100% | 100%
4.4 | Civil Works - Tie In 2 | 2025-10-11 | 7 | 2025-10-21 | 2025-10-01 | 5 | 2025-10-08 | 100% | 100%
4.5 | Rigging of Batteries | 2025-09-22 | 1 | 2025-10-10 | 2025-09-22 | 1 | 2025-10-10 | 100% | 100%
4.6 | AC Works Tie In 2 | 2025-10-24 | 10 | 2025-11-07 | 2025-10-07 | 7 | 2025-10-16 | 100% | 100%
4.7 | AC Tie-In 2 | 2025-11-07 | 1 | 2025-11-10 | 2025-10-08 | 1 | 2025-10-09 | 100% | 100%
5 | DC Works | 2025-08-08 | 84 | 2025-10-31 | 2025-08-08 | 73 | 2025-10-20 | 100% | 100%
5.1 | Module delivery | 2025-08-08 | 1 | 2025-08-11 | 2025-08-08 | 1 | 2025-08-11 | 100% | 100%
5.2 | Module mounting | 2025-10-03 | 20 | 2025-10-31 | 2025-09-26 | 12 | 2025-10-14 | 100% | 100%
5.3 | Mounting Structure delivered | 2025-08-09 | 1 | 2025-08-11 | 2025-08-09 | 1 | 2025-08-11 | 100% | 100%
5.4 | Mounting Structure installation | 2025-08-24 | 40 | 2025-10-20 | 2025-08-24 | 35 | 2025-10-13 | 100% | 100%
5.5 | Lintel Delivery | 2025-08-10 | 10 | 2025-08-22 | 2025-08-10 | 10 | 2025-08-22 | 100% | 100%
5.6 | DC Cable delivered | 2025-06-30 | 0 | 2025-06-30 | 2025-06-30 | 0 | 2025-06-30 | 100% | 100%
5.7 | DC Stringing | 2025-09-19 | 20 | 2025-10-20 | 2025-09-12 | 24 | 2025-10-17 | 100% | 100%
5.8 | DC Ready 1 | 2025-09-22 | 1 | 2025-09-23 | 2025-09-22 | 1 | 2025-09-23 | 100% | 100%
5.9 | DC Ready 2 | 2025-10-20 | 1 | 2025-10-21 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
6 | Commissioning | 2025-10-27 | 15 | 2025-11-11 | 2025-10-06 | 52 | 2025-11-27 | 90% | 100%
6.1 | Comms Equipment Testing | 2025-10-27 | 1 | 2025-10-28 | 2025-10-15 | 1 | 2025-10-16 | 100% | 100%
6.2 | Link to Client Network via Fiber |  |  |  | 2025-10-09 | 9 | 2025-10-22 | 100% | 100%
6.3 | Soft Commissioning (Energy Flowing) |  |  |  | 2025-10-06 | 11 | 2025-10-21 | 100% | 100%
6.4 | Higeco Commissioning |  |  |  | 2025-10-22 | 25 | 2025-11-26 | 100% | 100% | Red rocket running tests this week
6.5 | Techsitter Commissioning |  |  |  | 2025-10-20 | 1 | 2025-10-21 | 100% | 100%
6.6 | Full Commissioning Monitoring |  |  |  | 2025-10-21 | 5 | 2025-10-28 | 100% | 100%
6.7 | Installation of IRR Sensors |  |  |  | 2025-10-17 | 1 | 2025-10-18 | 100% | 100%
6.8 | Tie In 2 Summation Metering |  |  |  | 2025-10-17 | 5 | 2025-10-22 | 100% | 100%
6.9 | Inverter Monitoring - (Tie In 2) |  |  |  | 2025-10-21 | 5 | 2025-10-26 | 100% | 100%
6.10 | Additional Ventilation |  |  |  | 2025-10-27 | 31 | 2025-11-27 | 100% | 100%
6.11 | BESS Configuration |  |  |  | 2025-10-31 | 10 | 2025-11-10 | 100% | 100%
7 | QA Inspections | 2025-10-27 | 21 | 2025-11-17 | 2025-10-29 | 1 | 2025-10-30 | 100% | 100% |  | Delay damages @ R20 600 | Actual | Contract
7.1 | Red-Team Inspection | 2025-10-27 | 15 | 2025-11-17 | 2025-10-29 | 1 | 2025-10-30 | 100% | 100% |  | Commencement Date | 2025-07-11 | 2025-07-11
7.2 | Engineering Inspection | 2025-10-27 | 15 | 2025-11-17 | 2025-10-22 | 1 | 2025-10-23 | 100% | 100% |  | Energy flowing | 2025-10-21 | 2025-09-24
[11 empty] | Duration | 102 | 75
8 | Project Closure | 2025-11-11 | 9 | 2025-11-20 | 2025-10-23 | 43 | 2025-12-05 | 55.93% | 55.93% |  | Delayed days | 27
8.1 | Equipment serial numbers | 2025-11-17 | 1 | 2025-11-18 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100% |  | Penalties | 556200
8.2 | Snags completion | 2025-11-17 | 1 | 2025-11-18 | 2025-10-23 | 26 | 2025-11-28 | 100% | 100% | RS485 SPDs to be installed - Happy Solar
8.3 | String Updates | 2025-11-11 | 1 | 2025-11-12 | 2025-11-04 | 2 | 2025-11-06 | 100% | 100%
8.4 | Exit Roof Report |  |  |  | 2025-11-03 | 1 | 2025-11-04 | 100% | 100%
8.5 | As Built Drawings |  |  |  | 2025-10-31 | 8 | 2025-11-12 | 100% | 100%
| SSEG SLD |  |  |  | 2025-11-05 | 10 | 2025-11-19 | 100% | 100%
8.6 | Commissioning Form |  |  |  | 2025-10-31 | 12 | 2025-11-18 | 100% | 100%
8.7 | Techsitter Targets & Validate Targets |  |  |  | 2025-10-31 | 18 | 2025-11-26 | 100% | 100% | Submitted to Matriarch Fri - 7 Nov .(PG to be validated)
8.8 | PrEng Signoff |  |  |  | 2025-11-05 | 2 | 2025-11-07 | 100% | 100%
8.9 | Fritz HSE incident |  |  |  | 2025-11-05 | 1 | 2025-11-06 | 100% | 100%
8.10 | Handover documentation | 2025-11-18 | 1 | 2025-11-19 | 2025-10-23 | 25 | 2025-11-27 | 100% | 100% | To be printed
8.11 | Handover to Client | 2025-11-19 | 1 | 2025-11-20 | 2025-12-04 | 1 | 2025-12-05 | 100% | 100%
8.12 | Handover to Matriarch | 2025-11-19 | 1 | 2025-11-20 | 2025-11-17 | 11 | 2025-12-02 | 100% | 100%
Formulas:
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 10416339.814 |  | 8234669.3139 | 2181670.5001
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1788541.3681 |  | 1263945.2 | 524596.1681
2 | 2. Inverters | 356200 |  | 316436.04 | 39763.96
3 | 3. Mounting Structures | 1186680 |  | 887538.46 | 299141.54
4 | 4. DC Equipment | 1208947.5 |  | 371619.98 | 837327.52
5 | 5. Monitoring | 45636 |  | 200056.25 | -154420.25
6 | 6. AC Equipment | 849891.5 |  | 1071907.23 | -222015.73
7 | 7.BESS | 3616080.6087 |  | 2378460 | 1237620.6087
8 | 8. Product Add On | 145000 |  | 256749.19 | -111749.19
9 | 9. AC & DC installation | 687500 |  | 900817.81 | -213317.81
10 | 10. Site Logistics | 8500 |  | 216404.8 | -207904.8
11 | 11. Due Dilligence | 77050 |  | 52000 | 25050
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 434412.8372 |  | 154022.95 | 280389.8872
14 | 14. General Expenses | 11900 |  | 8514.52 | 3385.48
15 | 15. Service Add On | 0 |  | 156196.8839 | -156196.8839
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 10416339.814 | 12364058.4067 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 8234669.3139
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1788541.3681 | 2025-08-29 | 1788541.3681 | 2235676.7101 |  | 1 | 1. Panels | JA 615W | 1108.9431 | 1156.4 | 1282447.6 |  | Menlo INV0003051 | 2025-06-30 | 2235676.7101 | 42222.1643 | 2025-09-01 | 1263945.2
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels |  |  | 1.8803 |  |  |  |  | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 |  |  |  | 3.2781 | [5 empty] | 1 | 1. Panels | Panels moved to Stock | -16 | 1156.4 | -18502.4 |  | Allocated to Cpt Storeroom | 2025-11-30 | 0 |  | 2025-11-30
1 | [9 empty] | 1 | 1. Panels | X4 Broken panels |  | 1156.4 | 0 |  | Dont add as a credit | 2025-11-30 | 0 |  | 2025-11-30
[10 empty] | 1 | 1. Panels | Reduction in Size | [5 empty] | 2026-01-31 | -42222.1643 |  | 2026-01-31
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 849891.5
2 | Inverters | Inverter Budget |  |  | 356200 | 2025-07-29 | 356200 | 445250 |  | 2 | 2. Inverters | Sungrow SG125CX | 4 | 69140 | 276560 | PO4037-RR-20250626 - RV Approved | Herholdts INV1088936 | 2025-06-30 | 389826.3265 | 0 | 2025-07-29 | 316436.04 | DC Equipment | 724197.5
2 | [5 empty] | 2025-07-29 |  |  |  | 2 | 2. Inverters | Sungrow SG50CX | 1 | 39320 | 39320 |  | Herholdts INV1088936 | 2025-06-30 | 55423.6735 |  | 2025-07-29 |  | AC Labour | 341000
2 | [9 empty] | 2 | 2. Inverters | Sungrow SG125CX | 1 |  | 68050 |  | Herholdts -INV1165658 | 2025-10-31 | 0 |  | 2025-11-28 |  | DC Labour | 346500
2 | [9 empty] | 2 | 2. Inverters | Sungrow SG125CX - RMA |  |  | -69140 | RMA | Herholdts - CN130769 | 2026-01-31 | 0 |  | 2026-01-31 |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | courier of RMA |  |  | 1646.04 |  | DSV Inv: 180155155 | 2025-11-30 | 0 |  | 2025-12-30 |  | BESS Installation | 375000
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Inverter Room Upgrades | 50000
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 1186680 | 2025-07-29 | 1186680 | 1483350 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 344822.96 | PO4033-RR-20250626 - RV Approved | Schletter INV1906 | 2025-06-30 | 431028.7 | -0.0038501 | 2025-07-29 | 887538.46 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Lintels send back to Lintel for Africa | -120 | 119.75 | -16705.46 |  | Lintels Credit Note - CR2256 | 2025-11-30 | 0 |  | 2025-11-30 |  | Total | 2695089
[10 empty] | 3. | 3. Mounting Structures | Collection of Lintels |  |  | 1436.9 |  | Lintels Credit Note - CR2256 | 2025-11-30 | 0 |  | 2025-11-30
[10 empty] | 3. | 3. Mounting Structures | 1.2m Custom Rails - returned to stock | -55 | 78.4 |  |  |  | 2025-12-31 | 0 |  | 2025-12-31
[10 empty] | 3. | 3. Mounting Structures | Surface Protection Mats | -65 | 31.54 | -2050.1 | To be allocated to 7th Avenue | Allocated to 7th Avenue | 2026-01-31 | 0 |  | 2026-01-31
[6 empty] | 2025-07-31 |  |  |  | 3 | 3. Mounting Structures | Lintels |  |  | 278899.16 | PO4164-RR-20250725 - RV Approved | Lintels - 232597 | 2025-07-31 | 525027.7674 |  | 2025-07-31
3 | [5 empty] | 2025-08-30 |  |  |  | 3 | 3. Mounting Structures | Rail Length |  |  | 280280 | PO4033-RR-20250626 - RV Approved | Schletter INV1976 | 2025-07-31 | 527293.5564 |  | 2025-08-30 |  | R/Wp | #REF!
3 | [5 empty] | 1900-01-29 |  |  |  | 3 | 3. Mounting Structures | End Clamps |  |  | 650 | PO4360-RR-20251009 - RV Approved | Solarworld - Inv SASIV-25-00568 | 2025-10-31 | -0.02 |  | 2025-11-13
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery of Clamps |  |  | 205 |  | Uber Deilvery | 2025-10-31 | 0 |  | 2025-10-10 |  | ACTUAL - JA Electrical | Installer Price
[23 empty] | AC Equipment | 1058756.23
4 | DC Equipment | DC Cable Budget | 39818.75 |  | 484750 | 2009-02-04 18:00 | 1208947.5 | 1511184.375 |  | 4 | 4. DC Equipment | DC Cable | 40000 | 13.5 | 540000 | PO4126-RR-20250716 - RV Approved | Rubicon INVWCRE-00069640 | 2025-07-31 | 1491518.4828 | 0 | 2025-08-30 | 371619.98 | DC Equipment | 223119.98
4 |  | DC Equipment Budget |  |  | 724197.5 | 2025-07-31 |  |  |  | 4 | 4. DC Equipment | Move to Stock | -16000 | 13.5 | -216000 |  | Allocated to Stock | 2025-07-31 | -596607.3931 |  | 2025-07-31 |  | AC Labour | 237440.63
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable - black | -6000 | 13.5 | -81000 |  | Allocated to Stock | 2025-10-31 | 0 |  | 2025-10-31 |  | DC Labour | 663377.18 | 0.97269 | 12528.2963
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable - Red | -7000 | 13.5 | -94500 |  | Allocated to Stock | 2025-10-31 | 0 |  | 2025-10-31 |  | Offloading | 51940
[10 empty] | 4 | 4. DC Equipment
4 | [5 empty] | 2025-08-28 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 223119.98 | 10% | 22311.998 |  | JA Electrical Inv 1083 | 2025-08-31 | 61627.3285 |  | 2025-08-14 |  | BESS Installation | 110262
4 | [5 empty] | 2025-08-29 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 33467.997 |  | JA Electrical Inv 1083 | 2025-08-31 | 92440.9928 |  | 2025-08-29 |  | Inverter Room Upgrades | 7284.8
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 44623.996 |  | JA Electrical Inv 1083 | 2025-08-31 | 123254.6571 |  | 2025-10-16 |  | Ablutions | 15620
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 55779.995 |  | JA Electrical Inv 1083 | 2025-08-31 | 154068.3213 |  | 2025-10-16 |  | Return of excess material | 6583
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 22311.998 |  | JA Electrical Inv 1083 | 2025-08-31 | 61627.3285 |  | 2025-11-28 |  | Waste Skip | 15855
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 22311.998 |  | JA Electrical Inv 1083 | 2025-08-31 | 61627.3285 |  | 2025-12-05 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 11155.999 |  | JA Electrical Inv 1083 | 2025-08-31 | 30813.6643 |  | 2025-12-05 |  | Total | 2390238.82
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 11155.999 |  | JA Electrical Inv 1083 | 2025-08-31 | 30813.6643 |  | 2025-12-24 |  | R/Wp | 3.5047
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 30636 | 2025-07-28 | 45636 | 57045 |  | 5 | 5. Monitoring | [7 empty] | 0 | 0.002219 |  | 200056.25
5 |  | Revenue Metering |  |  | 15000 | 2025-07-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 17131.5 | PO4062-RR-20250630 - RV Approved | AccuEnergy ASAI-005841 | 2025-06-30 | 17332.9505 |  | 2025-07-29
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | AcuRev 1313 RCT-XO - Return to stock | 1 | 2970 | -2970 |  | Allocated to Cpt Stockroom | 2025-09-30 | 0 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | AcuCT3147-1000:5 - Return to stock | 3 | 1260 | -3780 |  | Allocated to Cpt Stockroom | 2025-09-30 | 0 |  | 2025-09-30
[10 empty] | 5 | 5. Monitoring | AcuCT3147-1000:5 - Return to stock | -3 | 1260 | -3780 |  | Allocated to Cpt Stockroom | 2025-11-30 | 0 |  | 2025-11-30
5 | [5 empty] | 2025-07-31 |  |  |  | 5 | 5. Monitoring | Techsitter - (Which Tie In) |  |  | 11169 |  | Matriarch - INV-4742 | 2025-07-31 | 1489.3546 |  | 2025-07-31
[6 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Techsitter - (Which Tie In) |  |  | 11169 |  | Matriarch - INV-5207 | 2025-10-31 | 3098.8521 |  | 2025-11-13
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 206.91 |  | DSV Inv: 180150385 | 2025-10-31 | 34.86 |  | 2025-11-30
5 | [5 empty] | 2025-08-07 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO4071-RR-20250630 - RV Approved | Frontline QTE107315 | 2025-07-31 | 300.0978 |  | 2025-08-07
5 | [9 empty] | 5 | 5. Monitoring | Higeco |  |  | 0 |  |  |  | 0
[6 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | CT equipement as below |  |  | 25703 | PO4219-RR-20250813 - RV Approved | AccuEnergy ASAI-006148 | 2025-08-31 | 5254.2227 |  | 2025-09-30
[10 empty] | 5 | 5. Monitoring | Intergator kit - RIK 5A | 1 | [5 empty] | 0
[10 empty] | 5 | 5. Monitoring | SumCT 5A/5+5 | 3 | [5 empty] | 0
[10 empty] | 5 | 5. Monitoring | CT - 2000A/5A CL 0.5 (Grid Meter) | 6 | [5 empty] | 0
[10 empty] | 5 | 5. Monitoring | CT - 600A/5A CL 0.5 (Techsitter) | 6 | [5 empty] | 0
[6 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Switch and PSU |  |  | 1644.5 | PO4226-RR-20250818 - RV Approved | Accuenergy - ASAI-006183 | 2025-08-31 | 336.1697 |  | 2025-09-30
[6 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Switch and PSU |  |  | -940.5 |  | Accuenergy - CN-00227 | 2025-08-31 | -192.2576 |  | 2025-08-31
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | Delivery |  |  | 200 |  | Accuenergy - ASAI-006213 | 2025-08-31 | 0 |  | 2025-09-30
[6 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Sungrow COM100 | 2 |  | 21200 | PO4221-RR-20250813 - RV Approved | Herholdts - INV1120131 | 2025-08-31 | 4333.7168 |  | 2025-09-30
[6 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Sungrow DTSD1352 | 2 |  | 9040 |  | Herholdts - INV1120131 | 2025-08-31 | 1847.9622 |  | 2025-09-30
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [5 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Irradiance sensors | 3 |  | 28431.28 | RV Approved | IBC Solar - ZA42502457 | 2025-10-31 | 7888.2918 |  | 2025-10-17
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[6 empty] | 0 |  |  |  | 5 | 5. Monitoring | Optic Fiber |  |  | 52911.24 | PO4359-RR-20251007 - RV Approved | WM Cabling - INV0001211 | 2025-10-31 | 6376.4952 |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring |  |  |  | 28219.32 |  | WM Cabling - INV0001211 | 2025-10-31 | 7829.4832 |  | 2025-10-09
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | 8 Port Switch |  |  | 1767.5 | PO4360-RR-20251014 - RV Approved | Accuenergy: ASAI-006611 | 2025-10-31 | 490.3949 |  | 2025-11-30
[10 empty] | 5 | 5. Monitoring | 8 Port Switch |  |  | -1767.5 |  | Allocated to riverside Mall | 2026-01-31 | 0 |  | 2026-01-31
[10 empty] | 5 | 5. Monitoring | Second Tie In UPS |  |  | 2250.5 | PO4367-RR-20251014 - RV Approved | Frontline INV746387 | 2025-10-31 | 624.4038 |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
[10 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 849891.5 | 2025-08-31 | 849891.5 | 1062364.375 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 1071907.23
6 | [9 empty] | 6 | 6. AC Equipment | QC4 Connectors |  |  | 13151 |  | Menlo Inv: INV0003305 + INV0003343 | 2025-10-31 | 0 |  | 2025-12-18
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Move old breakers to stock | [6 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-08-28 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 1058756.23 | 10% | 105875.623 |  | JA Electrical Inv 1083 | 2025-08-31 | 106236.4375 |  | 2025-08-14
6 | [5 empty] | 2025-08-29 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 158813.4345 |  | JA Electrical Inv 1083 | 2025-08-31 | 159354.6562 |  | 2025-08-29
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 211751.246 |  | JA Electrical Inv 1083 | 2025-08-31 | 212472.875 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 264689.0575 |  | JA Electrical Inv 1083 | 2025-08-31 | 265591.0938 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 105875.623 |  | JA Electrical Inv 1083 | 2025-08-31 | 106236.4375 |  | 2025-11-28
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 105875.623 |  | JA Electrical Inv 1083 | 2025-08-31 | 106236.4375 |  | 2025-12-05
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 52937.8115 |  | JA Electrical Inv 1083 | 2025-08-31 | 53118.2188 |  | 2025-12-05
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 52937.8115 |  | JA Electrical Inv 1083 | 2025-08-31 | 53118.2188 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | Battery Inverter + Battery Bank |  |  | 2863498 | 2025-08-31 | 3616080.6087 | 4017867.343 |  | 7 | 7.BESS | BESS Outdoor Cabinet - 229KWh BESS, 110KW,PCS, 200CS, LC200 Local controller | 2 | 673930 | 1347860 | PO4009-RR-20250618 - RV Approved | Herholdts - INV1111916 | 2025-07-31 | 2342698.6135 | 0 | 2025-08-31 | 2378460
7 |  | Separate AC Change over 250kW |  |  | 350000 | 2025-08-31 |  |  |  | 7 | 7.BESS | ATS Cabinet - EMS300 CP, 250KVA Isolation Transformer | 2 | 316900 | 633800 |  | Herholdts - INV1111916 | 2025-07-31 | 1101599.8555 |  | 2025-08-31
7 |  | Installation |  |  | 375000 | 2025-08-31 |  |  |  | 7 | 7.BESS | [7 empty] | 0
7 | [5 empty] | 2025-08-21 |  |  |  | 7 | 7.BESS | Civil Works - Deposit | 50% | 396800 | 198400 | PO2917-RR-20250819 - RV Approved | Ask Fritz 2508_014 | 2025-08-31 | 286784.437 |  | 2025-08-21
7 |  | AC Cable |  |  | 27582.6087 | 2025-09-18 |  |  |  | 7 | 7.BESS | Civil Works - Balance | 50% |  | 31388.96 |  | Ask Fritz 2508_014 | 2025-08-31 | 286784.437 |  | 2026-02-28
7 | [9 empty] | 7 | 7.BESS |  |  |  | 167011.04 |  | Ask Fritz 2508_014 | 2025-08-31 | 0 |  | 2025-11-06
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
8 | Product Add On | [5 empty] | 145000 | 181250 |  | 8 | 8. Product Add On | Additional Ventilation - V&A - VO |  |  | 120223.89 | PO4461-RR-20251111 - RV Approved | LW Refrigeration - 32296 | 2025-11-30 | 0 | 0 | 2025-11-28 | 256749.19
[10 empty] | 8 | 8. Product Add On
8 |  | Irradiance Sensors |  |  | 75000 | 2025-08-03 |  |  |  | 8 | 8. Product Add On | 8 port switch
8 |  | Inverter Room Upgrades |  |  | 50000 | 2025-08-04 |  |  |  | 8 | 8. Product Add On | Inverter Room Upgrades |  |  | 0 |  |  |  | 0
|  | MV Metering |  |  | 20000 | 2025-08-04 |  |  |  | 8 | 8. Product Add On | ABB XT3N 250A TP MCCB | 4 |  | 20597.8 |  | Switchboard - 2-SOI002560 | 2025-10-31 | 0 |  | 2025-11-28
8 | [5 empty] | 2025-08-06 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On | Top Tie In Fence/Gate - V&A |  |  | 18995 | PO4459-RR-20251111 - RV Approved |  | 2026-02-28 |  |  | 2026-02-26
[10 empty] | 8 | 8. Product Add On | Electrical Isolators - Aircon - V&A |  |  | 11229.25 | PO4460-RR-20251111 - RV Approved | W&F Electrical - INV08652 | 2025-11-30 |  |  | 2025-11-19
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On | Additional material for plinth size increase - VO |  |  | 7600 |  | Ask Fritz - 2510_015 | 2025-11-30 |  |  | 2025-11-13
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-08-07 |  |  |  | 8 | 8. Product Add On | Offloading |  |  | 12508.5 |  | Matthews Group MG INV-1513 | 2025-08-31 | 56118.1526 |  | 2025-08-07
8 | [5 empty] | 2025-07-03 |  |  |  | 8 | 8. Product Add On | Offloading |  |  | 14200 | PO4035-RR-20250626 - RV Approved | Happy Solar INV-0322 | 2025-06-30 | 16166.7714 |  | 2025-07-03
8 | [5 empty] | 2025-09-04 |  |  |  | 8 | 8. Product Add On | Crane Hire |  |  | 9900 | PO4185-RR-20250730 - RV Approved | Supply Chain Optimiser: SCO05200 | 2025-08-31 | 46812.8076 |  | 2025-09-04
[6 empty] | 2025-08-31 |  |  |  | 8 | 8. Product Add On | Offloading |  |  | 14200 |  | HappySolar - INV-0330 | 2025-08-31 | 62152.2685 |  | 2025-08-31
[10 empty] | 8 | 8. Product Add On | Replacement of Gas Extinguishing System |  |  | 0
8 | [9 empty] | 8 | 8. Product Add On | Replacement of Gas Extinguishing System - V&A |  |  | 27294.75 | PO4463-RR-20251111 - RV Approved |  | 2026-02-28 | 0 |  | 2026-02-28
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 341000 | 2025-08-27 | 687500 | 772471.9101 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.0026196 |  | 900817.81
9 |  | DC Installation Budget |  |  | 346500 | 2025-08-28 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 900817.81 | 10% | 90081.781 |  | JA Electrical Inv 1083 | 2025-08-31 | 77247.191 |  | 2025-08-14
9 | [5 empty] | 2025-08-29 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 135122.6715 |  | JA Electrical Inv 1083 | 2025-08-31 | 115870.7865 |  | 2025-08-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 180163.562 |  | JA Electrical Inv 1083 | 2025-09-30 | 154494.382 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 225204.4525 |  | JA Electrical Inv 1083 | 2025-10-31 | 189849.5333 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 90081.781 |  | JA Electrical Inv 1083 | 2025-10-31 | 78336.6733 |  | 2025-11-28
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 90081.781 |  | JA Electrical Inv 1083 | 2025-10-31 | 78336.6733 |  | 2025-12-05
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 45040.8905 |  | JA Electrical Inv 1083 | 2025-10-31 | 39168.3367 |  | 2025-12-05
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 45040.8905 |  | JA Electrical Inv 1083 | 2025-10-31 | 39168.3367 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | Reduced system Size |  |  | 0 |  |  | 2025-12-31 | 0 |  | 2025-12-31
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-06-26 | 8500 | 9550.5618 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0019372 |  | 216404.8
10 |  | Scaffolding |  |  | 0 | 2025-06-27 |  |  |  | 10 | 10. Site Logistics | Container rental |  |  | 6100 |  | Container World PFC02316 | 2025-06-30 | 195.4653 |  | 2025-06-27
[6 empty] | 2025-08-07 |  |  |  | 10 | 10. Site Logistics |  |  |  | 100 |  | Container World - C581575 | 2025-06-30 | 3.2043 |  | 2025-08-07
[6 empty] | 2025-08-21 |  |  |  | 10 | 10. Site Logistics |  |  |  | 4900 |  | Container World - CM19729 | 2025-07-31 | 267.0403 |  | 2025-08-21
[6 empty] | 2025-08-30 |  |  |  | 10 | 10. Site Logistics | Container Rental - August |  |  | 620 |  | Container World - C585034 | 2025-07-31 | 44.7855 |  | 2025-08-30
10 |  | Security |  |  | 0 | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | Container Rental - September |  |  | 600 |  | Container World - C588469 | 2025-08-31 | 24.663 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | 6900 |  | Container World - C580803 | 2025-08-31 | 0 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | 0 |  | Container World -C588469 | 2025-08-31 | 0 |  | 2025-09-30
[6 empty] | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | Container Rental - October |  |  | 620 |  | Container World - C591997 | 2025-09-30 |  |  | 2025-10-31
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | -5700 |  | Container World -CCM13070 | 2025-08-31 | 0 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | -6100 |  | Container World -PFC02316 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics | Container Rental - November |  |  | 600 |  | Container World -C595541 | 2025-10-31 | 0 |  | 2025-11-13
10 |  | Storage |  |  | 0 |  |  |  |  | 10 | 10. Site Logistics | Container Rental - December |  |  | 620 |  | Container World -C599043 | 2025-11-30 | 0 |  | 2025-12-04
[10 empty] | 10 | 10. Site Logistics |  |  |  | -400 |  | Container World -CC43644 | 2025-12-31 |  |  | 2026-01-09
[10 empty] | 10 | 10. Site Logistics
10 | [5 empty] | 2025-08-28 |  |  |  | 10 | 10. Site Logistics |  | 207544.8 | 10% | 20754.48 |  | JA Electrical Inv 1083 | 2025-08-31 | 901.5401 |  | 2025-08-14
10 | [5 empty] | 2025-08-29 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 31131.72 |  | JA Electrical Inv 1083 | 2025-08-31 | 1352.3102 |  | 2025-08-29
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 41508.96 |  | JA Electrical Inv 1083 | 2025-08-31 | 1803.0803 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 51886.2 |  | JA Electrical Inv 1083 | 2025-10-31 | 2253.8504 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 20754.48 |  | JA Electrical Inv 1083 | 2025-10-31 | 901.5401 |  | 2025-11-28
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 20754.48 |  | JA Electrical Inv 1083 | 2025-10-31 | 901.5401 |  | 2025-12-05
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 10377.24 |  | JA Electrical Inv 1083 | 2025-10-31 | 450.7701 |  | 2025-12-05
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 10377.24 |  | JA Electrical Inv 1083 | 2025-10-31 | 450.7701 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 17050 | 2025-08-29 | 77050 | 86573.0337 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 24500 |  | SunSpot E030 | 2025-11-30 | 33132.8878 | 0.0028191 | 2025-11-28 | 52000
11 | [5 empty] | 2025-08-30 |  |  |  | 11 | 11. Due Dilligence | Structural Assessment |  |  | 7500 |  | L&B Consulting: INV-2036 | 2025-07-31 | 19947.7036 |  | 2025-08-30
11 | [5 empty] | 2025-09-30 |  |  |  | 11 | 11. Due Dilligence |  |  |  | 12000 |  | L&B Consulting - INV-2087 | 2025-09-30 | 17946.2157 |  | 2025-09-30
11 |  | Grid Study - Outside of CoCT |  |  | 60000 | 2025-09-30 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 8000 |  | Matriarch - INV-5370 | 2025-10-31 | 15546.2238 |  | 2025-11-30
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 122812.8372 | 2025-09-30 | 434412.8372 | 488104.3115 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 154022.95 |  | Matriarch - INV-5976 | 2025-12-31 | 488104.3115 | 0 | 2026-01-29 | 154022.95
13 |  | Management |  |  | 52000 | 2025-09-30 |  |  |  | 13 | 13. Engineering | Management | [6 empty] | 0
13 |  | Project manager |  |  | 149600 | 2025-09-30 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 62400 | 2025-09-30 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 47600 | 2025-09-30 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 11900 | 2025-07-04 | 11900 | 13370.7865 |  | 14 | 14. General Expenses | Travel |  |  | 1418.96 |  | Expense Claim | 2025-06-30 | 2574.6702 | 0.0020815 | 2025-07-04 | 8514.52
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 735.36 |  | Expense Claim | 2025-07-31 | 887.4499 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 861.56 |  | Expense Claim | 2025-08-31 | 422.6015 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1311.5 |  | Expense Claim | 2025-09-30 | 1080.6296 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2775.54 |  | Expense Claim | 2025-10-31 | 309.8267 |  | 2025-11-06
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 123.76 |  | Expense Claim | 2025-12-31 | 162.2055 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 637.84 |  | Expense Claim | 2026-01-31 | 1001.6328 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 650 |  |  | 2026-02-28 | 6931.7683 |  | 2026-03-05
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | JA Electrical - Additional scope and EE changes - VO |  |  | 52687.9739 | PO4513-RR-20251202 - RV Approved | JA Electrical - INV 1158 | 2026-02-28 |  | 0 | 2026-02-20 | 156196.8839
15 | [9 empty] | 15 | 15. Service Add On | Domestic Transport |  |  | 5500 | PO4437-GEN-20251103 - RV Approved | ABL Transport Invoice 0205 | 2025-11-30 |  |  | 2025-11-06
15 | [9 empty] | 15 | 15. Service Add On | Courier of Sonel Meter for Testing |  |  | 801.11 |  | DSV Inv: 180153158 | 2025-10-31 |  |  | 2025-11-28
15 | [9 empty] | 15 | 15. Service Add On | Transport Modules to stock |  |  | 11500 |  | ABL Transport Inv 0215 | 2025-11-30 |  |  | 2025-11-13
15 | [9 empty] | 15 | 15. Service Add On | Additional trip for excess stock - VO |  |  | 2500 |  | ABL Transport Inv 0220 | 2025-11-30 |  |  | 2025-11-19
15 | [9 empty] | 15 | 15. Service Add On | Installation of SPD |  |  | 5450 | PO4492-20251126 - RV Apporoved | Happysolar Inv: 0344 | 2025-11-30 |  |  | 2025-12-04
15 | [9 empty] | 15 | 15. Service Add On | Additional Meters |  |  | 61237.8 | PO4511-RR-20251201 - RV Approved | Craigcor - PI141993 | 2026-01-31 | 70757.8 |  | 2026-01-15
15 | [9 empty] | 15 | 15. Service Add On | Installation of Meter |  |  | 9520 | PO4532-RR-20251209 - RV Approved | HappySolar - INV-0351 | 2026-01-31 |  |  | 2026-01-29
15 | [9 empty] | 15 | 15. Service Add On | Tie - in 2 Isolation Transformer Bypass |  |  | 7000 | JP Approved (no PO) | HappySolar - INV-0353 | 2026-02-28 |  |  | 2026-02-26
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1788541.3681 |  | 2235676.7101
| Inverter Procurement Budget | 356200 |  | 445250
| Mounting Structure Budget | 1186680 |  | 1483350
| DC Equipment Budget | 1208947.5 |  | 1511184.375
| AC Equipment Budget | 849891.5 |  | 1062364.375
| Monitoring Budget | 45636 |  | 57045
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 20000 |  | 25000
| ADD ON | 125000 |  | 156250
| Battery System | 3616080.6087 |  | 4017867.343
| Generator | 0 |  | 0
Services
| AC Installer Budget | 341000 |  | 383146.0674
| DC Installer Budget | 346500 |  | 389325.8427
| In-House Expense Budget | 434412.8372 |  | 488104.3115
| Compliance Budget | 77050 |  | 86573.0337
| Offloading Budget | 8500 |  | 9550.5618
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 0 |  | 0
| Roof Access Budget for Installers | 0 |  | 0
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 11900 |  | 13370.7865
Note on W206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Peet Verreynne, I am moving this date out by 2 weeks to 19 February. Let me know why we have not received an invoice and if the works are complete

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 12364058.4067 | 12321836.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4327420.4423 | 0 | 2472811.6813 | 0 | 0 | 0 | 0 | 3709217.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236405.8407 | 0 | 575980.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4327420.4423 | 4327420.4423 | 6800232.1237 | 6800232.1237 | 6800232.1237 | 6800232.1237 | 6800232.1237 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 11745855.4864 | 11745855.4864 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424 | 12321836.2424
| Planned Expenditure | 10416339.814 | 9931589.814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 11900 | 0 | 0 | 0 | 2387713.5 | 70000 | 0 | 0 | 6931480.8681 | 0 | 0 | 27582.6087 | 0 | 494412.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 20400 | 20400 | 20400 | 20400 | 2408113.5 | 2478113.5 | 2478113.5 | 2478113.5 | 9409594.3681 | 9409594.3681 | 9409594.3681 | 9437176.9768 | 9437176.9768 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814 | 9931589.814
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4318920.4423 | 4307020.4423 | 6779832.1237 | 6779832.1237 | 6779832.1237 | 4392118.6237 | 4322118.6237 | 8031336.1457 | 8031336.1457 | 1099855.2776 | 1099855.2776 | 1099855.2776 | 1072272.6689 | 1072272.6689 | 577859.8317 | 577859.8317 | 1814265.6724 | 1814265.6724 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285 | 2390246.4285
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 12392594.0424 | 12392594.0424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4327420.4423 | 0 | 0 | 0 | 0 | 0 | 0 | 6182029.2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236405.8407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646738.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4327420.4423 | 4327420.4423 | 4327420.4423 | 4327420.4423 | 4327420.4423 | 4327420.4423 | 4327420.4423 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 10509449.6457 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 11745855.4864 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424 | 12392594.0424
| Actual + Planned Expenditure | 8234669.3139 | 8234669.3139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100 | 15618.96 | 0 | 0 | 0 | 751902.62 | 15594.36 | 239023.882 | 203300 | 3181855.323 | 1293209.16 | 0 | 0 | 0 | 58737.5 | 29735.82 | 1104038.749 | 0 | -119718.26 | 175286.58 | 31519 | 13729.25 | 445620.132 | 364605.823 | 0 | 13151 | 119511.941 | 1646.04 | -276.24 | 61237.8 | 0 | 90585.35 | 637.84 | 0 | 52687.9739 | 84678.71 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100 | 21718.96 | 21718.96 | 21718.96 | 21718.96 | 773621.58 | 789215.94 | 1028239.822 | 1231539.822 | 4413395.145 | 5706604.305 | 5706604.305 | 5706604.305 | 5706604.305 | 5765341.805 | 5795077.625 | 6899116.374 | 6899116.374 | 6779398.114 | 6954684.694 | 6986203.694 | 6999932.944 | 7445553.076 | 7810158.899 | 7810158.899 | 7823309.899 | 7942821.84 | 7944467.88 | 7944191.64 | 8005429.44 | 8005429.44 | 8096014.79 | 8096652.63 | 8096652.63 | 8149340.6039 | 8234019.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139 | 8234669.3139
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6100 | -21718.96 | 4305701.4823 | 4305701.4823 | 4305701.4823 | 3553798.8623 | 3538204.5023 | 3299180.6203 | 3095880.6203 | 6096054.5007 | 4802845.3407 | 4802845.3407 | 4802845.3407 | 4802845.3407 | 4744107.8407 | 4714372.0207 | 3610333.2717 | 3610333.2717 | 3730051.5317 | 4791170.7924 | 4759651.7924 | 4745922.5424 | 4300302.4104 | 3935696.5874 | 3935696.5874 | 3922545.5874 | 3803033.6464 | 3801387.6064 | 4448402.4024 | 4387164.6024 | 4387164.6024 | 4296579.2524 | 4295941.4124 | 4295941.4124 | 4243253.4385 | 4158574.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285 | 4157924.7285
|  | CHECK | CHECK
| Revenue Recognition | -28535.6332 | 12392594.0399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148228.4719 | 0 | 0 | 0 | 5414467.3143 | 0 | 0 | 0 | 2626491.7495 | 0 | 0 | 0 | 0 | 173521.2273 | 0 | 0 | 0 | 472016.8354 | 0 | 0 | 0 | 33132.8878 | 0 | 0 | 0 | 0 | 488266.517 | 0 | 0 | 0 | 29537.2685 | 0 | 0 | 0 | 6931.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 12392594.0399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148228.4719 | 3148228.4719 | 3148228.4719 | 3148228.4719 | 8562695.7861 | 8562695.7861 | 8562695.7861 | 8562695.7861 | 11189187.5356 | 11189187.5356 | 11189187.5356 | 11189187.5356 | 11189187.5356 | 11362708.7628 | 11362708.7628 | 11362708.7628 | 11362708.7628 | 11834725.5983 | 11834725.5983 | 11834725.5983 | 11834725.5983 | 11867858.4861 | 11867858.4861 | 11867858.4861 | 11867858.4861 | 11867858.4861 | 12356125.0031 | 12356125.0031 | 12356125.0031 | 12356125.0031 | 12385662.2716 | 12385662.2716 | 12385662.2716 | 12385662.2716 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399 | 12392594.0399

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 2235676.7101 |  |  |  |  | 0 |  | 0 | -42222.1643 |  | 2193454.5458
2. Inverters |  | 445250 |  |  |  | 0 | 0 |  | 0 | 0 |  | 445250
3. Mounting Structures |  | 431028.7 | 1052321.3239 |  |  | -0.02 | 0 | 0 |  | 0 |  | 1483350.0039
4. DC Equipment |  |  | 894911.0897 | 616273.2853 |  | 0 |  |  | 0 |  |  | 1511184.375
5. Monitoring | 0 | 17332.9505 | 1789.4524 | 11579.8139 | 0 | 26342.781 | 0 |  | 0 | 0 |  | 57044.9978
6. AC Equipment |  |  |  | 1062364.375 |  | 0 |  |  | 0 |  |  | 1062364.375
8. Product Add On | 0 | 16166.7714 |  | 165083.2286 |  | 0 | 0 |  | 0 |  | 0 | 181250
9. AC & DC installation |  |  |  | 193117.9775 | 154494.382 | 424859.5532 |  | 0 | 0 |  |  | 772471.9127
10. Site Logistics | 0 | 198.6696 | 311.8258 | 4081.5937 |  | 4958.4708 | 0 |  | 0 |  |  | 9550.5599
11. Due Dilligence |  |  | 19947.7036 |  | 17946.2157 | 15546.2238 | 33132.8878 |  | 0 |  |  | 86573.0309
13. Engineering | 0 | [6 empty] | 488104.3115 | 0 |  |  | 488104.3115
14. General Expenses |  | 2574.6702 | 887.4499 | 422.6015 | 1080.6296 | 309.8267 | 0 | 162.2055 | 0 | 1001.6328 | 6931.7683 | 13370.7844
15. Service Add On | [9 empty] | 70757.8 |  | 70757.8
12. BDP Commission
7.BESS | 0 |  | 3444298.469 | 573568.874 |  |  |  |  | 0 |  |  | 4017867.343
Grand Total | 0 | 3148228.4719 | 5414467.3143 | 2626491.7495 | 173521.2273 | 472016.8354 | 33132.8878 | 488266.517 | 0 | 29537.2685 | 6931.7683 | 12392594.0399
|  | 3148228.47 | 5414467.31 | 2626491.75 | 173521.23 | 472016.84 | 33132.89 | 488266.52 |  | 29537.2685 | 6931.7683 | 12392594.0468
|  | 0.0018536 | 0.0042588 | -0.00053905 | -0.0027382 | -0.0045545 | -0.0021953 | -0.0030349 |  | 0 | 0
12392594.0424
-0.0043625

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 1282447.6 |  |  |  |  | -18502.4 |  |  |  | 1263945.2
2. Inverters |  | 315880 |  |  |  | 68050 | 1646.04 |  | -69140 |  | 316436.04
3. Mounting Structures |  | 344822.96 | 559179.16 |  |  | 855 | -15268.56 |  | -2050.1 |  | 887538.46
4. DC Equipment |  |  | 324000 | 223119.98 |  | -175500 |  |  |  |  | 371619.98
5. Monitoring | 0 | 17131.5 | 13419.5 | 56847 | -6750 | 124955.75 | -3780 |  | -1767.5 |  | 200056.25
6. AC Equipment |  |  |  | 1058756.23 |  | 13151 |  |  |  |  | 1071907.23
8. Product Add On | 0 | 14200 |  | 36608.5 |  | 20597.8 | 139053.14 |  |  | 46289.75 | 256749.19
9. AC & DC installation |  |  |  | 225204.4525 | 180163.562 | 495449.7955 |  | 0 |  |  | 900817.81
10. Site Logistics |  | 6200 | 5520 | 89095.16 | 620 | 114749.64 | 620 | -400 |  |  | 216404.8
11. Due Dilligence |  |  | 7500 |  | 12000 | 8000 | 24500 |  |  |  | 52000
13. Engineering | 0 | [6 empty] | 154022.95 |  |  | 154022.95
14. General Expenses |  | 1418.96 | 735.36 | 861.56 | 1311.5 | 2775.54 | 0 | 123.76 | 637.84 | 650 | 8514.52
15. Service Add On | [5 empty] | 801.11 | 24950 |  | 70757.8 | 60591.17 | 157100.08
12. BDP Commission
7.BESS |  |  | 1981660 | 396800 | [6 empty] | 2378460
Grand Total | 0 | 1982101.02 | 2892014.02 | 2087292.8825 | 187345.062 | 673885.6355 | 153218.22 | 153746.71 | -1561.96 | 107530.92 | 8235572.51

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.40747 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.20844 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.14102 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.33748 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Red Rocket |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Red Rocket | 0 | 0 | 0