## Summary
FY26 Budget vs Planned vs Realised - Summary (88 FY26 trackers)
ZAR. Budget = FY26 revised Solar-PV budget (annual R275,55m; ~R272m headline). Planned = all-state tracker recognition. Realised = realised to date. Line detail on 'Line Items' tab.
Metric | Budget (FY26) | Planned (FY26) | Realised (to date) | GP%
Revenue | 275550000 | 238405936 | 134794000
Cost of Sales | 241440000 | 216825559 | 118025634
Gross Profit | 34110000 | 21580377 | 16768366
GP % | 12.4 | 9.1 | 12.4
Line items (FY26 recognition lines): 2864 across 88 trackers. See 'Line Items' tab (one row per REV/COS recognition line).

## REV (monthly)
FY26 Revenue - Budget vs Planned vs Realised
Budget=Solar-PV revised. Planned=all-state tracker recognition by invoice month. Realised=realised by invoice month. ZAR.
Month | Budget | Planned | Realised | Plan vs Bud | Real vs Bud | Real vs Plan
Sep-25 | 6961493 | 2825580 | 2340384 | -4135913 | -4621109 | -485196
Oct-25 | 14078035 | 16478536 | 16296108 | 2400501 | 2218073 | -182428
Nov-25 | 17278981 | 20983731 | 20670319 | 3704750 | 3391337 | -313412
Dec-25 | 10663361 | 4375512 | 4376565 | -6287849 | -6286795 | 1054
Jan-26 | 10674966 | 5410236 | 5518527 | -5264730 | -5156440 | 108291
Feb-26 | 17848112 | 8024918 | 7568069 | -9823194 | -10280044 | -456849
Mar-26 | 17620281 | 22299181 | 22201880 | 4678900 | 4581599 | -97301
Apr-26 | 18563124 | 21842049 | 21654549 | 3278925 | 3091425 | -187500
May-26 | 26131558 | 31963683 | 31876183 | 5832125 | 5744625 | -87500
Jun-26 | 35921446 | 38981469 | 2291417 | 3060023 | -33630028 | -36690051
Jul-26 | 33687409 | 40146677 | 0 | 6459269 | -33687409 | -40146677
Aug-26 | 66121234 | 25074365 | 0 | -41046869 | -66121234 | -25074365
FY26 TOTAL | 275550000 | 238405936 | 134794000 | -37144064 | -140756000 | -103611936

## COS (monthly)
FY26 Cost of Sales - Budget vs Planned vs Realised
COS by month. ZAR.
Month | Budget | Planned | Realised | Plan vs Bud | Real vs Bud | Real vs Plan
Sep-25 | 6099738 | 2916997 | 2558030 | -3182741 | -3541709 | -358967
Oct-25 | 12335332 | 13456500 | 13344318 | 1121168 | 1008986 | -112182
Nov-25 | 15140037 | 15599057 | 15597237 | 459020 | 457200 | -1820
Dec-25 | 9343356 | 4391824 | 4390004 | -4951532 | -4953352 | -1820
Jan-26 | 9353525 | 5535819 | 5595930 | -3817706 | -3757595 | 60111
Feb-26 | 15638716 | 6440508 | 6440508 | -9198208 | -9198208 | 0
Mar-26 | 15439088 | 18918666 | 18918550 | 3479578 | 3479462 | -116
Apr-26 | 16265217 | 21341799 | 21341799 | 5076581 | 5076581 | 0
May-26 | 22896764 | 27163951 | 27163951 | 4267187 | 4267187 | 0
Jun-26 | 31474774 | 37071598 | 2675308 | 5596825 | -28799466 | -34396290
Jul-26 | 29517285 | 38254055 | 0 | 8736769 | -29517285 | -38254055
Aug-26 | 57936167 | 25734786 | 0 | -32201381 | -57936167 | -25734786
FY26 TOTAL | 241440000 | 216825559 | 118025634 | -24614441 | -123414366 | -98799925

## GP (monthly)
FY26 Gross Profit - Budget vs Planned vs Realised
GP = REV - COS by month. ZAR.
Month | Budget | Planned | Realised | Plan vs Bud | Real vs Bud | Real vs Plan
Sep-25 | 861755 | -91417 | -217646 | -953172 | -1079400 | -126229
Oct-25 | 1742703 | 3022036 | 2951790 | 1279334 | 1209088 | -70246
Nov-25 | 2138944 | 5384674 | 5073082 | 3245730 | 2934137 | -311592
Dec-25 | 1320004 | -16312 | -13438 | -1336317 | -1333443 | 2874
Jan-26 | 1321441 | -125583 | -77404 | -1447024 | -1398845 | 48179
Feb-26 | 2209396 | 1584410 | 1127561 | -624986 | -1081835 | -456849
Mar-26 | 2181193 | 3380515 | 3283330 | 1199322 | 1102137 | -97185
Apr-26 | 2297907 | 500250 | 312750 | -1797657 | -1985157 | -187500
May-26 | 3234794 | 4799732 | 4712232 | 1564938 | 1477438 | -87500
Jun-26 | 4446672 | 1909870 | -383891 | -2536802 | -4830563 | -2293761
Jul-26 | 4170123 | 1892623 | 0 | -2277500 | -4170123 | -1892623
Aug-26 | 8185067 | -660421 | 0 | -8845489 | -8185067 | 660421
FY26 TOTAL | 34110000 | 21580377 | 16768366 | -12529623 | -17341634 | -4812011

## Line Items
FY26 recognition line items (REV & COS) - 88 trackers
One row per Expenditure-Breakdown recognition line with an FY26 invoice-raised date. State from font colour. ZAR.
Month | Invoice raised | Project | State | Invoice no | REV | COS | GP | Finance payment date | Supplier / Description | PO | Source tracker | Sheet | Row
Sep-25 | 30/09/2025 | 1 Bolt Ave | Realised | Schletter - INV2244 | 178536.59 | 69250 | 109286.59 | 30/10/2025 |  | PO4324-BOLT-20250925 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 21
Sep-25 | 30/09/2025 | 1 Bolt Ave | Realised | Accuenergy - ASAI-006478 | 31168.85 | 22615.5 | 8553.35 | 30/10/2025 |  | PO4325-BOLT-20250925 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 45
Sep-25 | 30/09/2025 | 1 Bolt Ave | Realised | Red Pole - SO-35912 | 1343.75 | 975 | 368.75 | 09/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 48
Sep-25 | 30/09/2025 | 1 Bolt Ave | Realised | Rbicon - INVWCRE-0070990 | 87904.91 | 44000 | 43904.91 | 30/10/2025 |  | PO4326-BOLT-20250925 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 82
Sep-25 | 30/09/2025 | 1 Bolt Ave | Realised | Expense Claims | 62.9 | 28.56 | 34.34 | 10/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 137
Sep-25 | 30/09/2025 | Black Heath | Realised | Livewire - QLEC17355 | 0 | 10666 | -10666 | 26/09/2025 |  |  | Black Heath_Tracker.xlsx | Expenditure Breakdown | 123
Sep-25 | 30/09/2025 | Blackheath Park | Realised | Allocated to Milkwood | 0 | -81000 | 81000 | 30/09/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 29
Sep-25 | 30/09/2025 | Blackheath Park | Realised | Red Pole - SO-35912 | 0 | 975 | -975 | 25/09/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | Blackheath Park | Realised | Container World - C591996 | 1589.39 | 620 | 969.39 | 30/09/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 118
Sep-25 | 30/09/2025 | Blackheath Park | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 157
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Schletter - INVQ0135 | 0 | -344700 | 344700 | 30/09/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 23
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Schletter - CRN0273 | 0 | -344700 | 344700 | 30/09/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 24
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Schletter - INV2238 | 0 | 694199.98 | -694199.98 | 30/09/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 25
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Schletter INVQ0136 | 0 | -25790.99 | 25790.99 | 30/10/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 30
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Fidelis Solar - INV0000186 | 41473.91 | 27360 | 14113.91 | 18/09/2025 |  | PO4316-BMGFT-20250916 - RV approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 107
Sep-25 | 30/09/2025 | BMG Fluid Tech | Realised | Expense Claim | 820.2 | 845.78 | -25.58 | 10/10/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 169
Sep-25 | 30/09/2025 | Bochum Plaza | Realised | Shanduko Projects - QT2364 | 0 | 14200 | -14200 | 09/10/2025 |  | PO4337-DBP-20250929 - RV Approved | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 85
Sep-25 | 30/09/2025 | Bochum Plaza | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 147
Sep-25 | 30/09/2025 | Bochum Plaza | Realised | Cosmic Sun - CS_BPZ_009 | 56488.17 | 25801.88 | 30686.29 | 24/10/2025 |  |  | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 158
Sep-25 | 30/09/2025 | Boston Circle | Realised | Mantech - CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | Boston Circle_Tracker.xlsx | Expenditure Breakdown | 51
Sep-25 | 30/09/2025 | Boston Circle | Realised | CurrentAutomation Inv: SOQ324142 | 0 | 1214.1 | -1214.1 | 09/09/2025 |  |  | Boston Circle_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | Boundary Terraces | Realised | Menlo - CRN0000252 | 0 | -43606.08 | 43606.08 | 26/09/2025 |  |  | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 15
Sep-25 | 30/09/2025 | Boundary Terraces | Realised | DSV Inv: 180145917 | 0 | 209.27 | -209.27 | 31/10/2025 |  |  | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 49
Sep-25 | 30/09/2025 | Boundary Terraces | Realised | Mantech - CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | Boundary Terraces | Realised | Current Automotion - SOQ324142 | 0 | 1214.1 | -1214.1 | 09/09/2025 |  |  | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Schletter - CRN0271 | 0 | -1540370 | 1540370 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 47
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Schletter - CRN0272 | 0 | -1540370 | 1540370 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 48
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Schletter - INV2231 | 0 | 3006740 | -3006740 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 49
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Schletter - CRN0271 | 0 | -37000 | 37000 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Schletter - CRN0272 | 0 | -37000 | 37000 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Mantech INV1078143 | 335.82 | 1060 | -724.18 | 04/09/2025 |  | PO4259-CSHP2-20250821 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 107
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Container World - P594608 | 0 | 2635 | -2635 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 291
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Container World - P594597 | 0 | 1550 | -1550 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 292
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Container World - P594595 | 0 | 1550 | -1550 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 293
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Talisman Hire:Inv 212767 | 1258.87 | 2173.92 | -915.05 | 09/10/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 317
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Matriarch Inv: 5050 | 3164.39 | 2843 | 321.39 | 31/08/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 360
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 32154.96 | -32154.96 | 10/10/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 375
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76502 | 0 | 135.99 | -135.99 | 10/09/2025 |  | PO4303-CSPH2-20250909 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 396
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76691 | 0 | 2719.8 | -2719.8 | 23/09/2025 |  | PO4323-CSPH2-20250922 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 397
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76718 | 0 | 271.98 | -271.98 | 30/09/2025 |  | PO4324-CSPH2-20250925 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 398
Sep-25 | 30/09/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76726 | 0 | 271.98 | -271.98 | 30/09/2025 |  | PO4344-CSPH2-20250930 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 399
Sep-25 | 30/09/2025 | Corporate Park | Realised | Menlo - INV0003230 | 0 | 800 | -800 | 06/11/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 8
Sep-25 | 30/09/2025 | Corporate Park | Realised | Menlo INV0003243 | 0 | 8598.34 | -8598.34 | 06/11/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 46
Sep-25 | 30/09/2025 | Corporate Park | Realised | Expense Claims | 0 | 1307.83 | -1307.83 | 10/10/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 159
Sep-25 | 30/09/2025 | Corporate Park | Realised | DSV Inv:180147748 | 0 | 237.1 | -237.1 | 31/10/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 169
Sep-25 | 30/09/2025 | Dobsonpoint | Realised | Lutendo Construction: Inv INV00826 | 0 | 15220 | -15220 | 09/10/2025 |  | PO4354-DDC-20251006 - RV Approved | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 88
Sep-25 | 30/09/2025 | Dobsonpoint | Realised | JerryG & Sons INV13 | 2203.77 | 25500 | -23296.23 | 02/10/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 112
Sep-25 | 30/09/2025 | Dobsonpoint | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 152
Sep-25 | 30/09/2025 | Dobsonpoint | Realised | Thula Moya - IN04887 | 125000 | 91474.57 | 33525.43 | 11/09/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 165
Sep-25 | 30/09/2025 | Dobsonpoint | Realised | Thula Moya - IN04887 | 125000 | 91474.57 | 33525.43 | 12/12/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 166
Sep-25 | 30/09/2025 | Gezina Galleries | Realised | Bidvest Protea Coin: 760988 | 41618.08 | 59780 | -18161.92 | 31/10/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 107
Sep-25 | 30/09/2025 | Gezina Galleries | Realised | Bidvest Protea Coin: 760989 | 42250.3 | 59780 | -17529.7 | 09/10/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 108
Sep-25 | 30/09/2025 | Gezina Galleries | Realised | Expense Claim | 2071.13 | 980.56 | 1090.57 | 10/10/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 148
Sep-25 | 30/09/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_009 | 0 | 19400 | -19400 | 24/10/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 162
Sep-25 | 30/09/2025 | Gillwell | Realised | Sizisa Ukhanyo Developments Inv: A0018 | 0 | 12930 | -12930 | 30/09/2025 |  | PO4317-GILL-20250916 - RV Approved | Gillwell_Tracker.xlsx | Expenditure Breakdown | 88
Sep-25 | 30/09/2025 | Gillwell | Realised | Krannich - INV 15-10013984 | 0 | 97632.57 | -97632.57 | 28/11/2025 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 92
Sep-25 | 30/09/2025 | Gillwell | Realised | Expense Claim | 1151.09 | 5002.96 | -3851.87 | 10/10/2025 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 147
Sep-25 | 30/09/2025 | Gillwell | Realised | Cosmic Sun - CS_GWM_009 | 0 | 57750 | -57750 | 02/10/2025 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 158
Sep-25 | 30/09/2025 | IconSA | Realised | Red Pole Energy:SO-35912 | 0 | 975 | -975 | 10/09/2025 |  |  | IconSA_Tracker.xlsx | Expenditure Breakdown | 66
Sep-25 | 30/09/2025 | IconsSA_KZN | Realised | Schletter Inv: INV2149 | 103363.5 | 83929.11 | 19434.39 | 30/10/2025 |  | PO4272-IKZN-20250825 - RV Approved | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 21
Sep-25 | 30/09/2025 | IconsSA_KZN | Realised | Precast Structural - IN44436 | 21827.5 | 17723.5 | 4104 | 11/09/2025 |  | PO4293-IKZN-20250902 - RV Approved | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 22
Sep-25 | 30/09/2025 | IconsSA_KZN | Realised | Red Pole - SO-35912 | 2345.42 | 975 | 1370.42 | 09/10/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 49
Sep-25 | 30/09/2025 | Kroonstad | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 152
Sep-25 | 30/09/2025 | Kroonstad | Realised | Cosmic Sun: CS_KRN_009 | 0 | 16006.25 | -16006.25 | 02/10/2025 |  | PO4342-DPK-20250930 - RV Approved | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 163
Sep-25 | 30/09/2025 | Lynnridge Mall | Realised | JA Electrical - INV1092 | 0 | 79042.5 | -79042.5 | 25/09/2025 |  | PO4296-LYNN-20250903 - RV Approved | Lynnridge Mall_Tracker_1.xlsx | Expenditure Breakdown | 132
Sep-25 | 30/09/2025 | Marikana Old Church | Realised | Van Staden Three INV3000 | 0 | 44621.25 | -44621.25 | 02/10/2025 |  | PO4321-MAR-OC-20250919 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 84
Sep-25 | 30/09/2025 | Marikana Old Church | Realised | Van Staden Group Inv: 1655 | 0 | 6483.33 | -6483.33 | 13/10/2025 |  | PO4326-MAR-OC-20250929 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 86
Sep-25 | 30/09/2025 | Marikana Old Church | Realised | JerryG & Sons INV12 | 23508.19 | 48560 | -25051.81 | 02/10/2025 |  | PO4256-MAROC-20250831 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 107
Sep-25 | 30/09/2025 | Marikana Old Church | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 148
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | Van Staden Three INV3001 | 0 | 61125.75 | -61125.75 | 02/10/2025 |  | PO4322-MAR-SR-20250919 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 84
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | Van Staden Group Inv: 1656 | 0 | 12966.66 | -12966.66 | 13/10/2025 |  | PO4326-MAR-OC-2025092 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 86
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | Greenway Solar: INV0001425 | 198540.44 | 216687.15 | -18146.71 | 16/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 94
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | Greenway Solar: INV0001425 | 79416.18 | 86674.86 | -7258.68 | 16/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 95
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | JerryG & Sons: INV14 | 0 | 39900 | -39900 | 02/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 108
Sep-25 | 30/09/2025 | Marikana Shoprite | Realised | Expense Claim | 2060.36 | 862.99 | 1197.37 | 10/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 150
Sep-25 | 30/09/2025 | Mayo Macs | Realised | Sunray Energy Solutions #89 | 0 | 14110 | -14110 | 11/09/2025 |  | PO4312-MMS-20250916 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 136
Sep-25 | 30/09/2025 | Meraki Ph3 | Realised | Krannich -15-10013950 | 0 | 14516 | -14516 | 28/11/2025 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 9
Sep-25 | 30/09/2025 | Meraki Ph3 | Realised | DSV Inv: 180142244 | 0 | 223.56 | -223.56 | 31/10/2025 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 126
Sep-25 | 30/09/2025 | Meraki Ph3 | Realised | Thula Moya IN04906 | 0 | 69571.56 | -69571.56 | 02/10/2025 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 127
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | Schletter - INV2155 | 181694.12 | 96112.72 | 85581.4 | 30/10/2025 |  | PO4291-MLKW-20250901 - RV Approved | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 21
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | Allocated from Spear - Blackheath | 0 | 81000 | -81000 | 30/09/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 29
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | DSV Inv:180147748 | 478.58 | 297.62 | 180.96 | 30/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 47
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | Rubicon - INVWCRE-0070809 | 142740.14 | 85000 | 57740.14 | 30/10/2025 |  | PO4318-MLKW-20250916 - RV Approved | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 48
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | Mantech QUO124941 | 1913.55 | 1190 | 723.55 | 11/09/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 49
Sep-25 | 30/09/2025 | Milkwood_Square | Realised | Expense Claim | 2054.94 | 2831.27 | -776.33 | 10/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 136
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | Allocated to Stock | 0 | -1095 | 1095 | 30/09/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 24
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | Allocated to Stock | 0 | -576 | 576 | 30/09/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 25
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | Mantech - CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 50
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | Current Automotion - SOQ324142 | 0 | 1214.1 | -1214.1 | 10/09/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 51
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | HAPPYSAOLAR - INV-0328 | 6199.83 | 11970 | -5770.17 | 16/10/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 99
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | HAPPYSAOLAR - INV-0328 | 6199.83 | 11970 | -5770.17 | 16/10/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 100
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | HAPPYSAOLAR - INV-0328 | 3099.92 | 5985.01 | -2885.09 | 30/10/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 101
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | HAPPYSAOLAR - INV-0328 | 3099.91 | 5985 | -2885.09 | 19/11/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 102
Sep-25 | 30/09/2025 | Newlands Terraces | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 142
Sep-25 | 30/09/2025 | Northpoint | Realised | Allocated to Cpt Storeroom | 0 | -8160 | 8160 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 22
Sep-25 | 30/09/2025 | Northpoint | Realised | Allocated to Cpt Storeroom | 0 | -7095.6 | 7095.6 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 23
Sep-25 | 30/09/2025 | Northpoint | Realised | Allocated to Cpt Storeroom | 0 | -800.08 | 800.08 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 24
Sep-25 | 30/09/2025 | Northpoint | Realised | Uber: C/C DS 100902 | 0 | 172 | -172 | 10/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 47
Sep-25 | 30/09/2025 | Northpoint | Realised | Mantech-CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | Northpoint | Realised | Current Automotion - SOQ324142 | 0 | 1214.1 | -1214.1 | 10/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 86
Sep-25 | 30/09/2025 | Northpoint | Realised | Container World - C591998 | 0 | 620 | -620 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 113
Sep-25 | 30/09/2025 | Northpoint | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 148
Sep-25 | 30/09/2025 | Parklands | Realised | Leading Edge - INV-0148 | 0 | -0.01 | 0.01 | 24/10/2025 |  |  | Parklands_Tracker.xlsx | Expenditure Breakdown | 44
Sep-25 | 30/09/2025 | Parklands | Realised | Mantech - CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | Parklands_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | Parklands | Realised | Current Automotion Inv: SOQ324142 | 0 | 1214.1 | -1214.1 | 10/09/2025 |  |  | Parklands_Tracker.xlsx | Expenditure Breakdown | 54
Sep-25 | 30/09/2025 | Pimville | Realised | Lutendo Construction Inv: INV00825 | 0 | 15930 | -15930 | 09/10/2025 |  | PO4353-DPS-20251006 - RV Approved | Pimville_Tracker.xlsx | Expenditure Breakdown | 87
Sep-25 | 30/09/2025 | Pimville | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 153
Sep-25 | 30/09/2025 | Pretoria North | Realised | Supply Chain - SCO05262 | 17311.85 | 22800 | -5488.15 | 06/11/2025 |  | PO4283-DIP-Ph2-Shoprite-20250827 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 111
Sep-25 | 30/09/2025 | Pretoria North | Realised | GSG Tactical - INV000013885 | 14421.77 | 27900 | -13478.23 | 09/10/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 112
Sep-25 | 30/09/2025 | Pretoria North | Realised | Expense Claim | 1983.83 | 1085.28 | 898.55 | 30/09/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 151
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 51246.51 | 46634.32 | 4612.19 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 37
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 25623.25 | 23317.16 | 2306.09 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 38
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 131599.38 | 83828.81 | 47770.58 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 59
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 65799.69 | 41914.4 | 23885.29 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 60
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 95587.06 | 81249 | 14338.06 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 91
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 47793.53 | 40624.5 | 7169.03 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 92
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 10602.53 | 9012.15 | 1590.38 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 107
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 5301.27 | 4506.08 | 795.19 | 19/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 108
Sep-25 | 30/09/2025 | Protea Point | Unrealised |  | 30660 | 26061 | 4599 | 05/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 114
Sep-25 | 30/09/2025 | Protea Point | Committed | Expense Claim | 2141.18 | 1820 | 321.18 | 30/09/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 136
Sep-25 | 30/09/2025 | Randfontein | Realised | Menlo - INV0003274 | 0 | 4601.4 | -4601.4 | 19/11/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 9
Sep-25 | 30/09/2025 | Randfontein | Realised | Expense Claim | 0 | 0 | 0 | 09/10/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 149
Sep-25 | 30/09/2025 | Randfontein | Realised | Thula Moya IN04886 | 5570.41 | 27040.37 | -21469.96 | 11/09/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 164
Sep-25 | 30/09/2025 | Randfontein | Realised | Thula Moya IN04886 | 5570.41 | 44528.63 | -38958.22 | 02/10/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 165
Sep-25 | 30/09/2025 | Randfontein | Realised | Thula Moya IN04886 | 5570.41 | 71569 | -65998.59 | 04/12/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 166
Sep-25 | 30/09/2025 | Red Rocket | Realised | Allocated to Cpt Stockroom | 0 | -2970 | 2970 | 30/09/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 51
Sep-25 | 30/09/2025 | Red Rocket | Realised | Allocated to Cpt Stockroom | 0 | -3780 | 3780 | 30/09/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 154494.38 | 180163.56 | -25669.18 | 16/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 141
Sep-25 | 30/09/2025 | Red Rocket | Realised | Container World - C591997 | 0 | 620 | -620 | 31/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 159
Sep-25 | 30/09/2025 | Red Rocket | Realised | L&B Consulting - INV-2087 | 17946.22 | 12000 | 5946.22 | 30/09/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 180
Sep-25 | 30/09/2025 | Red Rocket | Realised | Expense Claim | 1080.63 | 1311.5 | -230.87 | 10/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 197
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Matriarch - INV-4742 | 7261.72 | 11169 | -3907.28 | 31/08/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 54
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Rubicon INVWCRE-0069079 | 28607.37 | 44000 | -15392.63 | 31/08/2025 |  | PO4077-DSHC-20250630 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 56
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Frontiline QTE107313 | 2324.67 | 3575.5 | -1250.83 | 07/08/2025 |  | PO4070-DSHC-20250630 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 62
Sep-25 | 30/09/2025 | Seshego Circle | Realised | L & B consulting Inv: 1934 | 14096.22 | 9019.6 | 5076.62 | 10/04/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 151
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Ace Properties: Inv 3031 | 15034.55 | 9620 | 5414.55 | 07/03/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 152
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Okusha Engineering EE20 | 123406.01 | 79700 | 43706.01 | 31/07/2026 |  | PO4167-DSHC-20250728 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 153
Sep-25 | 30/09/2025 | Seshego Circle | Realised | Expense Claim | 16326.89 | 13986.75 | 2340.14 | 05/09/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 166
Sep-25 | 30/09/2025 | Sibasa | Realised | Shanduka Projects - QT2365 | 0 | 24295 | -24295 | 30/09/2025 |  | PO4341-DSS-20250929 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 84
Sep-25 | 30/09/2025 | Sibasa | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 150
Sep-25 | 30/09/2025 | SupaStore | Realised | Herholdts - INV1150099 | 0 | 12701.09 | -12701.09 | 31/10/2025 |  | PO4253-SSS-20250820 | SupaStore_Tracker.xlsx | Expenditure Breakdown | 157
Sep-25 | 30/09/2025 | The Studios | Realised | Accuenergy - ASAI-006341 | 0 | 7130 | -7130 | 31/10/2025 |  | PO4300-STDS-20250908 - RV Approved | The Studios_Tracker.xlsx | Expenditure Breakdown | 47
Sep-25 | 30/09/2025 | The Studios | Realised | Mantech-CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 51
Sep-25 | 30/09/2025 | The Studios | Realised | Mantech - INV1078923 | 0 | 1300 | -1300 | 30/09/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | The Studios | Realised | Current Automotion - SOQ324142 | 0 | 1214.1 | -1214.1 | 10/09/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 85
Sep-25 | 30/09/2025 | The Studios | Realised | Matthews - INV1534 | 0 | 34654.75 | -34654.75 | 18/09/2025 |  | PO4302-STDS-20250908 - RV Approved | The Studios_Tracker.xlsx | Expenditure Breakdown | 151
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | DSV Inv: 180145917 | 0 | 209.27 | -209.27 | 31/10/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 47
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Mantech - CRN949171 | 0 | -850 | 850 | 30/09/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 52
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Current Automotion Inv: SOQ324142 | 0 | 1214.1 | -1214.1 | 10/09/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 53
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Cosmic Sun - CS_TVT_009 | 11176.47 | 11970 | -793.53 | 16/10/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 97
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Cosmic Sun - CS_TVT_009 | 11176.47 | 11970 | -793.53 | 19/11/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 98
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Cosmic Sun - CS_TVT_009 | 5588.23 | 5985 | -396.77 | 19/11/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 99
Sep-25 | 30/09/2025 | The View Tygervalley | Realised | Cosmic Sun - CS_TVT_009 | 5588.24 | 5985.01 | -396.77 | 24/12/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 100
Sep-25 | 30/09/2025 | The View Tygervalley | Unrealised |  | 1359.04 | 0 | 1359.04 | 09/10/2025 |  |  | The View Tygervalley_Tracker.xlsx | Expenditure Breakdown | 139
Sep-25 | 30/09/2025 | Tsakana Corner | Realised | Cosmic Sun: CS_TSK_009 | 0 | 7275 | -7275 | 02/10/2025 |  | PO4343-DTC-20250930 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 91
Sep-25 | 30/09/2025 | Tsakana Corner | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 152
Sep-25 | 30/09/2025 | Tsakana Corner | Unrealised |  | 17482.52 | 0 | 17482.52 | 30/09/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 165
Sep-25 | 30/09/2025 | Umzimkhulu | Realised | Menlo - INV0003277 | 0 | 4101.4 | -4101.4 | 19/11/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 8
Sep-25 | 30/09/2025 | Umzimkhulu | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 150
Sep-25 | 30/09/2025 | Upper_East_Side_Hotel | Realised | Red Pole - SO-35912 | 0 | 975 | -975 | 09/10/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 89
Sep-25 | 30/09/2025 | Upper_East_Side_Hotel | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 146
Sep-25 | 30/09/2025 | Waterside | Realised | Menlo - INV0003286 | 199846.35 | 106996.5 | 92849.85 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 6
Sep-25 | 30/09/2025 | Waterside | Realised | Menlo - INV0003286 | 4669.46 | 2500 | 2169.46 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 7
Sep-25 | 30/09/2025 | Waterside | Realised | Schletter - INV2213 | 57389.27 | 41240.97 | 16148.3 | 30/10/2025 |  | PO4258-WATER-20250831 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 21
Sep-25 | 30/09/2025 | Waterside | Realised | Menlo - INV0003286 | 60125.09 | 54600 | 5525.09 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 28
Sep-25 | 30/09/2025 | Waterside | Realised | Matthews Group - INV1533 | 4623.91 | 4199 | 424.91 | 18/09/2025 |  | PO4309-WATER-20250915 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 32
Sep-25 | 30/09/2025 | Waterside | Realised | Menlo - INV0003286 | 11738.53 | 8598.34 | 3140.19 | 26/09/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 44
Sep-25 | 30/09/2025 | Waterside | Realised | Mantech - CRN949171 | -1160.43 | -850 | -310.43 | 30/09/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 49
Sep-25 | 30/09/2025 | Waterside | Realised | Current Automotion - SOQ324142 | 1657.5 | 1214.1 | 443.4 | 10/09/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 50
Sep-25 | 30/09/2025 | Waterside | Realised | Matthews Group - INV1533 | 5195.72 | 2583.6 | 2612.12 | 18/09/2025 |  | PO4309-WATER-20250915 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 58
Sep-25 | 30/09/2025 | Waterside | Realised | Matthews Group - INV1533 | 5364.71 | 8873.2 | -3508.49 | 18/09/2025 |  | PO4309-WATER-20250915 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 90
Sep-25 | 30/09/2025 | Waterside | Realised | Matthews Group - INV1533 | 4412.76 | 3556.8 | 855.96 | 18/09/2025 |  | PO4309-WATER-20250915 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 106
Sep-25 | 30/09/2025 | Waterside | Realised | Expense Claim | 0 | 0 | 0 | 30/09/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 135
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Krannich - 15-10014113 | 982465.72 | 677100 | 305365.72 | 18/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Krannich - 15-10014113 | 20844.55 | 14365.74 | 6478.81 | 18/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 7
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Krannich - 15-10014113 | 18717.78 | 12900 | 5817.78 | 18/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 8
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Krannich - 15-10014113 | 256097.56 | 195738 | 60359.56 | 18/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 13
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Menlo - INV0003329 | 148263.87 | 109200 | 39063.87 | 12/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 28
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0158 | 30132.37 | 22193.23 | 7939.14 | 09/10/2025 |  | PO4349-BOLT-20251001 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 32
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0159 | 30132.37 | 22193.23 | 7939.14 | 09/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 33
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Menlo - INV0003329 | 11639.59 | 8598.34 | 3041.25 | 13/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 44
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Matriarch - INV-5207 | 15320.09 | 11169 | 4151.09 | 13/11/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 46
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | DSV Inv: 180150385 | 283.81 | 206.91 | 76.9 | 30/11/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 47
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0158 | 42903.64 | 17533.55 | 25370.09 | 09/10/2025 |  | PO4349-BOLT-20251001 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 59
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0159 | 42903.64 | 17533.55 | 25370.09 | 09/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 60
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Barrier Projects - 497 | 75668.14 | 37875 | 37793.14 | 09/10/2025 |  | PO4347-BOLT-20250930 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 84
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Barrier Projects - 497 | 75668.14 | 37875 | 37793.14 | 13/11/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 85
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0158 | 48500 | 48187.5 | 312.5 | 09/10/2025 |  | PO4349-BOLT-20251001 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 93
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0159 | 48500 | 48187.5 | 312.5 | 09/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 94
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0158 | 12824.24 | 13859.35 | -1035.11 | 09/10/2025 |  | PO4349-BOLT-20251001 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 109
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0159 | 12824.24 | 13859.35 | -1035.11 | 09/10/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 110
Oct-25 | 31/10/2025 | 1 Bolt Ave | Realised | Expense Claims | 299.72 | 37 | 262.72 | 06/11/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 138
Oct-25 | 31/10/2025 | Blackheath Park | Realised | Menlo INV0003324 | 0 | 81900 | -81900 | 12/12/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 30
Oct-25 | 31/10/2025 | Blackheath Park | Realised | Caltest CLTI1549 | 162840.03 | 70885.66 | 91954.37 | 03/07/2025 |  | PO4027-BLH-20250624 - RV Approved | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 60
Oct-25 | 31/10/2025 | Blackheath Park | Realised | Caltest CLTI1621 | 162840.04 | 70885.66 | 91954.38 | 28/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 61
Oct-25 | 31/10/2025 | Blackheath Park | Realised | Container World - C595540 | 1694.87 | 600 | 1094.87 | 13/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 119
Oct-25 | 31/10/2025 | Blackheath Park | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 158
Oct-25 | 31/10/2025 | BMG Fluid Tech | Unrealised |  | 35769.21 | 0 | 35769.21 |  |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 40
Oct-25 | 31/10/2025 | BMG Fluid Tech | Realised | CS_BMG_005_VO | 0 | 17891.32 | -17891.32 | 06/11/2025 |  | PO4313-BMGFT-20250916 - RV Approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 83
Oct-25 | 31/10/2025 | BMG Fluid Tech | Realised | CS_BMG_005_VO | 0 | 32171.96 | -32171.96 | 06/11/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 84
Oct-25 | 31/10/2025 | BMG Fluid Tech | Realised | Expense Claim | 1633.51 | 3844.23 | -2210.72 | 06/11/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 170
Oct-25 | 31/10/2025 | Bochum Plaza | Realised | Expense Claim | 1422.85 | 1247.84 | 175.01 | 06/11/2025 |  |  | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 148
Oct-25 | 31/10/2025 | Boston Circle | Realised | Expense claim | 0 | 176.12 | -176.12 | 06/11/2025 |  |  | Boston Circle_Tracker.xlsx | Expenditure Breakdown | 137
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Matriarch - INV-5207 | 3469.32 | 11169 | -7699.68 | 13/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 109
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | DSV Inv: 180150385 | 97.75 | 308.98 | -211.23 | 30/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 110
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Transfire Inv: UN-18217 | 1352.24 | 1376.27 | -24.03 | 10/10/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 214
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Container World - P598167 | 865.42 | 1500 | -634.58 | 13/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 296
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Container World - P598169 | 865.42 | 1500 | -634.58 | 13/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 297
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Container World - P598179 | 1471.22 | 2550 | -1078.78 | 13/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 298
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Talisman Hire:Inv 00214681 + 00214480 | 1781.02 | 3086.97 | -1305.95 | 06/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 318
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Okusha - EE18 | 58776.04 | 79700 | -20923.96 | 09/01/2026 |  | PO4078-COEG-20250701 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 337
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Matriarch Inv: 5241 | 3108.9 | 2843 | 265.9 | 28/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 361
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 20629.91 | -20629.91 | 06/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 376
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76801 | 0 | 271.98 | -271.98 | 02/10/2025 |  | PO4351-CSPH2-20251002 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 400
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation INV76861 | 0 | 12722.45 | -12722.45 | 30/10/2025 |  | PO4399-CSPH2-20251023 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 401
Oct-25 | 31/10/2025 | Coega Steels Ph2 | Realised | Ultimate Soltions INV 2636 | 0 | 1200 | -1200 | 16/10/2025 |  | PO4371-CSPH2-20251015 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 413
Oct-25 | 31/10/2025 | Corporate Park | Realised | Allocated to Icon SA - KZN | 0 | -44000 | 44000 | 31/10/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 53
Oct-25 | 31/10/2025 | Corporate Park | Realised | Allocated from Seshego Circle | 0 | 44000 | -44000 | 31/10/2025 |  | PO4077-DSHC-20250630 - RV Approved | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 54
Oct-25 | 31/10/2025 | Corporate Park | Realised | The Greenway - INV0001510 | 16658.27 | 5203 | 11455.27 | 13/02/2026 |  | PO4383-DCP-20251020 - RV Approved | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Corporate Park | Realised | Toys 4Boys - 12392 | 27307.71 | 8529.22 | 18778.49 | 28/11/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 93
Oct-25 | 31/10/2025 | Corporate Park | Realised | Expense Claims | 0 | 1901.74 | -1901.74 | 06/11/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 160
Oct-25 | 31/10/2025 | Corporate Park | Realised | Greenway Solar INV0001515 | 0 | 39935 | -39935 | 06/11/2025 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 173
Oct-25 | 31/10/2025 | Corporate Park | Realised | Greenway Solar INV0001515 | 0 | 39935 | -39935 | 05/02/2026 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 174
Oct-25 | 31/10/2025 | Dobsonpoint | Realised | JerryG & Sons INV17 | 1384.28 | 26350 | -24965.72 | 06/11/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 113
Oct-25 | 31/10/2025 | Dobsonpoint | Realised | Expense Claim | 1613.84 | 3363.46 | -1749.62 | 06/11/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 153
Oct-25 | 31/10/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_010 | 0 | 15620 | -15620 | 24/10/2025 |  | PO4351-DIP-Ph2-Gezi-20251006 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Gezina Galleries | Realised | Bidvest Protea Coin: 763696 | 4428.63 | 60760 | -56331.37 | 13/11/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 109
Oct-25 | 31/10/2025 | Gezina Galleries | Realised | Expense Claim | 3650.16 | 3618.49 | 31.67 | 06/11/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 149
Oct-25 | 31/10/2025 | Gillwell | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 148
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Krannich 15-10014209 | 447965.6 | 240370.5 | 207595.1 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Krannich 15-10014209 | 9823.63 | 5093.43 | 4730.2 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 8
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Krannich 15-10014209 | 97222.22 | 65246 | 31976.22 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 14
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Allocated from Cpt Storeroom | 50199.7 | 27000 | 23199.7 | 31/10/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 30
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Allocated from Cpt Storeroom | 50199.7 | 27000 | 23199.7 | 31/10/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 31
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1108 | 5529.14 | 2973.86 | 2555.28 | 06/11/2025 |  | PO4379-HLCD-20251017 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 34
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | AccuEnergy ASAI-006654 | 29559.17 | 24561 | 4998.17 | 30/11/2025 |  | PO4370-HLCD-20251015 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 50
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Matriarch Inv: 5366 | 26710.13 | 22338 | 4372.13 | 30/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 51
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | DSV Inv:180153158 | 410.53 | 343.33 | 67.2 | 30/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 52
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Red Pole - SO-35912 | 1165.83 | 975 | 190.83 | 07/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 53
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1108 | 7707.39 | 3412.26 | 4295.13 | 06/11/2025 |  | PO4379-HLCD-20251017 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 65
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Barrier Projects : 507 | 31111.11 | 11515 | 19596.11 | 24/10/2025 |  | PO4359-HLCD-20251007 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | Barrier Projects : 507 | 13333.33 | 4935 | 8398.33 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 90
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1108 | 11532.22 | 18598.62 | -7066.4 | 06/11/2025 |  | PO4379-HLCD-20251017 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 99
Oct-25 | 31/10/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1108 | 3912.43 | 6704.05 | -2791.62 | 06/11/2025 |  | PO4379-HLCD-20251017 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 117
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Allocated from Corporate PArk | 139319.35 | 44000 | 95319.35 | 31/10/2025 |  | PO4176-DCP-20250728 - RV Approved | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 47
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | DSV Inv: 180150385 | 1379.89 | 577.37 | 802.52 | 30/11/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 48
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Allocated from Cpt Storeroom | 3094.79 | 1300 | 1794.79 | 31/10/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 50
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 12051.2 | 11862 | 189.2 | 16/10/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 93
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 15064 | 14827.5 | 236.5 | 16/10/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 94
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 6025.6 | 5931 | 94.6 | 26/02/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 95
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 6025.6 | 5931 | 94.6 | 26/02/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 96
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 3012.8 | 2965.5 | 47.3 | 26/02/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 97
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Thula Moya IN04921 | 3012.8 | 2965.5 | 47.3 | 26/02/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 98
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Matriarch - INV-5370 | 13449.46 | 6000 | 7449.46 | 30/11/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 122
Oct-25 | 31/10/2025 | IconsSA_KZN | Realised | Matriarch - INV-5369 | 11445 | 12839.2 | -1394.2 | 30/11/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 128
Oct-25 | 31/10/2025 | Kroonstad | Realised | Rubycon - RD1112253 | 0 | 5770 | -5770 | 09/10/2025 |  | PO4355-DPK-20251006 - RV Approved | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Kroonstad | Realised | Rubycon - RD2310251 | 0 | 24908.5 | -24908.5 | 13/11/2025 |  | PO4387-DPK-202510210 - RVApproved | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Kroonstad | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 153
Oct-25 | 31/10/2025 | Kroonstad | Realised | Matriarch - INV-5208 | 0 | 5756.25 | -5756.25 | 30/11/2025 |  | PO4345-DPK-20251003 - RV Approved | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 164
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Menlo INV0003366 | 637909 | 487812 | 150097 | 28/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Menlo INV0003366 | 280682 | 174424.32 | 106257.68 | 28/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 13
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Schletter INV 2353 | 106628.8 | 45051 | 61577.8 | 28/11/2025 |  | PO4401-MBE-20251023 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 21
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Schletter INV 2353 | 7053.2 | 2980 | 4073.2 | 28/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 22
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Menlo INV0003366 | 76217.1 | 81900 | -5682.9 | 28/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 28
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001528 | 10778.99 | 11582.69 | -803.7 | 30/10/2025 |  | PO4415-MBE-20251028 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 34
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001529 | 16168.48 | 17374.04 | -1205.55 | 06/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 35
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Menlo INV0003366 | 9890.21 | 8598.34 | 1291.87 | 28/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 46
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001528 | 31666 | 38981 | -7315 | 30/10/2025 |  | PO4415-MBE-20251028 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 61
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001529 | 47499 | 58471.49 | -10972.49 | 06/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 62
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001528 | 22094.4 | 36133.4 | -14039 | 30/10/2025 |  | PO4415-MBE-20251028 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 117
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001529 | 33141.6 | 54200.1 | -21058.5 | 06/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 118
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001528 | 5312.97 | 14815.05 | -9502.08 | 30/10/2025 |  | PO4415-MBE-20251028 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 133
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001529 | 7969.45 | 22222.58 | -14253.13 | 06/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 134
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | L&B Consulting IN-2113 | 2679.88 | 11373.5 | -8693.62 | 30/10/2025 |  | PO4385-MBE-20251021 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 146
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Cosmic Sun - CS_MHK_001 | 1413.75 | 6000 | -4586.25 | 24/10/2025 |  | PO4386-MBE-20251021 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 147
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | WAGMA - INV-000001 | 5937.76 | 25200 | -19262.24 | 06/11/2025 |  | PO4422-MBE-20251029 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 150
Oct-25 | 31/10/2025 | Mahikeng Builders Express | Realised | Expense Claim | 1536.81 | 8016.46 | -6479.65 | 06/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 164
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Krannich - 15-10014204 | 458160.11 | 271968.5 | 186191.61 | 28/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Krannich - 15-10014204 | 9854.4 | 5849.67 | 4004.73 | 28/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 7
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Krannich - 15-10014204 | 26937.71 | 15990.5 | 10947.21 | 28/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 8
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Krannich - 15-10014204 | 111111.11 | 53700.89 | 57410.22 | 28/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 13
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Schletter Inv: 2352 | 24789.93 | 9972 | 14817.93 | 28/11/2025 |  | PO4402-MVE2-20251023 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 21
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Allocated from Cpt Storeoom | 1122.66 | 451.6 | 671.06 | 31/10/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 23
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Allocated from Cpt Storeoom | 1988.96 | 800.08 | 1188.88 | 31/10/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 24
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Allocated from Cpt Storeoom | 658.68 | 264.96 | 393.72 | 31/10/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 25
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Allocared from Cpt Storeoom | 14917.22 | 6000.6 | 8916.62 | 31/10/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 26
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Allocated from The Sudios | 6724.18 | 2704.87 | 4019.31 | 31/10/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 27
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | DSV Inv: 180153158 | 2643.07 | 1063.2 | 1579.87 | 30/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 31
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Menlo - INV0003367 | 117950.34 | 82900 | 35050.34 | 30/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 35
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | JA Electrical INV 111 | 5362.22 | 3768.77 | 1593.45 | 06/11/2025 |  | PO4403-MVE2-20251023 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 39
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | JA Electrical INV 111 | 22911.84 | 6474.03 | 16437.81 | 06/11/2025 |  | PO4403-MVE2-20251023 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 65
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | JA Electrical INV 111 | 13007.5 | 17554.41 | -4546.91 | 06/11/2025 |  | PO4403-MVE2-20251023 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 97
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | JA Electrical INV 111 | 2578.68 | 10598.05 | -8019.37 | 06/11/2025 |  | PO4403-MVE2-20251023 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 113
Oct-25 | 31/10/2025 | Malvern Ph2 | Realised | Expense claim | 410.25 | 326.06 | 84.19 | 06/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 141
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | The Greenway - INV0001511 | 0 | 695 | -695 | 31/10/2025 |  | PO4397-MAROC-20251023 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 80
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Van Staden Three INV3038 | 0 | 14873.75 | -14873.75 | 31/10/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 85
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | The Greenway INV0001525 | 0 | 2036 | -2036 | 31/10/2025 |  | PO4412-MAROC-20251027 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 87
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Greenway Solar - INV0001424 | 40698.53 | 51542.8 | -10844.27 | 24/10/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 94
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Greenway Solar - INV0001424 | 16279.41 | 20617.12 | -4337.71 | 30/10/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 95
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Greenway Solar - INV0001424 | 16279.41 | 20617.12 | -4337.71 | 29/01/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 96
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Greenway Solar - INV0001424 | 8139.71 | 10308.56 | -2168.85 | 05/02/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 97
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Greenway Solar - INV0001424 | 8139.71 | 10308.56 | -2168.85 | 05/03/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 98
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | JerryG & Sons INV15 | 0 | 41230 | -41230 | 06/11/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 108
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Matriarch - INV-5370 | 10995.33 | 6000 | 4995.33 | 28/11/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 128
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Matriarch - INV-5369 | 92357.15 | 25463.83 | 66893.33 | 28/11/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 135
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 149
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | The Greenway Soalr - INV0001516 | 0 | 12449 | -12449 | 06/11/2025 |  | PO4433-MAROC-20251031 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 163
Oct-25 | 31/10/2025 | Marikana Old Church | Realised | The Greenway Soalr - INV0001516 | 0 | 12449 | -12449 | 19/03/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 164
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Menlo - INV0003291 | 0 | 68870.35 | -68870.35 | 04/12/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 14
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Menlo - INV0003291 | 0 | 1000 | -1000 | 04/12/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 15
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Menlo - CRN0000261 | 0 | -68870.35 | 68870.35 | 30/11/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 16
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | The Greenway - INV0001512 | 0 | 695 | -695 | 31/10/2025 |  | PO4396-MARSR-20251023 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 80
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Van Staden Three INV3039 | 0 | 20375.25 | -20375.25 | 31/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 85
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | The Greenway - INV0001527 | 0 | 6844 | -6844 | 30/10/2025 |  | PO4411-MARSR-20251027 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 87
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | The Greenway - INV0001518 | 0 | 6190 | -6190 | 31/10/2025 |  | PO4410-MARSR-20251027 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Greenway Solar: INV0001425 | 79416.18 | 86674.86 | -7258.68 | 29/01/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 96
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Greenway Solar: INV0001425 | 39708.09 | 43337.43 | -3629.34 | 05/02/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 97
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Greenway Solar: INV0001425 | 39708.09 | 43337.43 | -3629.34 | 05/03/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 98
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | JerryG & Sons: INV16 | 0 | 65710 | -65710 | 06/11/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 109
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Matriarch - INV-5370 | 34709.44 | 8000 | 26709.44 | 28/11/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 130
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Matriarch - INV-5369 | 302799.94 | 111329.69 | 191470.25 | 30/11/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 137
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 151
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | The Greenway - INV0001517 | 0 | 56737.5 | -56737.5 | 06/11/2025 |  | PO4434-MARSR-20251031 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 164
Oct-25 | 31/10/2025 | Marikana Shoprite | Realised | The Greenway - INV0001517 | 0 | 56737.5 | -56737.5 | 19/03/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 165
Oct-25 | 31/10/2025 | Meraki Ph3 | Realised | Expense Claims | 0 | 1947.77 | -1947.77 | 06/11/2025 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 117
Oct-25 | 31/10/2025 | Meraki Ph3 | Realised | Thula Moya - IN04942 | 0 | 30339 | -30339 | 13/11/2025 |  | PO2918-MER-20251024 - RV Approved | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 124
Oct-25 | 31/10/2025 | Meraki Ph3 | Realised | DSV Inv: 180152208 | 0 | 537.94 | -537.94 | 28/11/2025 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 130
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | Allocated to Cpt Storeoom | 0 | -15958.8 | 15958.8 | 31/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 10
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | Matriarch - INV-5207 | 17959.99 | 11169 | 6790.99 | 13/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 46
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | ABL Transport - 0196 | 0 | 18600 | -18600 | 24/10/2025 |  | PO4384-MLKW-20251020 - RV Approved | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 78
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | CS_MWS_004 | 74347.06 | 92450 | -18102.94 | 30/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | CS_MWS_003 | 92933.82 | 115562.5 | -22628.68 | 09/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 90
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | CS_MWS_005 | 37173.53 | 46225 | -9051.47 | 30/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 91
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | CS_MWS_006 | 37173.53 | 46225 | -9051.47 | 30/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 92
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | CS_MWS_007 | 18586.76 | 23112.5 | -4525.74 | 19/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 93
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | Matriarch - INV-5370 | 45801.38 | 6000 | 39801.38 | 30/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 118
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | Matriarch - INV-5369 | 157727.8 | 39216.49 | 118511.31 | 30/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 124
Oct-25 | 31/10/2025 | Milkwood_Square | Realised | Expense Claim | 0 | 0 | 0 | 30/10/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 137
Oct-25 | 31/10/2025 | Newlands Terraces | Realised | Menlo INV0003289 | 0 | 8998.34 | -8998.34 | 04/12/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 52
Oct-25 | 31/10/2025 | Newlands Terraces | Realised | Expense Claim | 678.36 | 265.06 | 413.3 | 06/11/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 143
Oct-25 | 31/10/2025 | Northpoint | Realised | Expense Claim | 0 | 218.96 | -218.96 | 06/11/2025 |  |  | Northpoint_Tracker.xlsx | Expenditure Breakdown | 149
Oct-25 | 31/10/2025 | Pimville | Realised | Expense Claim | 612.52 | 113.76 | 498.76 | 06/11/2025 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 154
Oct-25 | 31/10/2025 | Pimville | Realised | Thula Moya - IN04930 | 0 | 6926 | -6926 | 19/11/2025 |  | PO4389-DPS-20251021 - RV Approved | Pimville_Tracker.xlsx | Expenditure Breakdown | 169
Oct-25 | 31/10/2025 | Pretoria North | Realised | Schletter - CRN0278 | 0 | -40497.6 | 40497.6 | 31/10/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 24
Oct-25 | 31/10/2025 | Pretoria North | Realised | Schletter - INV2301 | 0 | 83015.5 | -83015.5 | 28/11/2025 |  | PO4369-DIP-Ph2-Shoprite-20251015 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 26
Oct-25 | 31/10/2025 | Pretoria North | Realised | Schletter - INV2356 | 0 | 22912.4 | -22912.4 | 28/11/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 27
Oct-25 | 31/10/2025 | Pretoria North | Realised | CS_PTN_006 B | 48464.71 | 21054.3 | 27410.4 | 24/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 99
Oct-25 | 31/10/2025 | Pretoria North | Realised | CS_PTN_006 B | 0 | 29845.7 | -29845.7 | 24/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 100
Oct-25 | 31/10/2025 | Pretoria North | Realised | CS_PTN_007 B | 24232.35 | 25450 | -1217.65 | 18/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 101
Oct-25 | 31/10/2025 | Pretoria North | Realised | CS_PTN_008 B | 24232.35 | 25450 | -1217.65 | 05/02/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 102
Oct-25 | 31/10/2025 | Pretoria North | Realised | CS_PTN_006 B | 0 | -0.01 | 0.01 | 05/02/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 103
Oct-25 | 31/10/2025 | Pretoria North | Realised | GSG Tactical - INV000013973 | 0 | 27900 | -27900 | 06/11/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 113
Oct-25 | 31/10/2025 | Pretoria North | Realised | Expense Claim | 1080.81 | 3791.54 | -2710.73 | 06/11/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 152
Oct-25 | 31/10/2025 | Protea Point | Unrealised |  | 25623.25 | 23317.16 | 2306.09 | 12/10/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 39
Oct-25 | 31/10/2025 | Protea Point | Unrealised |  | 65799.69 | 41914.4 | 23885.29 | 12/10/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 61
Oct-25 | 31/10/2025 | Protea Point | Unrealised |  | 47793.53 | 40624.5 | 7169.03 | 12/10/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 93
Oct-25 | 31/10/2025 | Protea Point | Unrealised |  | 5301.27 | 4506.08 | 795.19 | 12/10/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 109
Oct-25 | 31/10/2025 | Protea Point | Committed | Expense Claim | 2141.18 | 1820 | 321.18 | 31/10/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 137
Oct-25 | 31/10/2025 | Randfontein | Realised | Expense Claim | 176.55 | 125.19 | 51.36 | 06/11/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 150
Oct-25 | 31/10/2025 | Red Rocket | Realised | Herholdts -INV1165658 | 0 | 68050 | -68050 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 16
Oct-25 | 31/10/2025 | Red Rocket | Realised | Solarworld - Inv SASIV-25-00568 | -0.02 | 650 | -650.02 | 13/11/2025 |  | PO4360-RR-20251009 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 29
Oct-25 | 31/10/2025 | Red Rocket | Realised | Uber Deilvery | 0 | 205 | -205 | 10/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 30
Oct-25 | 31/10/2025 | Red Rocket | Realised | Allocated to Stock | 0 | -81000 | 81000 | 31/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 34
Oct-25 | 31/10/2025 | Red Rocket | Realised | Allocated to Stock | 0 | -94500 | 94500 | 31/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 35
Oct-25 | 31/10/2025 | Red Rocket | Realised | Matriarch - INV-5207 | 3098.85 | 11169 | -8070.15 | 13/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 55
Oct-25 | 31/10/2025 | Red Rocket | Realised | DSV Inv: 180150385 | 34.86 | 206.91 | -172.05 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 56
Oct-25 | 31/10/2025 | Red Rocket | Realised | IBC Solar - ZA42502457 | 7888.29 | 28431.28 | -20542.99 | 17/10/2025 |  | RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 71
Oct-25 | 31/10/2025 | Red Rocket | Realised | WM Cabling - INV0001211 | 6376.5 | 52911.24 | -46534.74 | 31/10/2025 |  | PO4359-RR-20251007 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 73
Oct-25 | 31/10/2025 | Red Rocket | Realised | WM Cabling - INV0001211 | 7829.48 | 28219.32 | -20389.84 | 09/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 74
Oct-25 | 31/10/2025 | Red Rocket | Realised | Accuenergy: ASAI-006611 | 490.39 | 1767.5 | -1277.11 | 30/11/2025 |  | PO4360-RR-20251014 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 76
Oct-25 | 31/10/2025 | Red Rocket | Realised | Frontline INV746387 | 624.4 | 2250.5 | -1626.1 | 31/10/2025 |  | PO4367-RR-20251014 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 78
Oct-25 | 31/10/2025 | Red Rocket | Realised | Menlo Inv: INV0003305 + INV0003343 | 0 | 13151 | -13151 | 18/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 87
Oct-25 | 31/10/2025 | Red Rocket | Realised | Switchboard - 2-SOI002560 | 0 | 20597.8 | -20597.8 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 117
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 189849.53 | 225204.45 | -35354.92 | 16/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 142
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 78336.67 | 90081.78 | -11745.11 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 143
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 78336.67 | 90081.78 | -11745.11 | 05/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 144
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 39168.34 | 45040.89 | -5872.55 | 05/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 145
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 39168.34 | 45040.89 | -5872.55 | 24/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 146
Oct-25 | 31/10/2025 | Red Rocket | Realised | Container World -C595541 | 0 | 600 | -600 | 13/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 162
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 2253.85 | 51886.2 | -49632.35 | 16/10/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 169
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 901.54 | 20754.48 | -19852.94 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 170
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 901.54 | 20754.48 | -19852.94 | 05/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 171
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 450.77 | 10377.24 | -9926.47 | 05/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 172
Oct-25 | 31/10/2025 | Red Rocket | Realised | JA Electrical Inv 1083 | 450.77 | 10377.24 | -9926.47 | 24/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 173
Oct-25 | 31/10/2025 | Red Rocket | Realised | Matriarch - INV-5370 | 15546.22 | 8000 | 7546.22 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 181
Oct-25 | 31/10/2025 | Red Rocket | Realised | Expense Claim | 309.83 | 2775.54 | -2465.71 | 06/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 198
Oct-25 | 31/10/2025 | Red Rocket | Realised | DSV Inv: 180153158 | 0 | 801.11 | -801.11 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 209
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003320 | 1729623.93 | 1493349 | 236274.93 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003319 | 1343190.23 | 1159704 | 183486.23 | 18/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 7
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003320 | 827956.99 | 757573.94 | 70383.05 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 13
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Krannich - 15-10014095 | 142264.22 | 40621.45 | 101642.77 | 12/12/2025 |  | PO4364-DSHC-20251009 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 21
Oct-25 | 31/10/2025 | Seshego Circle | Realised | krannich - 15-10014122 | 160326.79 | 45778.95 | 114547.84 | 18/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 22
Oct-25 | 31/10/2025 | Seshego Circle | Realised | krannich - 15-10014093 | 178370.97 | 50931.2 | 127439.77 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 23
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Krannich - 15-10014094 | 708089.86 | 202184.62 | 505905.24 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 24
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003320 | 318265 | 189000 | 129265 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 31
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003320 | 597630.94 | 354900 | 242730.94 | 18/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 32
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1104 | 28570.63 | 16966.52 | 11604.11 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 35
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1105 | 42855.95 | 25449.78 | 17406.17 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 36
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Menlo - INV0003320 | 5015.46 | 8598.34 | -3582.88 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 51
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Accuenergy Inv :ASAI-006727 | 9478.94 | 27301 | -17822.06 | 28/11/2025 |  | PO4416-DSHC-20251028 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 52
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Allocated to Corporate Park | 0 | -44000 | 44000 | 31/10/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 57
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1104 | 64141.15 | 23150.88 | 40990.27 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 74
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1105 | 96211.73 | 34726.32 | 61485.41 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 75
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Van Staden Three : Inv 3021 | 200089.19 | 174717 | 25372.19 | 16/10/2025 |  | PO4365-DSHC-20251013 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 102
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Van Staden Three : Inv 3037 | 66696.4 | 58239 | 8457.4 | 18/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 103
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1104 | 120469.6 | 110529.12 | 9940.48 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 110
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1105 | 180704.4 | 165793.68 | 14910.72 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 111
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Cycad Security - INV0002672 | 12469.74 | 18000 | -5530.26 | 16/10/2025 |  | PO4363-DSHC-20251009 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 127
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Cycad Security - INV0002672 | 12469.74 | 18000 | -5530.26 | 31/10/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 128
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1104 | 13615.85 | 19654.4 | -6038.55 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 134
Oct-25 | 31/10/2025 | Seshego Circle | Realised | JA Electrical - Inv 1105 | 20423.78 | 29481.6 | -9057.82 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 135
Oct-25 | 31/10/2025 | Seshego Circle | Realised | Expense Claim | 3732.11 | 10587.7 | -6855.59 | 06/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 167
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1110 | 8718.12 | 4267.34 | 4450.78 | 06/11/2025 |  | PO4381-RRB-20251017 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 33
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | Accuenergy Inv: ASAI-006653 | 26936.92 | 25321 | 1615.92 | 07/01/2026 |  | PO4374-RRB-20251015 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 47
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | Matriarch - INV-5366 | 23763.55 | 22338 | 1425.55 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 48
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | DSV Inv: 180153158 | 365.24 | 343.33 | 21.91 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 49
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | Red Pole - SO-35912 | 1037.22 | 975 | 62.22 | 09/10/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 50
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1110 | 11394.76 | 4116.49 | 7278.27 | 06/11/2025 |  | PO4381-RRB-20251017 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 62
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1110 | 21883.4 | 31114.83 | -9231.42 | 06/11/2025 |  | PO4381-RRB-20251017 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 95
Oct-25 | 31/10/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1110 | 6317.1 | 10270.08 | -3952.98 | 06/11/2025 |  | PO4381-RRB-20251017 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 112
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Krannich Inv 15-10014211 | 695754.36 | 462685 | 233069.36 | 18/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 6
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Krannich Inv 15-10014211 | 14754.11 | 9811.66 | 4942.45 | 18/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 8
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Krannich Inv 15-10014211 | 175000 | 130492 | 44508 | 18/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 14
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Allocated from Cpt Storeroom | 75830.45 | 27000 | 48830.45 | 31/10/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 30
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Allocated from Cpt Storeroom | 75830.45 | 27000 | 48830.45 | 31/10/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 31
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1109 | 9426.85 | 3356.5 | 6070.35 | 06/11/2025 |  | PO4380-SMCD-20251017 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 34
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Accuenergy Inv: ASAI-006652 | 26936.92 | 25321 | 1615.92 | 28/11/2025 |  | PO4373-SMCD-20251015 - RV approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 49
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Matriarch - INV-5366 | 23763.55 | 22338 | 1425.55 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 50
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | DSV Inv: 180153158 | 365.24 | 343.33 | 21.91 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 51
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Red Pole - SO-35912 | 1037.22 | 975 | 62.22 | 09/10/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 52
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1109 | 14044.92 | 6438.55 | 7606.37 | 06/11/2025 |  | PO4380-SMCD-20251017 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 64
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Barrier Projects INV508 | 26737.33 | 11060 | 15677.33 | 24/10/2025 |  | PO4360-SMCD-20251007 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Barrier Projects INV508 | 11458.86 | 4740 | 6718.86 | 04/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1109 | 22094.44 | 27201.3 | -5106.85 | 06/11/2025 |  | PO4380-SMCD-20251017 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 98
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1109 | 6317.16 | 7485.95 | -1168.79 | 06/11/2025 |  | PO4380-SMCD-20251017 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 116
Oct-25 | 31/10/2025 | Shoprite Mini_Citrusdal | Realised | Expense Claim | 0 | 0 | 0 | 31/10/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 146
Oct-25 | 31/10/2025 | Sibasa | Realised | Cosmic Sun - CS_SRS_009 | 0 | 224160 | -224160 | 24/10/2025 |  | PO4376-DSS-20251017 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 86
Oct-25 | 31/10/2025 | Sibasa | Realised | Expense Claim | 0 | 1247.83 | -1247.83 | 07/11/2025 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 151
Oct-25 | 31/10/2025 | STD GQ | Realised | Schletter - INV2313 | 419817.36 | 307922.87 | 111894.49 | 28/11/2025 |  | PO4368-STD-20251014 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 21
Oct-25 | 31/10/2025 | STD GQ | Realised | Schletter - INV2317 | 29997.47 | 22002.2 | 7995.27 | 28/11/2025 |  | PO4405-STD-20251024 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 24
Oct-25 | 31/10/2025 | STD GQ | Realised | Schletter - INV2333 | 26551.92 | 19475 | 7076.92 | 28/11/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 25
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0673 | 6308.57 | 4239.98 | 2068.59 | 24/10/2025 |  | PO4351-STD-20251009 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 35
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0674 | 9462.86 | 6359.97 | 3102.89 | 24/10/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 36
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0673 | 2571.43 | 1728.25 | 843.18 | 24/10/2025 |  | PO4351-STD-20251009 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 63
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0674 | 3857.14 | 2592.38 | 1264.77 | 24/10/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 64
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0673 | 55120.78 | 46374.76 | 8746.02 | 24/10/2025 |  | PO4351-STD-20251009 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 96
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0674 | 82681.17 | 69562.14 | 13119.03 | 24/10/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 97
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0673 | 7306.25 | 2857.01 | 4449.23 | 24/10/2025 |  | PO4351-STD-20251009 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 113
Oct-25 | 31/10/2025 | STD GQ | Realised | Luken Solar INV-0674 | 10959.37 | 4285.52 | 6673.85 | 24/10/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 114
Oct-25 | 31/10/2025 | STD GQ | Realised | Expense Claim | 52.58 | 23.8 | 28.78 | 06/11/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 142
Oct-25 | 31/10/2025 | The Studios | Realised | Allocated to Malverne Engineering | 0 | -2704.87 | 2704.87 | 31/10/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 22
Oct-25 | 31/10/2025 | The Studios | Realised | Expense Claim | 891.17 | 0 | 891.17 | 31/10/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 140
Oct-25 | 31/10/2025 | Tsakana Corner | Realised | Cosmic Sun - CS_TSK_010 | 0 | 115500 | -115500 | 09/10/2025 |  | PO4357-DTC-20251006 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Tsakana Corner | Realised | Expense Claim | 647.88 | 631.18 | 16.7 | 06/11/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 153
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | DSV Inv: 180150385 | 0 | 304.8 | -304.8 | 30/11/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 52
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Justin & Joann Construction | 0 | 4430 | -4430 | 16/10/2025 |  | PO4320-UMZ-20250918 - RV Approved | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 83
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Thula Moya - IN04932 | 0 | 2050 | -2050 | 31/10/2025 |  | PO4388-UMZ-20251021 - RV Approved | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 89
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | The Engineering Hub Inv: INV/2025/10/0526 | 0 | 16439 | -16439 | 28/11/2025 |  | PO4408-UMZ-20251027 - RV Approved | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 90
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Thula Moya IN04939 | 79717.65 | 107921.3 | -28203.65 | 12/12/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 99
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Thula Moya IN04940 | 39858.82 | 53960.65 | -14101.83 | 19/03/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 100
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Thula Moya IN04945 | 39858.82 | 53960.65 | -14101.83 | 19/03/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 101
Oct-25 | 31/10/2025 | Umzimkhulu | Realised | Expense Claim | 2337.22 | 0 | 2337.22 | 30/10/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 151
Oct-25 | 31/10/2025 | Upper_East_Side_Hotel | Realised | INV000336 | 0 | 60101.68 | -60101.68 | 24/10/2025 |  | PO4378-UESH-20251017 - RV Approved | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 87
Oct-25 | 31/10/2025 | Upper_East_Side_Hotel | Realised | INV000336 | 0 | 60101.68 | -60101.68 | 07/11/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 88
Oct-25 | 31/10/2025 | Upper_East_Side_Hotel | Realised | City of Cape Town - 708360339 | 66714.99 | 35409.13 | 31305.86 | 24/10/2025 |  | PO4381-UESH-20251020 - RV Approved | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 127
Oct-25 | 31/10/2025 | Upper_East_Side_Hotel | Realised | Expense Claim | 295.24 | 95.2 | 200.04 | 06/11/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 147
Oct-25 | 31/10/2025 | Waterside | Realised | Schletter - INV2374 | 0 | 5329.25 | -5329.25 | 28/11/2025 |  | PO4427-WATER-20251030 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 23
Oct-25 | 31/10/2025 | Waterside | Realised | Matthews Group - INV1548 | 6935.86 | 6298.5 | 637.36 | 24/10/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 33
Oct-25 | 31/10/2025 | Waterside | Realised | Matriarch INV-5207 | 15248.01 | 11169 | 4079.01 | 13/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 46
Oct-25 | 31/10/2025 | Waterside | Realised | Matthews Group - INV1548 | 7793.58 | 3875.4 | 3918.18 | 24/10/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 59
Oct-25 | 31/10/2025 | Waterside | Realised | Accend Rope Access - INV-4926 | 2085.22 | 23172.98 | -21087.76 | 24/10/2025 |  | PO4278-WSD-20250826 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 83
Oct-25 | 31/10/2025 | Waterside | Realised | Accend Rope Access - INV-4926 | 2085.22 | 23172.98 | -21087.76 | 29/01/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 84
Oct-25 | 31/10/2025 | Waterside | Realised | Matthews Group - INV1548 | 8047.06 | 13309.8 | -5262.74 | 24/10/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 91
Oct-25 | 31/10/2025 | Waterside | Realised | Matthews Group - INV1548 | 6619.15 | 5335.2 | 1283.95 | 24/10/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 107
Oct-25 | 31/10/2025 | Waterside | Realised | Expense Claim | 202.27 | 435.52 | -233.25 | 06/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 136
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0172 | 40176.49 | 29590.98 | 10585.51 | 08/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 34
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Switchboard - 2-SOI002605 | 320138.65 | 130831.95 | 189306.7 | 30/12/2025 |  | PO4329-BOLT-20250925 - MI Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 54
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0172 | 57204.85 | 23378.07 | 33826.79 | 08/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 61
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0169 | 0 | 29500 | -29500 | 19/11/2025 |  | PO4465-BOLT-20251111 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 87
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Onvlee Engineering PO4662-Bolt-20251111 | 0 | 71592.3 | -71592.3 | 13/11/2025 |  | PO4462-BOLT-20251111 - RV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 88
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0172 | 64666.67 | 64250 | 416.67 | 08/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 95
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0172 | 17098.99 | 18479.14 | -1380.15 | 08/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 111
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | New roof, not required | 0 | 0 | 0 | 30/11/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 122
Nov-25 | 30/11/2025 | 1 Bolt Ave | Realised | Expense Claims | 234.91 | 37 | 197.91 | 05/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 139
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Menlo INV0003423 | 0 | 7009.2 | -7009.2 | 15/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 7
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Menlo INV0003423 | 0 | 700 | -700 | 15/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 8
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Menlo INV003399 | 0 | 246400 | -246400 | 09/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 31
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Allocated from Cpt Storeroom | 0 | 27000 | -27000 | 30/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 32
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Allocated from Cpt Storeroom | 0 | 40500 | -40500 | 30/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 33
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Cosmic Sun - CS_BHP_008 | 0 | 10830 | -10830 | 19/11/2025 |  | PO4474-SBP-20251117 - RV Approved | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 88
Nov-25 | 30/11/2025 | Blackheath Park | Realised | CS_BHP_002 | 141404.44 | 168000 | -26595.56 | 19/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 97
Nov-25 | 30/11/2025 | Blackheath Park | Realised | CS_BHP_003 | 162615.11 | 193200 | -30584.89 | 19/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 98
Nov-25 | 30/11/2025 | Blackheath Park | Realised | CS_BHP_003 | 14140.44 | 16800 | -2659.56 | 19/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 99
Nov-25 | 30/11/2025 | Blackheath Park | Realised | CS_BHP_004 | 70702.22 | 84000 | -13297.78 | 28/11/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 100
Nov-25 | 30/11/2025 | Blackheath Park | Realised | CS_BHP_005 | 70702.22 | 84000 | -13297.78 | 26/02/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 101
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Container World - C599042 | 1589.87 | 620 | 969.87 | 04/12/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 120
Nov-25 | 30/11/2025 | Blackheath Park | Realised | HappySolar - INV-0343 | 26993.62 | 8100 | 18893.62 | 18/12/2025 |  | PO4477-SBP-20251118 - RV Approved | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 141
Nov-25 | 30/11/2025 | Blackheath Park | Realised | Expense Claim | 3667.57 | 723.52 | 2944.05 | 05/12/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 159
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Schletter - INV2416 | 0 | 4800 | -4800 | 30/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 26
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Allocated from Kroonstad | 0 | 8598.35 | -8598.35 | 30/11/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 62
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Accuenergy - ASAI-006969 | 0 | 4110 | -4110 | 07/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 64
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Accuenergy - ASAI-006969 | 0 | 2970 | -2970 | 07/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 65
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | CS_BMG_006_VO | 0 | 16085.98 | -16085.98 | 04/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 85
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Volkirk Properties - INV0001309 | 0 | 18931 | -18931 | 28/11/2025 |  | PO4479-BMGFT-20251119 - RV Approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 109
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Cosmic Sun - CS_BMG_003F | 31401.11 | 44064 | -12662.89 | 12/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 121
Nov-25 | 30/11/2025 | BMG Fluid Tech | Realised | Expense Claim | 170.15 | 410.79 | -240.64 | 05/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 171
Nov-25 | 30/11/2025 | Bochum Plaza | Realised | Cosmic Sun - CS_BPZ_010 | 0 | 11250 | -11250 | 19/11/2025 |  | PO4394-DBP-20251023 - RV Approved | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 80
Nov-25 | 30/11/2025 | Boundary Terraces | Realised | Solarworld SASIV-25-00684 | 0 | 3250 | -3250 | 09/01/2026 |  | PO4471-SBT-20251114 - RV Approved | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 24
Nov-25 | 30/11/2025 | Boundary Terraces | Realised | Switchboard 2-SOI002578 | 0 | 10499.85 | -10499.85 | 30/12/2025 |  | PO4445-SBT-20251105 - RV Approved | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 57
Nov-25 | 30/11/2025 | Cascades | Realised | Scrapped MS | 0 | -3017.39 | 3017.39 | 24/11/2025 |  |  | Cascades_Tracker.xlsx | Expenditure Breakdown | 29
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | MSA Energy: CRN0000262 | 0 | -43292.88 | 43292.88 | 29/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 19
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Advanced Strut INV56863 | 0 | 51044 | -51044 | 07/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 140
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 1549556.86 | 862215.35 | 687341.51 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 159
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 3615632.68 | 2011835.81 | 1603796.87 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 160
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 133635.85 | 74358.6 | 59277.25 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 161
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 311816.98 | 173503.4 | 138313.58 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 162
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 1252691.2 | 695317.04 | 557374.16 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 164
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 2915757.67 | 1622406.43 | 1293351.24 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 165
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 103833.42 | 57775.72 | 46057.7 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 166
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 242277.98 | 134810.02 | 107467.96 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 167
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 130642.51 | 72693.02 | 57949.48 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 169
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 304832.52 | 169617.06 | 135215.46 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 170
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 49281.15 | 27421.37 | 21859.79 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 172
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 114989.35 | 63983.19 | 51006.17 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 173
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea S19625 | 286664.29 | 159507.77 | 127156.53 | 12/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 175
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Kathea 500247 | 608953.24 | 338838.05 | 270115.19 | 27/11/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 176
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Omega - OM040496 | 0 | 41010 | -41010 | 15/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 266
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Container World - P601672 | 1770.44 | 1550 | 220.44 | 04/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 299
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Container World - P601674 | 1770.44 | 1550 | 220.44 | 04/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 300
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Container World P601684 | 988.11 | 2635 | -1646.89 | 04/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 301
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Talisman Hire - 00216276 | 1343.36 | 2434.8 | -1091.44 | 04/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 319
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | 2Xtwo - 785 | 21812.5 | 28400 | -6587.5 | 04/12/2025 |  | PO4400-CSPH2-20251030 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 331
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Matriarch - INV-5464 | 3155.14 | 2843 | 312.14 | 30/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 362
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 15266.94 | -15266.94 | 05/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 377
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation - INV77241 | 0 | 14381.9 | -14381.9 | 18/12/2025 |  | PO4446-CSPH2-20251106 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 402
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Coega Development Corporation - INV77755 | 0 | 9126.98 | -9126.98 | 04/12/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 403
Nov-25 | 30/11/2025 | Coega Steels Ph2 | Realised | Alpha Omega Inv 102784 | 0 | 160210.05 | -160210.05 | 12/12/2025 |  | PO4417-CSPH2-20251028 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 412
Nov-25 | 30/11/2025 | Corporate Park | Realised | Van Staden Three - Inv3075 | 188952.72 | 26550 | 162402.72 | 28/11/2025 |  | PO4483-DCP-20251124 - RV Approved | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 91
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | MSA Energy INV0003444 | 0 | 4935.2 | -4935.2 | 23/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 8
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | MSA Energy INV0003444 | 0 | 600 | -600 | 23/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04964 | 22939.26 | 21394.97 | 1544.28 | 29/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 38
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04965 | 11469.63 | 10697.49 | 772.14 | 05/02/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 39
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04964 | 20499.06 | 10682.33 | 9816.73 | 29/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 66
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04965 | 10249.53 | 5341.16 | 4908.37 | 05/02/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 67
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04852 | 37707.35 | 55856.64 | -18149.29 | 18/12/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 98
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04964 | 37707.35 | 55856.64 | -18149.29 | 29/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 99
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04965 | 18853.68 | 27928.32 | -9074.64 | 05/02/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 100
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | JerryG & Sons INV21 | 0 | 25500 | -25500 | 28/11/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 114
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04964 | 2443.3 | 5750.06 | -3306.76 | 29/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 122
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Thula Moya IN04965 | 1230.39 | 2875.03 | -1644.64 | 05/02/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 123
Nov-25 | 30/11/2025 | Dobsonpoint | Realised | Expense Claim | 676.88 | 59.5 | 617.38 | 05/12/2025 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 154
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | MSA Energy Solutions INV0003443 | 0 | 6169 | -6169 | 23/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | MSA Energy Solutions INV0003443 | 0 | 800 | -800 | 23/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Schletter - INV2459 | 0 | 6506 | -6506 | 30/12/2025 |  | PO4484-DIP-Ph2-Gezi-20251124 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 22
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_011_VO | 0 | 6000 | -6000 | 19/11/2025 |  | PO4393-DIP-Ph2-Gezi-20251023 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 80
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | NDAWONGA TRADING - 1485 | 0 | 16488 | -16488 | 12/12/2025 |  | PO4339-DIP-Ph2-Gezi-20250929 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 86
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_003_B | 227036.76 | 238500 | -11463.24 | 18/12/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 95
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_005_B | 90814.71 | 95400 | -4585.29 | 29/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 96
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_006_B | 90814.71 | 95400 | -4585.29 | 05/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 97
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_003_B | 11245.37 | 17363.75 | -6118.38 | 18/12/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 116
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_005_B | 4498.15 | 6945.5 | -2447.35 | 29/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 117
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_006_B | 4498.15 | 6945.5 | -2447.35 | 05/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 118
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Expense Claim | 1572.17 | 1827.75 | -255.58 | 05/12/2025 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 150
Nov-25 | 30/11/2025 | Gezina Galleries | Realised | Ecom Electrical | 0 | 4950 | -4950 | 28/11/2025 |  | PO4500-DIP-Ph2-Gezi-20251127 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 164
Nov-25 | 30/11/2025 | Gillwell | Realised | Cosmic Sun - CS_GWM_010 | 0 | 12500 | -12500 | 27/11/2025 |  | PO4395-GILL-20251023 - RV Approved | Gillwell_Tracker.xlsx | Expenditure Breakdown | 86
Nov-25 | 30/11/2025 | Gillwell | Realised | Expense Claim | 3092.71 | 0 | 3092.71 | 30/11/2025 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 149
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Allocated to Cpt Storeroom | 0 | -13542 | 13542 | 30/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Krannich 17-01001217 | 0 | 5436.12 | -5436.12 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Schletter INV2383 | 58665.53 | 27460 | 31205.53 | 30/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 22
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Schletter INV2383 | 13856.69 | 6486 | 7370.69 | 30/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 23
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1118 | 8307.42 | 4460.79 | 3846.63 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 35
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 5529.81 | 2973.86 | 2555.95 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 36
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 11059.61 | 5947.72 | 5111.89 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 38
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1130 | 2764.9 | 1486.93 | 1277.97 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 39
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1137 | 5529.81 | 2973.86 | 2555.95 | 29/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 40
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1138 | 5529.81 | 2973.86 | 2555.95 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 41
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1139 | 2764.9 | 1486.93 | 1277.97 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 42
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1140 | 2746.29 | 1476.92 | 1269.37 | 05/03/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 43
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Menlo INV0003384 | 10016 | 8598.34 | 1417.66 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 48
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Menlo INV0003384 | 119.44 | 100 | 19.44 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 49
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Uber | 25.48 | 21.33 | 4.15 | 12/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 54
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Uber | 48.97 | 41 | 7.97 | 29/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 55
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Switchboard 2-SOI002609 | 136435.66 | 60403.57 | 76032.09 | 30/12/2025 |  | PO4327-HLCD-20250925 - MI Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 60
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1118 | 11561.09 | 5118.39 | 6442.7 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 66
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 7707.39 | 3412.26 | 4295.13 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 67
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 15414.78 | 6824.52 | 8590.26 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 69
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1130 | 3853.7 | 1706.13 | 2147.57 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 70
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1137 | 7707.39 | 3412.26 | 4295.13 | 29/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 71
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1138 | 7707.39 | 3412.26 | 4295.13 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 72
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1139 | 3853.7 | 1706.13 | 2147.57 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 73
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1140 | 3853.7 | 1706.13 | 2147.57 | 05/03/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 74
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Barrier Projects Credit : 507 | 0 | -16450 | 16450 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 91
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Barrier Projects : 507 | 0 | 24900 | -24900 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 92
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1118 | 17306.09 | 27897.93 | -10591.84 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 100
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 11535.31 | 18598.6 | -7063.29 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 101
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 23070.65 | 37197.24 | -14126.59 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 103
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1130 | 5767.66 | 9299.31 | -3531.65 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 104
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1137 | 11522.92 | 18578.62 | -7055.7 | 29/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 105
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1138 | 11522.92 | 18578.62 | -7055.7 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 106
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1139 | 5761.45 | 9289.3 | -3527.85 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 107
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1140 | 5767.66 | 9299.31 | -3531.65 | 05/03/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 108
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | HP Security Inv 3951 | 894.68 | 1533.06 | -638.38 | 28/11/2025 |  | PO4486-HLCD-20251124 - RV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 113
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1118 | 5868.64 | 10056.07 | -4187.43 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 118
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 3912.43 | 6704.05 | -2791.62 | 04/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 119
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1125 | 7824.86 | 13408.1 | -5583.24 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 121
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1130 | 1956.21 | 3352.03 | -1395.81 | 09/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 122
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1137 | 3912.43 | 6704.05 | -2791.62 | 29/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 123
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1138 | 3912.43 | 6704.05 | -2791.62 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 124
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1139 | 1956.21 | 3352.03 | -1395.81 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 125
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1140 | 1956.21 | 3352.03 | -1395.81 | 05/03/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 126
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | Expense Claim | 1960.17 | 863.34 | 1096.83 | 05/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 148
Nov-25 | 30/11/2025 | Hungry Lion_Citrusdal | Realised | ABL Transport - 0217 | 0 | 3650 | -3650 | 28/11/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 162
Nov-25 | 30/11/2025 | IconsSA_KZN | Realised | Accuenergy - ASAI-006874 | 0 | 350 | -350 | 07/01/2026 |  | PO4472-IKZN-20251114 - RV Approved | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 51
Nov-25 | 30/11/2025 | IconsSA_KZN | Realised | Expense Claim | 1361 | 3159.05 | -1798.05 | 05/12/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 138
Nov-25 | 30/11/2025 | IconsSA_KZN | Realised | DSV Inv: 180154233 | 0 | 298.24 | -298.24 | 31/12/2025 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 148
Nov-25 | 30/11/2025 | Kroonstad | Realised | Allocated to BMG Fluid Tech | 0 | -8598.35 | 8598.35 | 30/11/2025 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 49
Nov-25 | 30/11/2025 | Kroonstad | Realised | Cosmic Sun - CS_KRN_010 | 0 | 6000 | -6000 | 19/11/2025 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 165
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Accuenergy Inv:ASAI-006830 | 25155.73 | 14118 | 11037.73 | 07/01/2026 |  | PO4458-MBE-2025111 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 47
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | DSV Inv: 180156930 | 475.08 | 307.94 | 167.14 | 30/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 49
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | IBC Solar - ZA12502620 | 109519.52 | 70989.17 | 38530.35 | 18/11/2025 |  | PO4451-MBE-20251107 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 50
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Onvlee - Inv01051750 | 197924.52 | 213097.85 | -15173.33 | 01/12/2025 |  | PO4451-MBE-20251107 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 82
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Onvlee - PO-4505-MBE-20251128 | 201610.04 | 19795.6 | 181814.44 | 01/12/2025 |  | PO4505-MBE-20251128 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 83
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Boukon -25/11/2025 | 51113.11 | 26500 | 24613.11 | 27/11/2025 |  | PO4499-MBE-20251126 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 90
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | LPS - IN307444 | 6733.77 | 7250 | -516.23 |  |  | PO4406-MBE-20251024 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 96
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | JJL Steel & Construction INV251112 | 27740.45 | 29867.1 | -2126.64 | 13/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 104
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | JJL Steel & Construction INV251112 | 27740.45 | 29867.1 | -2126.64 | 04/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 105
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Expense Claim | 1455.28 | 10490.93 | -9035.65 | 05/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 165
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Evolution Coatings - INV0000122 | 23350 | 18680 | 4670 | 04/11/2025 |  | PO4436-MBE-20251102 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 178
Nov-25 | 30/11/2025 | Mahikeng Builders Express | Realised | Evolution Coatings - INV0000122 | 0 | 4670 | -4670 | 27/11/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 179
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | IBC Solar - ZA42502733 | 0 | 1305.4 | -1305.4 | 19/11/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | Schletter - INV2378 | 38661.55 | 15552 | 23109.55 | 30/12/2025 |  | PO4428-MVE2-20251030 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 22
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | Schletter - CRN0281 | 0 | -9092 | 9092 | 31/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 32
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1117 | 8043.32 | 5653.15 | 2390.17 | 24/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 40
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1129 | 10724.43 | 7537.54 | 3186.89 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 41
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1132 | 13405.54 | 9421.92 | 3983.61 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 42
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1133 | 5362.22 | 3768.77 | 1593.45 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 43
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1134 | 5362.22 | 3768.77 | 1593.45 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 44
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1135 | 2681.11 | 1884.38 | 796.72 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 45
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1136 | 2681.11 | 1884.38 | 796.72 | 05/03/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 46
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | DSV Inv: 180156055 | 344.44 | 188.5 | 155.94 | 30/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 54
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1117 | 34367.76 | 9711.05 | 24656.72 | 24/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 66
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1129 | 45823.68 | 12948.06 | 32875.62 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 67
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1132 | 57279.6 | 16185.08 | 41094.53 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 68
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1133 | 22911.84 | 6474.03 | 16437.81 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 69
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1134 | 22911.84 | 6474.03 | 16437.81 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 70
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1135 | 11455.92 | 3237.02 | 8218.91 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 71
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1136 | 11455.92 | 3237.02 | 8218.91 | 05/03/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 72
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JRL Engineering INV00427 | 0 | 5900 | -5900 | 30/12/2025 |  | PO4504-MVE2-20251128 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 87
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1117 | 19511.25 | 26331.61 | -6820.36 | 24/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 98
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1129 | 26015 | 35108.82 | -9093.82 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 99
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1132 | 32518.75 | 43886.02 | -11367.28 | 12/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 100
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1133 | 13007.5 | 17554.41 | -4546.91 | 18/12/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 101
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1134 | 13007.5 | 17554.41 | -4546.91 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 102
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1135 | 6503.75 | 8777.2 | -2273.46 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 103
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1136 | 6503.75 | 8777.2 | -2273.46 | 05/03/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 104
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | Gaul Solution - Inv 2318 | 1737.28 | 7140 | -5402.72 | 04/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 110
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1117 | 3868.03 | 15897.07 | -12029.05 | 24/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 114
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1129 | 5157.37 | 21196.1 | -16038.73 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 115
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1132 | 6446.71 | 26495.12 | -20048.41 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 116
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1133 | 2578.68 | 10598.05 | -8019.37 | 18/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 117
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1134 | 2578.68 | 10598.05 | -8019.37 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 118
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1135 | 1289.34 | 5299.03 | -4009.68 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 119
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | JA Electrical INV 1136 | 1289.34 | 5299.03 | -4009.68 | 05/03/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 120
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | LPS - IN307443 | 8137.12 | 5100 | 3037.12 | 07/01/2026 |  | PO4407-MVE2-20251024 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 127
Nov-25 | 30/11/2025 | Malvern Ph2 | Realised | Expense claim | 988.52 | 968.66 | 19.86 | 05/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 142
Nov-25 | 30/11/2025 | Marikana Old Church | Realised | JerryG& Sons INV19 | 0 | 39900 | -39900 | 28/11/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 109
Nov-25 | 30/11/2025 | Marikana Old Church | Realised | Expense Claim | 1496.03 | 0 | 1496.03 | 05/12/2025 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 150
Nov-25 | 30/11/2025 | Marikana Shoprite | Realised | JerryG & Sons INV20 | 0 | 63700 | -63700 | 28/11/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 110
Nov-25 | 30/11/2025 | Marikana Shoprite | Realised | Expense Claim | 4489.35 | 0 | 4489.35 | 05/12/2025 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 152
Nov-25 | 30/11/2025 | Marikana Shoprite | Unrealised |  | 311271.3 | 0 | 311271.3 |  |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 166
Nov-25 | 30/11/2025 | Meraki Ph3 | Realised | Thula Moya IN04946 | 0 | 11800 | -11800 | 18/12/2025 |  | PO4346-MER-20250930 - RV Approved | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 72
Nov-25 | 30/11/2025 | Milkwood_Square | Realised | CS_MWS_008 | 18586.76 | 23112.5 | -4525.74 | 19/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 94
Nov-25 | 30/11/2025 | Milkwood_Square | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 138
Nov-25 | 30/11/2025 | Newlands Terraces | Realised | Expense Claim | 0 | 214.2 | -214.2 | 05/12/2025 |  |  | Newlands Terraces_Tracker.xlsx | Expenditure Breakdown | 144
Nov-25 | 30/11/2025 | Nquthu | Realised | Rubicon: INVWCRE-0072122 | 0 | 40000 | -40000 | 31/12/2025 |  |  | Nquthu_Tracker.xlsx | Expenditure Breakdown | 85
Nov-25 | 30/11/2025 | Nquthu | Realised | DSV Inv: 180155155 | 0 | 255.89 | -255.89 | 31/12/2025 |  |  | Nquthu_Tracker.xlsx | Expenditure Breakdown | 86
Nov-25 | 30/11/2025 | Pimville | Realised | MSA Energy INV0003446 | 0 | 3701.4 | -3701.4 | 23/01/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 8
Nov-25 | 30/11/2025 | Pimville | Realised | MSA Energy INV0003446 | 0 | 600 | -600 | 23/01/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Pimville | Realised | Expense Claim | 76.87 | 83.78 | -6.91 | 05/12/2025 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 155
Nov-25 | 30/11/2025 | Pretoria North | Realised | Menlo - INV0003424 | 0 | 3701.4 | -3701.4 | 15/01/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 7
Nov-25 | 30/11/2025 | Pretoria North | Realised | Menlo - INV0003424 | 0 | 1000 | -1000 | 15/01/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 8
Nov-25 | 30/11/2025 | Pretoria North | Realised | DSV Inv: 180155155 & 180154233 | 0 | 616.92 | -616.92 | 31/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 25
Nov-25 | 30/11/2025 | Pretoria North | Realised | Ndawonga Trading - 1484 | 0 | 14332 | -14332 | 12/12/2025 |  | PO4340-DIP-Ph2-Shoprite-20250929 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 87
Nov-25 | 30/11/2025 | Pretoria North | Realised | Cosmic Sun - CS_PTN_009 | 0 | 6000 | -6000 | 04/12/2025 |  | PO4392-DIP-Ph2-Shoprite-20251023 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 88
Nov-25 | 30/11/2025 | Pretoria North | Realised | GSG Tactical - INV000014095 | 0 | 27900 | -27900 | 12/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 114
Nov-25 | 30/11/2025 | Pretoria North | Realised | Expense Claim | 794.96 | 2115.3 | -1320.34 | 05/12/2025 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 153
Nov-25 | 30/11/2025 | Pretoria North | Realised | Cosmic Sun - CS_PTN_010 | 0 | 7350 | -7350 | 31/10/2025 |  | PO4352-DIP-Ph2-Shoprite-20251006 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 164
Nov-25 | 30/11/2025 | Pretoria North | Realised | Ecom Electrical INV2892 | 0 | 4950 | -4950 | 28/11/2025 |  | PO4501-DIP-Ph2-Shoprite-20251127 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 165
Nov-25 | 30/11/2025 | Protea Point | Committed | Expense Claim | 2141.18 | 1820 | 321.18 | 30/11/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 138
Nov-25 | 30/11/2025 | Randfontein | Realised | MSA Energy INV0003445 | 0 | 3701.4 | -3701.4 | 23/01/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Randfontein | Realised | MSA Energy INV0003445 | 0 | 600 | -600 | 23/01/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 11
Nov-25 | 30/11/2025 | Randfontein | Realised | Thula Moya IN04963 | 0 | 245754.52 | -245754.52 | 05/02/2026 |  | PO4488-DRS-20251124 - RV Approved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 82
Nov-25 | 30/11/2025 | Randfontein | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 151
Nov-25 | 30/11/2025 | Red Rocket | Realised | Allocated to Cpt Storeroom | 0 | -18502.4 | 18502.4 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Red Rocket | Realised | Dont add as a credit | 0 | 0 | 0 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Red Rocket | Realised | DSV Inv: 180155155 | 0 | 1646.04 | -1646.04 | 30/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 18
Nov-25 | 30/11/2025 | Red Rocket | Realised | Lintels Credit Note - CR2256 | 0 | -16705.46 | 16705.46 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 23
Nov-25 | 30/11/2025 | Red Rocket | Realised | Lintels Credit Note - CR2256 | 0 | 1436.9 | -1436.9 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 24
Nov-25 | 30/11/2025 | Red Rocket | Realised | Allocated to Cpt Stockroom | 0 | -3780 | 3780 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 53
Nov-25 | 30/11/2025 | Red Rocket | Realised | LW Refrigeration - 32296 | 0 | 120223.89 | -120223.89 | 28/11/2025 |  | PO4461-RR-20251111 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 113
Nov-25 | 30/11/2025 | Red Rocket | Realised | W&F Electrical - INV08652 | 0 | 11229.25 | -11229.25 | 19/11/2025 |  | PO4460-RR-20251111 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 121
Nov-25 | 30/11/2025 | Red Rocket | Realised | Ask Fritz - 2510_015 | 0 | 7600 | -7600 | 13/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 124
Nov-25 | 30/11/2025 | Red Rocket | Realised | Emergent Inv: 0004894 | 0 | -27294.75 | 27294.75 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 127
Nov-25 | 30/11/2025 | Red Rocket | Realised | Container World -C599043 | 0 | 620 | -620 | 04/12/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 163
Nov-25 | 30/11/2025 | Red Rocket | Realised | SunSpot E030 | 33132.89 | 24500 | 8632.89 | 28/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 178
Nov-25 | 30/11/2025 | Red Rocket | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 199
Nov-25 | 30/11/2025 | Red Rocket | Realised | ABL Transport Invoice 0205 | 0 | 5500 | -5500 | 06/11/2025 |  | PO4437-GEN-20251103 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 208
Nov-25 | 30/11/2025 | Red Rocket | Realised | ABL Transport Inv 0215 | 0 | 11500 | -11500 | 13/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 210
Nov-25 | 30/11/2025 | Red Rocket | Realised | ABL Transport Inv 0220 | 0 | 2500 | -2500 | 19/11/2025 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 211
Nov-25 | 30/11/2025 | Red Rocket | Realised | Happysolar Inv: 0344 | 0 | 5450 | -5450 | 04/12/2025 |  | PO4492-20251126 - RV Apporoved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 212
Nov-25 | 30/11/2025 | Riverside Mall | Realised | L&B Invoice: | 10023.65 | 8572.5 | 1451.15 | 13/11/2025 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 123
Nov-25 | 30/11/2025 | Seshego Circle | Realised | K2 Systems - Inv139402 | 0 | 71394.92 | -71394.92 | 28/11/2025 |  | PO4490-DSHC-20251125 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 25
Nov-25 | 30/11/2025 | Seshego Circle | Realised | DSV Inv:180156930 | 0 | 335.86 | -335.86 | 31/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 55
Nov-25 | 30/11/2025 | Seshego Circle | Realised | Rubicon - INVWCRE-0072121 | 0 | 40000 | -40000 | 30/12/2025 |  | PO4420-DSHC-20251029 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 58
Nov-25 | 30/11/2025 | Seshego Circle | Realised | DSV Inv:180155155 | 0 | 285.59 | -285.59 | 30/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 59
Nov-25 | 30/11/2025 | Seshego Circle | Realised | Switchboard - 2-SOI002604 | 983356.54 | 354929.22 | 628427.32 | 30/12/2025 |  | PO4330-DSHC-20250925 - MI Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 69
Nov-25 | 30/11/2025 | Seshego Circle | Realised | Cycad Security - INV0002699 | 38348.82 | 60000 | -21651.18 | 28/11/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 129
Nov-25 | 30/11/2025 | Seshego Circle | Realised | Expense Claim | 3279.47 | 5515.35 | -2235.88 | 05/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 168
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Menlo - INV0003417 | 594339.81 | 432000 | 162339.81 | 15/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 6
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Menlo - INV0003407 | 94103.8 | 68400 | 25703.8 | 15/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 7
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | MSA Energy INV0003456 | 4324.92 | 3143.6 | 1181.32 | 23/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 8
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | MSA Energy INV0003436 | 3439.47 | 2500 | 939.47 | 23/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Menlo - INV0003407 | 175000 | 137740.7 | 37259.3 | 15/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 13
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Schletter - INV2381 | 124985.3 | 76171 | 48814.3 | 30/12/2025 |  | PO4423-RRB-20251030 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 22
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Schletter - INV2403 | 3125.47 | 1948 | 1177.47 | 30/12/2025 |  | PO4455-RRB-20251110 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 24
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Menlo - INV0003407 | 143405.59 | 81900 | 61505.59 | 15/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 29
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1120 | 17778.05 | 6401.01 | 11377.04 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 34
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 23704.07 | 8534.68 | 15169.39 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 35
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 23704.07 | 8534.68 | 15169.39 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 36
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Menlo - INV0003384 | 9080.93 | 8698.34 | 382.59 | 09/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 46
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Uber | 22.64 | 21.34 | 1.3 | 12/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 51
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Uber | 43.49 | 41 | 2.49 | 29/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 52
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Switchboard - 2-SOI002612 | 68483.98 | 24740.64 | 43743.34 | 30/12/2025 |  | PO4348-RRB-20250930 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 57
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Switchboard - 2-SOI002610 | 153282.44 | 55375.08 | 97907.36 |  |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 58
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1120 | 17092.14 | 6174.73 | 10917.4 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 63
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 22789.52 | 8232.98 | 14556.54 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 64
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 22789.52 | 8232.98 | 14556.54 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 65
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Overstaalwerke - IN100634 | 0 | 12761.85 | -12761.85 | 19/11/2025 |  | PO4476-RRB-20251118 - RV Approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 87
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Overstaalwerke - IN100634 | 0 | 5469.37 | -5469.37 | 18/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 88
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1120 | 32825.1 | 46672.24 | -13847.14 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 96
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 43766.8 | 62229.65 | -18462.85 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 97
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 43766.8 | 62229.65 | -18462.85 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 98
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1120 | 8858.9 | 15405.11 | -6546.22 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 113
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 11811.86 | 20540.15 | -8728.29 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 114
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1123 | 11811.86 | 20540.15 | -8728.29 | 28/11/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 115
Nov-25 | 30/11/2025 | Shoprite Mini_Bredarsdorp | Realised | Expense Claim | 2291.98 | 1951.6 | 340.38 | 05/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 142
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Allocated to Cpt Storeroom | 0 | -22579 | 22579 | 30/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 9
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Krannich Inv: 17010001217 | 0 | 10463.88 | -10463.88 | 18/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 10
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Schletter - INV2382 | 101943.17 | 47705 | 54238.17 | 30/12/2025 |  | PO4424-SMCD-20251030 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 22
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Schletter - INV2410 | 23106.83 | 10813 | 12293.83 | 30/12/2025 |  | PO4467-SMCD-20251111 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 23
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1119 | 14140.27 | 5034.75 | 9105.52 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 35
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 9426.85 | 3356.5 | 6070.35 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 36
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 18853.7 | 6713 | 12140.7 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 38
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Menlo - INV0003384 | 9080.94 | 8698.34 | 382.6 | 09/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 48
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Uber | 22.63 | 21.33 | 1.3 | 12/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 53
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Uber | 43.49 | 41 | 2.49 | 29/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 54
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Switchboard - 2-SOI002606 | 174533.76 | 80010.72 | 94523.04 | 29/12/2025 |  | PO4328-SMCD-20250925 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 59
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1119 | 21067.38 | 9657.82 | 11409.56 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 65
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 14044.92 | 6438.55 | 7606.37 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 66
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 28089.84 | 12877.1 | 15212.74 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 68
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Barrier Projects INV527 | 5874.48 | 2430 | 3444.48 | 13/11/2025 |  | PO4441-SMCD-20251104 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 90
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Barrier Projects INV527 | 13707.11 | 5670 | 8037.11 | 04/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 91
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1119 | 33141.67 | 40801.94 | -7660.28 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 99
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 22094.44 | 27201.3 | -5106.85 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 100
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 44188.89 | 54402.59 | -10213.7 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 102
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | HP Private Security - 3946 | 1876.5 | 2555.1 | -678.6 | 13/11/2025 |  | PO4468-SMCD-20251111 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 112
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1119 | 9162.99 | 11228.92 | -2065.93 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 117
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 6108.66 | 7485.95 | -1377.29 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 118
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1124 | 12217.32 | 14971.9 | -2754.58 | 28/11/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 120
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | Expense Claim | 2144.35 | 863.3 | 1281.05 | 05/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 147
Nov-25 | 30/11/2025 | Shoprite Mini_Citrusdal | Realised | ABL Transport Inv 0205 | 0 | 7000 | -7000 | 06/11/2025 |  | PO4437-GEN-20251103 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 160
Nov-25 | 30/11/2025 | Sibasa | Realised | Cosmic Sun - CS_SRS_010 | 0 | 12300 | -12300 | 04/12/2025 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 83
Nov-25 | 30/11/2025 | Sibasa | Realised | Bright Integrated Solutions: Inv10/25 | 0 | 29000 | -29000 | 28/11/2025 |  | PO4377-DSS-20251017 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 110
Nov-25 | 30/11/2025 | Sibasa | Realised | Expense Claim | 0 | 4630.14 | -4630.14 | 05/12/2025 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 152
Nov-25 | 30/11/2025 | STD GQ | Realised | Schletter - INV2392 | 88776.8 | 65115 | 23661.8 | 30/12/2025 |  | PO4440-STD-20251104 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 26
Nov-25 | 30/11/2025 | STD GQ | Realised | Schletter - CRN0282 | 0 | -50525 | 50525 | 30/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 27
Nov-25 | 30/11/2025 | STD GQ | Realised | Schletter - INV2449 | 0 | 5195.4 | -5195.4 | 30/12/2025 |  | PO4480-STD-20251120 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 28
Nov-25 | 30/11/2025 | STD GQ | Realised | Schletter - INV2415 | 0 | 5751.74 | -5751.74 | 30/12/2025 |  | PO4470-STD-20251113 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 29
Nov-25 | 30/11/2025 | STD GQ | Realised | Accuenergy Inv: ASAI-006805 | 16958.36 | 18378 | -1419.64 | 07/01/2026 |  | PO4449-STD-20251106 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 49
Nov-25 | 30/11/2025 | STD GQ | Realised | DSV Inv: 180156055 | 284.15 | 307.94 | -23.79 | 30/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 51
Nov-25 | 30/11/2025 | STD GQ | Realised | Current Automotion - INV346556 | 1535.55 | 1664.1 | -128.55 | 11/11/2025 |  | PO4452-STD-20251107 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 52
Nov-25 | 30/11/2025 | STD GQ | Realised | DSV Inv: 180155155 | 237.78 | 257.68 | -19.9 | 30/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 53
Nov-25 | 30/11/2025 | STD GQ | Realised | Talisman - 00216340 | 1893.39 | 1217.4 | 675.99 | 04/12/2025 |  | PO4432-STD-20251031 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 91
Nov-25 | 30/11/2025 | STD GQ | Realised | Luken INV-0683 | 29938.94 | 19250 | 10688.94 | 28/11/2025 |  | PO4503-STD-20251127 -RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 93
Nov-25 | 30/11/2025 | STD GQ | Realised | Expense Claim | 1573.15 | 142.8 | 1430.35 | 05/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 143
Nov-25 | 30/11/2025 | Superspar Ph2 | Realised | Expense Claim | 521.24 | 428.4 | 92.84 | 05/12/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 137
Nov-25 | 30/11/2025 | Superspar Ph2 | Realised | Luken Solar - Invoice 0658 | 0 | 450 | -450 | 02/10/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 150
Nov-25 | 30/11/2025 | The Studios | Realised | All in Glass Alu INV0002092 | 0 | 11188.2 | -11188.2 | 28/11/2025 |  | PO4485-STS-20251124 - RV Approved | The Studios_Tracker.xlsx | Expenditure Breakdown | 86
Nov-25 | 30/11/2025 | The Studios | Realised | All in Glass Alu INV0002092 | 0 | 7458.8 | -7458.8 | 14/12/2025 |  |  | The Studios_Tracker.xlsx | Expenditure Breakdown | 87
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | JRL Engineering INV00425 | 0 | 6341.4 | -6341.4 | 27/11/2025 |  | PO4481-DTC-20251124 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 82
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | JRL Engineering INV00425 | 0 | 14796.6 | -14796.6 | 30/12/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 83
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | JRL Engineering INV00426 | 0 | 6870 | -6870 | 27/11/2025 |  | PO4481-DTC-20251124 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 84
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | JRL Engineering INV00426 | 0 | 16030 | -16030 | 30/12/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 85
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | Cosmic Sun - CS_TSK_012 | 0 | 115500 | -115500 | 18/12/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 89
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | Cosmic Sun - CS_TSK_011 | 0 | 6000 | -6000 | 20/11/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 92
Nov-25 | 30/11/2025 | Tsakana Corner | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 154
Nov-25 | 30/11/2025 | Umzimkhulu | Realised | Expense Claim | 0 | 5134.76 | -5134.76 | 05/12/2025 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 152
Nov-25 | 30/11/2025 | Upper_East_Side_Hotel | Realised | FMS Property - INV22455 | 1993368.7 | 2292374 | -299005.3 | 18/12/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 91
Nov-25 | 30/11/2025 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 87414.12 | 95340 | -7925.88 | 18/12/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 97
Nov-25 | 30/11/2025 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 13672.11 | 30209.5 | -16537.39 | 18/12/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 114
Nov-25 | 30/11/2025 | Upper_East_Side_Hotel | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 148
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1564 | 9247.81 | 8398 | 849.81 | 04/12/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 34
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1565 | 11559.76 | 10497.5 | 1062.26 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 35
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1564 | 10391.43 | 5167.2 | 5224.23 | 04/12/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 60
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1565 | 12989.29 | 6459 | 6530.29 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 61
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1564 | 10729.41 | 17746.4 | -7016.99 | 04/12/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 92
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1565 | 13411.76 | 22183 | -8771.24 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 93
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1564 | 8825.53 | 7113.6 | 1711.93 | 04/12/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 108
Nov-25 | 30/11/2025 | Waterside | Realised | Matthews Group - INV1565 | 11031.91 | 8892 | 2139.91 | 28/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 109
Nov-25 | 30/11/2025 | Waterside | Realised | Expense Claim | 0 | 0 | 0 | 30/11/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 137
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Allocated from Cpt Storeroom | 0 | 2257 | -2257 | 31/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 9
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0176 | 40176.49 | 29590.98 | 10585.51 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 35
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0177 | 20088.25 | 14795.49 | 5292.76 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 36
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0178 | 20088.25 | 14795.49 | 5292.76 | 30/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0179 | 10044.12 | 7397.74 | 2646.38 | 05/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 38
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0180 | 10044.12 | 7397.74 | 2646.38 | 30/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 39
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Allocated from Cpt Storeroom | 0 | 1300 | -1300 | 31/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 49
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0176 | 57204.85 | 23378.07 | 33826.79 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 62
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0177 | 28602.43 | 11689.03 | 16913.39 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 63
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0178 | 28602.43 | 11689.03 | 16913.39 | 30/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 64
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0179 | 14301.21 | 5844.52 | 8456.7 | 05/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 65
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0180 | 14301.21 | 5844.52 | 8456.7 | 30/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 66
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0176 | 64666.67 | 64250 | 416.67 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 96
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0177 | 32333.33 | 32125 | 208.33 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 97
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0178 | 32333.33 | 32125 | 208.33 | 30/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 98
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0179 | 16166.67 | 16062.5 | 104.17 | 05/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 99
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0180 | 16166.67 | 16062.5 | 104.17 | 30/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 100
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0176 | 17098.99 | 18479.14 | -1380.15 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 112
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0177 | 8549.5 | 9239.57 | -690.07 | 24/12/2025 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 113
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0178 | 8549.5 | 9239.57 | -690.07 | 30/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 114
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0179 | 4274.75 | 4619.78 | -345.04 | 05/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 115
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Leading Edge - INV-0180 | 4274.75 | 4619.78 | -345.04 | 30/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 116
Dec-25 | 31/12/2025 | 1 Bolt Ave | Realised | Expense Claims | 366.32 | 57.12 | 309.2 | 08/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 140
Dec-25 | 31/12/2025 | 7th Avenue Park | Realised | L&B Consulting - Inv 2124 | 9727.19 | 8572.5 | 1154.69 | 13/11/2025 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 121
Dec-25 | 31/12/2025 | Blackheath Park | Realised | Allocated from Freeway Park | 0 | 850 | -850 | 31/12/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 54
Dec-25 | 31/12/2025 | Blackheath Park | Realised | CS_BHP_006 | 35351.11 | 42000 | -6648.89 | 12/12/2025 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 102
Dec-25 | 31/12/2025 | Blackheath Park | Realised | Container World - C602492 | 0 | 620 | -620 | 09/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 121
Dec-25 | 31/12/2025 | Blackheath Park | Realised | Sunspot - E032 | 282226.9 | 12250 | 269976.9 | 23/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 138
Dec-25 | 31/12/2025 | Blackheath Park | Realised | Expense Claim | 0 | 0 | 0 | 09/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 160
Dec-25 | 31/12/2025 | Blackheath Park | Realised | Cosmic Sun - CS_BHP_009 | 0 | 15292.07 | -15292.07 | 24/12/2025 |  | PO4530-SBP-20251209 - RV Approved | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 167
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Menlo INV0003504 | 0 | 3469.2 | -3469.2 | 05/02/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 8
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Menlo INV0003504 | 0 | 1000 | -1000 | 05/02/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 9
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Schletter - INV2528 | 0 | 12832.45 | -12832.45 | 29/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 27
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Schletter - INV2518 | 0 | 25790.99 | -25790.99 | 29/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 31
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Accuenergy - ASAI-007074 | 0 | 6900 | -6900 | 07/01/2026 |  | PO4525-BMGFT-20251208 - RV Approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 63
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Volkirk Properties - INV0001336 | 0 | 6610 | -6610 | 18/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Cosmic Sun: CS_BMG_007F | 39251.39 | 55080 | -15828.61 | 18/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 122
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Cosmic Sun: CS_BMG_008 | 15700.56 | 22032 | -6331.44 | 15/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 123
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | SunSpot - E033 | 22531.33 | 13950 | 8581.33 | 23/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 147
Dec-25 | 31/12/2025 | BMG Fluid Tech | Realised | Expense Claim | 0 | 0 | 0 | 31/12/2025 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 172
Dec-25 | 31/12/2025 | China Town Adhoc | Unrealised |  | 46645.91 | 0 | 46645.91 |  |  |  | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 80
Dec-25 | 31/12/2025 | China Town Adhoc | Realised | Solarworld - SASIV-25-00724 | 3850 | 3850 | 0 | 07/01/2026 |  | PO4527-CTOP1-20251208 - RV Approved | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 81
Dec-25 | 31/12/2025 | China Town Adhoc | Realised | Happy Solar INV-0347 | 14420 | 14420 | 0 | 24/12/2025 |  | PO4545-CTOP1-20251218 - RV Approved | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 82
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Kathea - 500335 | 0 | 899.72 | -899.72 | 31/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 27
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Paul van Vuuren Inv: IOG090 | 17237.1 | 83760 | -66522.9 | 15/01/2026 |  | PO4506-CSPH2-20251128 - RV Approve | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 104
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Herholdts - INV1198397 | 0 | 111600 | -111600 | 29/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 123
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Omega - OM040593 | 0 | 41010 | -41010 | 09/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 267
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Omega - OM040944 | 790.55 | 41470 | -40679.45 | 31/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 268
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Omega - OMO40594 | 0 | 460 | -460 | 09/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 269
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Container World P605064 | 0 | 1550 | -1550 | 09/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 302
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Container World P605066 | 0 | 1550 | -1550 | 09/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 303
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Container World P605075 | 0 | 2635 | -2635 | 09/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 304
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Talisman Hire - 00217594 | 608.43 | 1217.4 | -608.97 | 07/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 320
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Talisman Hire - 00217616 | 304.21 | 608.7 | -304.49 | 07/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 321
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Matriarch - INV-5801 | 3118.03 | 2843 | 275.03 | 29/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 363
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 59700.29 | -59700.29 | 08/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 378
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | DSV Inv: 180157893 | 0 | 319.09 | -319.09 | 29/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 408
Dec-25 | 31/12/2025 | Coega Steels Ph2 | Realised | Ultimate Soltions INV 2647 | 0 | 1200 | -1200 | 12/12/2025 |  | PO4419-CSPH2-20251029 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 414
Dec-25 | 31/12/2025 | Corporate Park | Realised | Van Staden Three - Inv3110 | 51172.22 | 8850 | 42322.22 | 09/01/2026 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 92
Dec-25 | 31/12/2025 | Dobsonpoint | Realised | Matriarch - INV-5975 | 26915.13 | 6000 | 20915.13 | 30/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 132
Dec-25 | 31/12/2025 | Dobsonpoint | Realised | Expense Claim | 201.38 | 154.7 | 46.68 | 08/01/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 155
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Helukabel - PSI0047534 | 0 | 89700 | -89700 | 30/01/2026 |  | PO4495-GEZ-20251126 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 30
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Rubicon Inv: INVWCRE-0072974 | 0 | 57500 | -57500 | 30/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 31
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_007_B | 45407.35 | 47700 | -2292.65 | 13/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 98
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_008_B | 45407.35 | 47700 | -2292.65 | 19/03/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 99
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Bidvest Protea Coin: 773193 | 4323.91 | 10780 | -6456.09 | 15/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_007_B | 2249.07 | 3472.75 | -1223.68 | 13/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 119
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_008_B | 2249.08 | 3472.75 | -1223.67 | 19/03/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 120
Dec-25 | 31/12/2025 | Gezina Galleries | Realised | Expense Claim | 698.1 | 495.04 | 203.06 | 08/01/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 151
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Unrealised |  | -20283.58 | 0 | -20283.58 |  |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 11
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1141 | 5529.73 | 2973.82 | 2555.91 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | Allocated from Cpt Storeroom | 0 | 1300 | -1300 | 31/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 56
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1141 | 7707.35 | 3412.24 | 4295.11 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 68
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1141 | 11535.33 | 18598.6 | -7063.27 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 102
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | JA Electrical Inv 1141 | 3912.42 | 6704.03 | -2791.61 | 18/12/2025 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 120
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | SunSpot - E034 | 19801.19 | 9565 | 10236.19 | 23/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 131
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | Matriarch - INV-5975 | 12421.03 | 6000 | 6421.03 | 30/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 134
Dec-25 | 31/12/2025 | Hungry Lion_Citrusdal | Realised | Expense Claim | 567.61 | 1023.4 | -455.79 | 08/01/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 149
Dec-25 | 31/12/2025 | Kroonstad | Realised | Rubycon - RD0710251 | 0 | 36794.4 | -36794.4 | 18/12/2025 |  | PO4534-DPK-20251210 - RV Approved | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 87
Dec-25 | 31/12/2025 | Kroonstad | Realised | DSV Inv: 180158820 | 0 | 261.4 | -261.4 | 29/01/2026 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 90
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001555 | 21557.98 | 23165.38 | -1607.4 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 36
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001556 | 26947.47 | 28956.73 | -2009.26 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001557 | 10778.99 | 11582.69 | -803.7 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 38
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001564 | 10778.99 | 11582.69 | -803.7 | 24/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 39
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001565 | 5389.49 | 5791.35 | -401.85 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 40
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001555 | 63332 | 77961.99 | -14629.99 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 63
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001556 | 79165 | 97452.49 | -18287.49 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 64
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001557 | 31666 | 38981 | -7315 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 65
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001564 | 31666 | 38981 | -7315 | 24/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 66
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001565 | 15833 | 19490.5 | -3657.5 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 67
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001563 | 23797.95 | 23510 | 287.95 | 24/12/2025 |  | PO4529-MBE-20251209 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 84
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | LPS - IN307595 | 21272.13 | 21014.75 | 257.38 | 05/02/2026 |  | PO4482-MBE-20251124 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 95
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001558 | 19296.48 | 19063 | 233.48 | 12/12/2025 |  | PO4508-MBE-20251201 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001559 | 9692 | 9574.73 | 117.27 | 18/12/2025 |  | PO4509-MBE-20251201 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 112
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001559 | 17031.98 | 16825.9 | 206.08 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 113
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001555 | 44188.8 | 72266.8 | -28078 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 119
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001556 | 55236 | 90333.5 | -35097.5 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 120
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001557 | 22094.4 | 36133.4 | -14039 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 121
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001564 | 22094.4 | 36133.4 | -14039 | 24/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 122
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001565 | 11047.2 | 18066.7 | -7019.5 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 123
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | Setso Security - SET001551 | 10041.34 | 28000 | -17958.66 | 12/12/2025 |  | PO4409-MBE-20251027 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 129
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001555 | 10625.93 | 29630.1 | -19004.17 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 135
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001556 | 13282.41 | 37037.62 | -23755.21 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 136
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001557 | 5312.97 | 14815.05 | -9502.08 | 12/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 137
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway INV0001564 | 5312.97 | 14815.05 | -9502.08 | 24/12/2025 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 138
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | The Greenway - INV0001565 | 2656.48 | 7407.53 | -4751.05 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 139
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | SunSpot - E035 | 3664.32 | 17750 | -14085.68 | 23/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 145
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | WAGMA - INV-000010 | 17164.06 | 75600 | -58435.94 | 15/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 151
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | Expense Claim | 1016.03 | 8655.54 | -7639.51 | 08/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 166
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | Evolution Coatings - INV0000138 | 2725 | 5450 | -2725 | 18/12/2025 |  | PO4519-MBE-20251203 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 180
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | L&B Consulting IN-2175 | 0 | 3500 | -3500 | 18/12/2025 |  | PO4543-MBE-20251217 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 182
Dec-25 | 31/12/2025 | Mahikeng Builders Express | Realised | DSV Inv: 180158820 | 0 | 273.93 | -273.93 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 183
Dec-25 | 31/12/2025 | Malvern Ph2 | Realised | SunSpot - E033 | 20592.08 | 13950 | 6642.08 | 23/01/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 125
Dec-25 | 31/12/2025 | Malvern Ph2 | Realised | Expense claim | 0 | 0 | 0 | 31/12/2025 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 143
Dec-25 | 31/12/2025 | Malvern Ph2 | Realised | Infinity Renewable - IN002297 | 0 | 14000 | -14000 | 12/12/2025 |  | PO4491-MVE2-20251126 - RV Approved | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 154
Dec-25 | 31/12/2025 | Marikana Old Church | Realised | JerryG& Sons INV23 | 0 | 41230 | -41230 | 09/01/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | Marikana Shoprite | Realised | The Greenway Solar Inv: INV0001585 | 0 | 8260 | -8260 | 15/01/2026 |  | PO4535-MARSR-20251210 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 83
Dec-25 | 31/12/2025 | Marikana Shoprite | Realised | JerryG & Sons INV23 | 0 | 41230 | -41230 | 09/01/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 111
Dec-25 | 31/12/2025 | Mayo Macs | Realised | Accuenergy Inv: ASAI-007060 | 0 | 15813 | -15813 | 07/01/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 40
Dec-25 | 31/12/2025 | Milkwood_Square | Realised | Expense Claim | 2740.78 | 0 | 2740.78 | 08/01/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 139
Dec-25 | 31/12/2025 | Northpoint | Realised | PLS - IN106336 | 0 | 3524.1 | -3524.1 | 12/12/2025 |  | PO4493-20251126 - RV Approved | Northpoint_Tracker.xlsx | Expenditure Breakdown | 160
Dec-25 | 31/12/2025 | Pimville | Realised | Matriarch - INV-5975 | 27796.81 | 6000 | 21796.81 | 29/01/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 136
Dec-25 | 31/12/2025 | Pimville | Realised | Expense Claim | 616.28 | 88.06 | 528.22 | 08/01/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 156
Dec-25 | 31/12/2025 | Pretoria North | Realised | Rubicon - INVRED-0136040 | 0 | 29500 | -29500 | 30/01/2026 |  | PO4496-DIP-PH2-SPN-20251126 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 32
Dec-25 | 31/12/2025 | Pretoria North | Realised | The Engineering Hub - INV/2025/12/0065 | 0 | 22639 | -22639 | 30/01/2026 |  | PO4522-DIP-Ph2-Shoprite-20251204 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 86
Dec-25 | 31/12/2025 | Pretoria North | Realised | GSG Tactical - INV000014166 | 0 | 6750 | -6750 | 29/01/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 115
Dec-25 | 31/12/2025 | Pretoria North | Realised | Matriarch - INV-5975 | 33773.38 | 8000 | 25773.38 | 30/01/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 134
Dec-25 | 31/12/2025 | Pretoria North | Realised | Expense Claim | 0 | 533.12 | -533.12 | 08/01/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 154
Dec-25 | 31/12/2025 | Protea Point | Committed | Expense Claim | 2141.18 | 1820 | 321.18 | 31/12/2025 |  |  | Protea Point_Tracker.xlsx | Expenditure Breakdown | 139
Dec-25 | 31/12/2025 | Randfontein | Realised | Expense Claim | 242.88 | 244.66 | -1.78 | 08/01/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 152
Dec-25 | 31/12/2025 | Red Rocket | Realised | Container World -CC43644 | 0 | -400 | 400 | 09/01/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 164
Dec-25 | 31/12/2025 | Red Rocket | Realised | Matriarch - INV-5976 | 488104.31 | 154022.95 | 334081.36 | 29/01/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 187
Dec-25 | 31/12/2025 | Red Rocket | Realised | Expense Claim | 162.21 | 123.76 | 38.45 | 08/01/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 200
Dec-25 | 31/12/2025 | Riverside Mall | Realised | Expense Claim | 0 | 0 | 0 | 07/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 139
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 28570.63 | 16966.52 | 11604.11 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 57141.26 | 33933.04 | 23208.22 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 40
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 64141.29 | 23150.78 | 40990.51 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 76
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 128282.07 | 46301.66 | 81980.41 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 79
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA Electrical - Inv 1144 | 55795.06 | 48720 | 7075.06 | 13/02/2026 |  | PO4450-DSHC-20251107 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 104
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 120469.6 | 110529.12 | 9940.48 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 112
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 240939.2 | 221058.24 | 19880.96 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 115
Dec-25 | 31/12/2025 | Seshego Circle | Realised | Cycad Security - INV0002713 | 6927.64 | 10000 | -3072.36 | 12/12/2025 |  | PO4524-DSHC-20251208-MI - Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 130
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 16832.88 | 19654.4 | -2821.52 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 136
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA ElectricalInv 1142 | 27231.64 | 39308.7 | -12077.06 | 12/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 139
Dec-25 | 31/12/2025 | Seshego Circle | Realised | Expense Claim | 0 | 0 | 0 | 31/12/2025 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 169
Dec-25 | 31/12/2025 | Seshego Circle | Realised | JA Electrical - Inv 1143 | 0 | 56132.72 | -56132.72 | 05/02/2026 |  | PO4507-DSHC-20251201 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 181
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | Alllocated to Cpt Storeroom | 0 | -13650 | 13650 | 31/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 30
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | Alllocated to Cpt Storeroom | 0 | -17745 | 17745 | 31/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 31
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | Allocated from cpt Storeroom | 0 | 1300 | -1300 | 31/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 53
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | DK Refrigeration - INV0003287 | 0 | 7826.09 | -7826.09 | 19/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 89
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | Overberg Security : IN24945 | 3700.52 | 7150 | -3449.48 | 04/12/2025 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 108
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | Expense Claim | 1471.58 | 1799.28 | -327.7 | 08/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 143
Dec-25 | 31/12/2025 | Shoprite Mini_Bredarsdorp | Realised | ABL Transport Inv0231 | 0 | 7500 | -7500 | 04/12/2025 |  | PO4515-GEN-20251202-RV approved | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 156
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Unrealised |  | -29557.15 | 0 | -29557.15 |  |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 11
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | Allocated from Cpt Storeroom | 0 | 1300 | -1300 | 31/12/2025 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 55
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | DSV Inv: 180157893 | 0 | 244.42 | -244.42 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 56
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | SunSpot - E034 | 19801.19 | 9565 | 10236.19 | 23/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 130
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | Matriarch - INV-5975 | 12421.03 | 6000 | 6421.03 | 30/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 133
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | Expense Claim | 2716.77 | 1023.4 | 1693.37 | 08/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 148
Dec-25 | 31/12/2025 | Shoprite Mini_Citrusdal | Realised | ABL Transport Inv 0231 | 0 | 14800 | -14800 | 04/12/2025 |  | PO4515-GEN-20251203 - RV Approved | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 161
Dec-25 | 31/12/2025 | Sibasa | Realised | Cosmic Sun -CS_SRS_011 | 0 | 112080 | -112080 | 12/12/2025 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 87
Dec-25 | 31/12/2025 | Sibasa | Realised | Bright Integrated Solutions: Inv12/25 | 0 | 19333.35 | -19333.35 | 09/01/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 111
Dec-25 | 31/12/2025 | STD GQ | Realised | Schletter - INV2479 | 0 | 15800 | -15800 | 30/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 22
Dec-25 | 31/12/2025 | STD GQ | Realised | Schletter - INV2483 | 0 | 1578 | -1578 | 30/12/2025 |  | PO4516-STD-20251202 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 23
Dec-25 | 31/12/2025 | STD GQ | Realised | Rubicon INVRED-0136070 | 34768.21 | 117500 | -82731.79 | 30/01/2026 |  | PO4497-STB-20251126 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 32
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0689 | 3345.62 | 8479.96 | -5134.33 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0684 | 1672.81 | 4239.98 | -2567.17 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 38
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken INV0692 | 2509.22 | 6359.97 | -3850.75 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 39
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0689 | 5142.86 | 3456.5 | 1686.35 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 65
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0684 | 2571.43 | 1728.25 | 843.18 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 66
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken INV0692 | 3857.14 | 2592.38 | 1264.77 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 67
Dec-25 | 31/12/2025 | STD GQ | Realised | LPS - IN307558 | 53378.26 | 34320.9 | 19057.36 | 09/01/2026 |  | PO4421-STD-20251029 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 89
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0689 | 110241.56 | 92749.51 | 17492.04 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 98
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0684 | 55120.78 | 46374.76 | 8746.02 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 99
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken INV0692 | 82681.17 | 69562.14 | 13119.03 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 100
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0689 | 14612.49 | 5714.03 | 8898.47 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 115
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken Solar INV-0684 | 7306.25 | 2857.01 | 4449.23 | 12/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 116
Dec-25 | 31/12/2025 | STD GQ | Realised | Luken INV0692 | 10959.37 | 4285.52 | 6673.85 | 18/12/2025 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 117
Dec-25 | 31/12/2025 | STD GQ | Realised | SunSpot - E036 | 78841.6 | 20725 | 58116.6 | 27/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 126
Dec-25 | 31/12/2025 | STD GQ | Realised | Expense Claim | 1018.72 | 85.68 | 933.04 | 08/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 144
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | MSA Energy - INV0003484 | 485847.99 | 306891 | 178956.99 | 04/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 6
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | MSA Energy - INV0003484 | 91846.38 | 68870.35 | 22976.03 | 04/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 13
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | MSA Energy - INV0003484 | 58153.62 | 43606.08 | 14547.54 | 04/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 14
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | Schletter - INV2520 | 6504.86 | 5492 | 1012.86 | 30/12/2025 |  | PO4526-SSDPH2-20251208 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 26
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000763 | 7903.19 | 3934.5 | 3968.69 | 12/12/2025 |  | PO4523-SSDPH2-20251208 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 35
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000764 | 11854.78 | 5901.75 | 5953.03 | 12/12/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 36
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000763 | 7648.16 | 6295.2 | 1352.96 | 12/12/2025 |  | PO4523-SSDPH2-20251208 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 61
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000764 | 11472.24 | 9442.8 | 2029.44 | 12/12/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 62
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000763 | 13903.33 | 13534.68 | 368.65 | 12/12/2025 |  | PO4523-SSDPH2-20251208 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 93
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000764 | 20855 | 20302.02 | 552.98 | 12/12/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 94
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000763 | 4368.74 | 2231.18 | 2137.56 | 12/12/2025 |  | PO4523-SSDPH2-20251208 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 109
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | BDL Solar- IN000764 | 6553.11 | 3346.77 | 3206.34 | 12/12/2025 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | Superspar Ph2 | Realised | Expense Claim | 606.41 | 456.96 | 149.45 | 08/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 138
Dec-25 | 31/12/2025 | Topsteel | Realised | L&B Consulting - Inv 2039 | 8777.12 | 7500 | 1277.12 | 04/09/2025 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 119
Dec-25 | 31/12/2025 | Topsteel | Realised | Expense Claim | 454.15 | 447.44 | 6.71 | 08/01/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 135
Dec-25 | 31/12/2025 | Tsakana Corner | Realised | Expense Claim | 0 | 0 | 0 | 30/12/2025 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 155
Dec-25 | 31/12/2025 | Umzimkhulu | Realised | Thula Moya Inv - IN04962 | 0 | 4825.5 | -4825.5 | 12/12/2025 |  | PO4438-UMZ-20251104 - RV Approved | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 58
Dec-25 | 31/12/2025 | Umzimkhulu | Realised | Expense Claim | 0 | 2386.49 | -2386.49 | 08/01/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 153
Dec-25 | 31/12/2025 | Upper_East_Side_Hotel | Realised | Expense Claim | 419.62 | 104.72 | 314.9 | 08/01/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 149
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1572 | 4631.28 | 4206 | 425.28 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 36
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1573 | 4623.57 | 4199 | 424.57 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 37
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1574 | 2311.79 | 2099.5 | 212.29 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 38
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1575 | 2311.79 | 2099.5 | 212.29 | 19/03/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 39
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1572 | 5195.72 | 2583.6 | 2612.12 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 62
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1573 | 5195.72 | 2583.6 | 2612.12 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 63
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1574 | 2597.86 | 1291.8 | 1306.06 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 64
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1575 | 2597.86 | 1291.8 | 1306.06 | 19/03/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 65
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1573 | 5364.71 | 8873.2 | -3508.49 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 95
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1574 | 2682.35 | 4436.6 | -1754.25 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 96
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1575 | 2682.35 | 4436.6 | -1754.25 | 19/03/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 97
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1572 | 4412.76 | 3556.8 | 855.96 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 110
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1573 | 4412.76 | 3556.8 | 855.96 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 111
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1574 | 2206.38 | 1778.4 | 427.98 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 112
Dec-25 | 31/12/2025 | Waterside | Realised | Matthews Group - INV-1575 | 2206.38 | 1778.4 | 427.98 | 19/03/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 113
Dec-25 | 31/12/2025 | Waterside | Realised | Matriarch - INV-5975 | 9348.29 | 6000 | 3348.29 | 29/01/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 121
Dec-25 | 31/12/2025 | Waterside | Realised | Expense Claim | 0 | 0 | 0 | 31/12/2025 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 138
Jan-26 | 31/01/2026 | 1 Bolt Ave | Realised | Onvlee Engineering - CN 01001981 | 0 | -5272.5 | 5272.5 | 21/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 89
Jan-26 | 31/01/2026 | 1 Bolt Ave | Realised | Onvlee Engineering - ONV1702 | 0 | 10436.7 | -10436.7 | 09/01/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 90
Jan-26 | 31/01/2026 | 1 Bolt Ave | Realised | Sunspot E040 | 72043.31 | 8750 | 63293.31 | 13/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 121
Jan-26 | 31/01/2026 | 1 Bolt Ave | Realised | Expense Claims | 520.69 | 109.48 | 411.21 | 05/02/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 141
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Allocated from Red Rocket | 2690.72 | 2050.1 | 640.62 | 31/01/2026 |  | Allocated from Red Rocket | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 22
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Lintels for Africa - 234145 | 37994.45 | 28948.57 | 9045.88 | 05/02/2026 |  | PO4589-7AP-20260129 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 26
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Photon Solar INV-0159 | 8262.68 | 6955 | 1307.68 | 05/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 32
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Accuenergy Inv: ASAI-007259 | 22791 | 13984.5 | 8806.5 | 26/02/2026 |  | PO4578-7AP-20260126 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 45
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Photon Solar INV-0159 | 4699.35 | 1945.2 | 2754.15 | 05/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 58
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Hisafe - Inv 00361 | 65746 | 31132.38 | 34613.62 | 29/01/2026 |  | PO4566-7AP-20260121 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 80
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Hisafe - Inv 00361 | 65746 | 31132.38 | 34613.62 | 29/01/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 81
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Photon Solar INV-0159 | 15167.78 | 15200 | -32.22 | 05/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 92
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Photon Solar INV-0159 | 2835.99 | 2755 | 80.99 | 05/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 108
Jan-26 | 31/01/2026 | 7th Avenue Park | Realised | Expense Claim | 382.25 | 314.16 | 68.09 | 05/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 137
Jan-26 | 31/01/2026 | Blackheath Park | Realised | CS_BHP_011 | 35351.11 | 42000 | -6648.89 | 05/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 103
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Container World - C605863 | 0 | 560 | -560 | 05/02/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 122
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Expense Claim | 0 | 0 | 0 | 07/02/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 161
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Cosmic Sun - CS_BHP_009 | 0 | -15292.07 | 15292.07 | 31/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 168
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Cosmic Sun - CS_BHP_009 | 0 | 15292.04 | -15292.04 | 31/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 169
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Cosmic Sun - CS_BHP_010 | 0 | 15292.04 | -15292.04 | 29/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 170
Jan-26 | 31/01/2026 | Blackheath Park | Realised | Caltest - CLTI1633 | 0 | 6550 | -6550 | 30/01/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 171
Jan-26 | 31/01/2026 | BMG Fluid Tech | Realised | Cosmic Sun - CS_BMG_009 | 15700.56 | 22032 | -6331.44 | 29/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 124
Jan-26 | 31/01/2026 | BMG Fluid Tech | Realised | Cosmic Sun - CS_BMG_010 | 7850.28 | 11016 | -3165.72 | 29/01/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 125
Jan-26 | 31/01/2026 | BMG Fluid Tech | Realised | Matriarch - INV-6235 | 9690.89 | 6000 | 3690.89 |  |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 150
Jan-26 | 31/01/2026 | BMG Fluid Tech | Realised | Expense Claim | 239.89 | 659.76 | -419.87 | 05/02/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 173
Jan-26 | 31/01/2026 | Bochum Plaza | Realised | The Engineering Hub INV/2026/01/0247 | 0 | 37476 | -37476 | 26/02/2026 |  | PO4581-DBP-20260127 - RV Approved | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 87
Jan-26 | 31/01/2026 | Bochum Plaza | Realised | Eskom: SMG954130213 | 0 | 22137.5 | -22137.5 | 29/01/2026 |  |  | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 159
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Kathea - 500335 | 0 | -899.72 | 899.72 | 31/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 28
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Paul Van Vuuren - IOG122 | 562.22 | 1980 | -1417.78 | 31/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 105
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Paul van Vuuren - CN000217 | 0 | -1980 | 1980 | 31/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 106
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | AccuEnergy - ASAI-007302 | 7.42 | 3170 | -3162.58 | 26/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 112
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 305666.3 | 480000 | -174333.7 | 23/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 224
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 76416.57 | 120000 | -43583.43 | 23/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 225
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 76416.57 | 120000 | -43583.43 | 12/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 226
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 38208.29 | 60000 | -21791.71 | 30/04/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 227
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 47760.36 | 75000 | -27239.64 | 30/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 238
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 23880.18 | 37500 | -13619.82 | 30/04/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 239
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 62088.47 | 97500 | -35411.53 | 30/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 249
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0701 | 31044.23 | 48750 | -17705.77 | 30/04/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 250
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Container World P608429 | 0 | 1400 | -1400 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 305
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Container World P608431 | 0 | 1400 | -1400 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 306
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Container World P608440 | 0 | 2380 | -2380 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 307
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Talisman Hire - 00218837 | 0 | 1826.1 | -1826.1 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 322
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Talisman Hire - 00218853 | 0 | 913.05 | -913.05 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 323
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6102 | 2843 | 2843 | 0 | 26/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 364
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6216 | 8737.26 | 8737.26 | 0 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 365
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 28655.7 | -28655.7 | 05/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 379
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Coega Development Corporation INV78403 | 0 | 140.75 | -140.75 | 19/01/2026 |  | PO4554-CSPH2-20260116 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 391
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Coega Development Corporation - INV78326 | 0 | 1936.03 | -1936.03 | 29/01/2026 |  | PO4550-CSPH2-20260112 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 404
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Ultimate Soltions INV 2667 | 0 | 1200 | -1200 | 02/04/2026 |  | PO4473-CSPH2-20251114 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 415
Jan-26 | 31/01/2026 | Coega Steels Ph2 | Realised | Fedgroup - LT000589_251231 | 0 | 271125.69 | -271125.69 | 29/01/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 442
Jan-26 | 31/01/2026 | Dobsonpoint | Realised | Thula Moya IN05014 | 11469.63 | 10697.49 | 772.14 | 23/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 40
Jan-26 | 31/01/2026 | Dobsonpoint | Realised | Thula Moya IN05014 | 10249.53 | 5341.16 | 4908.37 | 23/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 68
Jan-26 | 31/01/2026 | Dobsonpoint | Realised | Thula Moya IN05014 | 18853.68 | 27928.32 | -9074.64 | 23/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 101
Jan-26 | 31/01/2026 | Dobsonpoint | Realised | Thula Moya IN05014 | 1230.39 | 2875.03 | -1644.64 | 23/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 124
Jan-26 | 31/01/2026 | Dobsonpoint | Realised | Expense Claim | 241.27 | 89.01 | 152.26 | 05/02/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 156
Jan-26 | 31/01/2026 | Gezina Galleries | Realised | Cosmic Sun - CS_GZG_012 | 0 | 1728.1 | -1728.1 | 29/01/2026 |  | PO4562-DIP-Ph2-Gezi-20260121 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 81
Jan-26 | 31/01/2026 | Gezina Galleries | Realised | The Engineering Hub INV/2026/01/0248 | 0 | 85867 | -85867 | 26/02/2026 |  | PO4579-DIP-Ph2-Gezi-20260127 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 89
Jan-26 | 31/01/2026 | Gezina Galleries | Realised | Bidvest Protea Coin: 768743 | 0 | 35280 | -35280 | 05/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 111
Jan-26 | 31/01/2026 | Gezina Galleries | Realised | Expense Claim | 349.3 | 990.08 | -640.79 | 05/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 152
Jan-26 | 31/01/2026 | Gillwell | Realised | The Engineering Hub INV/2026/01/0250 | 0 | 36463 | -36463 | 26/02/2026 |  | PO4575-DIP2GILL-20260126 - RV Approved | Gillwell_Tracker.xlsx | Expenditure Breakdown | 90
Jan-26 | 31/01/2026 | Gillwell | Realised | Emergent Invoice: 004910 | 0 | -60000 | 60000 | 29/01/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 93
Jan-26 | 31/01/2026 | Hungry Lion_Citrusdal | Realised | Matriarch - INV-6234 | 13287.72 | 16154.12 | -2866.4 | 26/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 140
Jan-26 | 31/01/2026 | Hungry Lion_Citrusdal | Realised | Expense Claim | 0 | 136.45 | -136.45 | 05/02/2026 |  |  | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 150
Jan-26 | 31/01/2026 | IconsSA_KZN | Realised | SunSpot - E039 | 18772.54 | 12575 | 6197.54 | 29/01/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 119
Jan-26 | 31/01/2026 | Kopanong Kudube | Realised | Eskom: 917332967 | 0 | 4249.75 | -4249.75 | 29/01/2026 |  |  | Kopanong Kudube_Tracker.xlsx | Expenditure Breakdown | 134
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -27300 | 27300 | 31/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 29
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -27300 | 27300 | 31/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 30
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | Matriarch Inv: 6200 | 23141.46 | 11169 | 11972.46 | 29/01/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 48
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | ATS Africa - INV-0468 | 56217.71 | 55537.5 | 680.21 | 23/01/2026 |  | PO4552-MBE-20260116 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 107
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | ATS Africa - INV-0468 | 56217.71 | 55537.5 | 680.21 | 05/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 108
Jan-26 | 31/01/2026 | Mahikeng Builders Express | Realised | Expense Claim | 352.41 | 3332 | -2979.59 | 05/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 167
Jan-26 | 31/01/2026 | Malvern Ph2 | Realised | Matriarch Inv: 6200 | 52433.34 | 11169 | 41264.34 | 29/01/2026 |  | Roedolph to confirm cost, what happened to PH1 meter? | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 53
Jan-26 | 31/01/2026 | Malvern Ph2 | Unrealised |  | 3129.06 | 0 | 3129.06 | 31/01/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 109
Jan-26 | 31/01/2026 | Malvern Ph2 | Realised | Matriarch - INV-6235 | 9048.57 | 6000 | 3048.57 | 26/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 128
Jan-26 | 31/01/2026 | Malvern Ph2 | Realised | Expense claim | 430.87 | 337.48 | 93.39 | 05/02/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 144
Jan-26 | 31/01/2026 | Marikana Old Church | Realised | The Engineering Hub INV/2026/01/0253 | 0 | 6089 | -6089 | 26/02/2026 |  | PO4574-MAROC-20260126 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 88
Jan-26 | 31/01/2026 | Marikana Old Church | Realised | JerryG & Sons INV25 | 0 | 33900 | -33900 | 29/01/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 111
Jan-26 | 31/01/2026 | Marikana Shoprite | Realised | The Engineering Hub Inv: INV/2026/01/0252 | 0 | 8375 | -8375 | 26/02/2026 |  | PO4573-MARSH-20260126 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 81
Jan-26 | 31/01/2026 | Marikana Shoprite | Realised | JerryG & Sons INV26 | 0 | 33900 | -33900 | 29/01/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 112
Jan-26 | 31/01/2026 | Mayo Macs | Realised | Allocated to Joburg Storeroom | 0 | -68870 | 68870 | 31/01/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 15
Jan-26 | 31/01/2026 | Mayo Macs | Realised | Expense Claim | 0 | 3613.64 | -3613.64 | 05/02/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 127
Jan-26 | 31/01/2026 | Mayo Macs | Realised | Herholdts - INV1208290 | 0 | 161300 | -161300 | 26/02/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 140
Jan-26 | 31/01/2026 | Mayo Macs | Realised | MG INV-1589 | 0 | 88678.15 | -88678.15 | 23/01/2026 |  | PO4561-MMS-20250121 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 144
Jan-26 | 31/01/2026 | Mayo Macs | Realised | MG INV-1590 | 0 | 17157.5 | -17157.5 | 23/01/2026 |  | PO4560-MMS-20250121 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 148
Jan-26 | 31/01/2026 | Meraki Ph3 | Unrealised |  | 0 | -67440 | 67440 | 31/01/2026 |  |  | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 17
Jan-26 | 31/01/2026 | Meraki Ph3 | Unrealised |  | 0 | 7328.61 | -7328.61 | 28/02/2026 |  | PO4559-MER-20260120 - RV Apporved | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 128
Jan-26 | 31/01/2026 | Meraki Ph3 | Realised | Thula Moya - IN04998 | 0 | 6542.61 | -6542.61 | 28/02/2026 |  | PO4557-MER-20260119 - RV Apporved | Meraki Ph3_Tracker.xlsx | Expenditure Breakdown | 129
Jan-26 | 31/01/2026 | Milkwood_Square | Unrealised |  | -61932.04 | 0 | -61932.04 | 31/01/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 11
Jan-26 | 31/01/2026 | Milkwood_Square | Realised | Allocated from Steelpark | 0 | 975 | -975 | 31/01/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 50
Jan-26 | 31/01/2026 | Milkwood_Square | Realised | SunSpot E031 | 83969.2 | 20180 | 63789.2 | 05/02/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 115
Jan-26 | 31/01/2026 | Northpoint | Realised | Omarlek IIN106336 | 0 | 3524.1 | -3524.1 | 19/03/2026 |  | PO4494-20251126 - RV Approved | Northpoint_Tracker.xlsx | Expenditure Breakdown | 161
Jan-26 | 31/01/2026 | Pimville | Realised | Eskom Inv: SDI965705783 | 0 | 13611.42 | -13611.42 | 29/01/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 134
Jan-26 | 31/01/2026 | Pimville | Realised | Expense Claim | 785.4 | 66.16 | 719.24 | 05/02/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 157
Jan-26 | 31/01/2026 | Pretoria North | Realised | The Engineering Hub INV/2026/01/0249 | 0 | 44224 | -44224 | 26/02/2026 |  | PO4580-DIP-Ph2-SPN-20260127 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 90
Jan-26 | 31/01/2026 | Pretoria North | Realised | Expense Claim | 0 | 971.04 | -971.04 | 05/02/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 155
Jan-26 | 31/01/2026 | Randfontein | Realised | Rubicon - INVCRED-0137907 | 0 | 84000 | -84000 | 26/02/2026 |  | PO4572-DRS-20260123 - RV Approved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 30
Jan-26 | 31/01/2026 | Randfontein | Realised | Rubicon - INVCRED-0137907 | 0 | 4500 | -4500 | 26/02/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 31
Jan-26 | 31/01/2026 | Randfontein | Realised | Plumbryt Inv 023 | 0 | 17120 | -17120 | 29/01/2026 |  | PO4548-DRS-20260108 - RV Apporved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 86
Jan-26 | 31/01/2026 | Randfontein | Realised | Plumbryt Inv 023 | 0 | 4280 | -4280 | 30/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 87
Jan-26 | 31/01/2026 | Randfontein | Realised | Expense Claim | 325.67 | 315.11 | 10.56 | 05/02/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 153
Jan-26 | 31/01/2026 | Red Rocket | Unrealised |  | -42222.16 | 0 | -42222.16 | 31/01/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 11
Jan-26 | 31/01/2026 | Red Rocket | Realised | Herholdts - CN130769 | 0 | -69140 | 69140 | 31/01/2026 |  | RMA | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 17
Jan-26 | 31/01/2026 | Red Rocket | Realised | Allocated to 7th Avenue | 0 | -2050.1 | 2050.1 | 31/01/2026 |  | To be allocated to 7th Avenue | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 26
Jan-26 | 31/01/2026 | Red Rocket | Realised | Allocated to riverside Mall | 0 | -1767.5 | 1767.5 | 31/01/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 77
Jan-26 | 31/01/2026 | Red Rocket | Realised | Expense Claim | 1001.63 | 637.84 | 363.79 | 05/02/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 201
Jan-26 | 31/01/2026 | Red Rocket | Realised | Craigcor - PI141993 | 70757.8 | 61237.8 | 9520 | 15/01/2026 |  | PO4511-RR-20251201 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 213
Jan-26 | 31/01/2026 | Red Rocket | Realised | HappySolar - INV-0351 | 0 | 9520 | -9520 | 29/01/2026 |  | PO4532-RR-20251209 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 214
Jan-26 | 31/01/2026 | Riverside Mall | Realised | MSA Energy - INV0003559 | 511106.69 | 368440 | 142666.69 | 30/03/2026 |  | PO4751-RSM-20250414 - JT Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 6
Jan-26 | 31/01/2026 | Riverside Mall | Realised | MSA Energy - INV0003559 | 88048.51 | 68870.35 | 19178.16 | 26/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 13
Jan-26 | 31/01/2026 | Riverside Mall | Realised | MSA Energy - INV0003559 | 55748.96 | 43606.08 | 12142.88 | 26/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 14
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Schletter - INV002599 | 105322.5 | 51620.6 | 53701.9 | 26/02/2026 |  | PO4563-RSM-20260121 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 21
Jan-26 | 31/01/2026 | Riverside Mall | Realised | MSA Energy - INV0003559 | 69733.17 | 55960 | 13773.17 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 28
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0182 | 24814.79 | 19913.56 | 4901.23 | 29/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 32
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0183 | 24814.79 | 19913.56 | 4901.23 | 05/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 33
Jan-26 | 31/01/2026 | Riverside Mall | Realised | MSA Energy - INV0003570 | 9671.84 | 8598.34 | 1073.5 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 44
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Accuenergy Inv: ASAI-007302 | 13967.25 | 12417 | 1550.25 | 26/02/2026 |  | PO4577-RSM-20260126 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 45
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Allocated from Red Rocket | 1988.17 | 1767.5 | 220.67 | 31/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 46
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0182 | 28696.28 | 13764.63 | 14931.65 | 29/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 59
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0183 | 28696.28 | 13764.63 | 14931.65 | 05/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 60
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Hisafe - 00360 | 53617.21 | 67474.56 | -13857.35 | 29/01/2026 |  | PO4565-RSM-20260121 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 84
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0182 | 32716.67 | 38850 | -6133.34 | 29/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 94
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0183 | 32716.67 | 38850 | -6133.34 | 05/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 95
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0182 | 7636.95 | 8833.24 | -1196.29 | 29/01/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 110
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Leading Edge Power INV-0183 | 7636.95 | 8833.24 | -1196.29 | 05/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 111
Jan-26 | 31/01/2026 | Riverside Mall | Realised | Expense Claim | 249.57 | 261.8 | -12.23 | 05/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 140
Jan-26 | 31/01/2026 | SA Metal_14 Christiaan_B | Realised | Thula Moya - IC200104 | 0 | -19463.42 | 19463.42 | 31/01/2026 |  |  | SA Metal_14 Christiaan_B_Tracker.xlsx | Expenditure Breakdown | 124
Jan-26 | 31/01/2026 | SA Metal_20 Christiaan | Realised | Thula Moya - IC200104 | 0 | -19463.42 | 19463.42 | 31/01/2026 |  |  | SA Metal_20 Christiaan_Tracker.xlsx | Expenditure Breakdown | 121
Jan-26 | 31/01/2026 | SA Metal_22 Christiaan | Realised | Thula Moya - IC200104 | 0 | -9731.71 | 9731.71 | 31/01/2026 |  |  | SA Metal_22 Christiaan_Tracker.xlsx | Expenditure Breakdown | 131
Jan-26 | 31/01/2026 | Seshego Circle | Realised | MSA Energy - INV0003547 | 0 | 4136.4 | -4136.4 | 19/03/2026 |  | PO4556-DSHC-20260119 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 9
Jan-26 | 31/01/2026 | Seshego Circle | Realised | MSA Energy - INV0003541 | 0 | 10677.4 | -10677.4 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 10
Jan-26 | 31/01/2026 | Seshego Circle | Realised | K2 Systems - Credit SACN42026 | 0 | -67046.2 | 67046.2 | 06/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 26
Jan-26 | 31/01/2026 | Seshego Circle | Realised | K2 Systems - InvSAI672026 | 0 | 15556.95 | -15556.95 | 23/01/2026 |  | PO4553-DSHC-20260116 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 29
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 21427.97 | 12724.89 | 8703.08 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 38
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 7142.66 | 4241.63 | 2901.03 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 41
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 48105.88 | 17363.16 | 30742.72 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 77
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 16035.29 | 5787.72 | 10247.57 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 81
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 0 | 10150 | -10150 | 13/02/2026 |  | PO4571-DSHC-20260123 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 106
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 90352.2 | 82896.92 | 7455.28 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 113
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 30117.4 | 27632.28 | 2485.12 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 116
Jan-26 | 31/01/2026 | Seshego Circle | Unrealised |  | -20049.89 | 0 | -20049.89 |  |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 131
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 16832.88 | 14740.8 | 2092.08 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 137
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 16832.88 | 4913.6 | 11919.28 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 140
Jan-26 | 31/01/2026 | Seshego Circle | Realised | Expense Claim | 0 | 0 | 0 | 05/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 170
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 0 | 54437.33 | -54437.33 | 13/02/2026 |  | PO4518-DSHC-20251203 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 182
Jan-26 | 31/01/2026 | Seshego Circle | Realised | JA Electrical Inv 1156 | 0 | 95838 | -95838 | 13/02/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 184
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Unrealised |  | 12784.22 | 0 | 12784.22 |  |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 25
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 5925.93 | 2133.64 | 3792.29 | 31/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 37
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 11852.04 | 4267.34 | 7584.7 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 38
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 11852.04 | 4267.34 | 7584.7 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 39
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 5926.02 | 2133.67 | 3792.35 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 40
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 5926.02 | 2133.67 | 3792.35 | 05/03/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 41
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 5697.38 | 2058.25 | 3639.13 | 31/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 66
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 11394.76 | 4116.49 | 7278.27 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 67
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 11394.76 | 4116.49 | 7278.27 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 68
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 5697.38 | 2058.25 | 3639.13 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 69
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 5697.38 | 2058.25 | 3639.13 | 05/03/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 70
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 10941.7 | 15557.41 | -4615.71 | 31/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 99
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 21883.4 | 31114.83 | -9231.42 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 100
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 21883.4 | 31114.83 | -9231.42 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 101
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 10941.7 | 15557.41 | -4615.71 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 102
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 10941.7 | 15557.41 | -4615.71 | 05/03/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 103
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 2952.97 | 5135.04 | -2182.07 | 31/01/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 116
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 5905.93 | 10270.08 | -4364.15 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 117
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical: Inv 1152 | 5905.93 | 10270.08 | -4364.15 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 118
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 2952.97 | 5135.04 | -2182.07 | 13/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 119
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | 2952.97 | 5135.04 | -2182.07 | 05/03/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 120
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | JA Electrical Inv 1153 | -0.01 | -0.01 | 0 | 05/03/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 121
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | SunSpot - E037 | 71130.68 | 15375 | 55755.68 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 125
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | Matriarch - INV-6235 | 27758.32 | 6000 | 21758.32 | 26/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 128
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | Matriarch - INV-6234 | 23822 | 25967.95 | -2145.95 | 26/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 134
Jan-26 | 31/01/2026 | Shoprite Mini_Bredarsdorp | Realised | Expense Claim | 1097.44 | 136.45 | 960.99 | 05/02/2026 |  |  | Shoprite Mini_Bredarsdorp_Tracker.xlsx | Expenditure Breakdown | 144
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 9426.87 | 3356.5 | 6070.37 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 37
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 4713.42 | 1678.25 | 3035.17 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 39
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 9426.85 | 3356.5 | 6070.35 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 40
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 9426.85 | 3356.5 | 6070.35 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 41
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 4713.42 | 1678.25 | 3035.17 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 42
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 4713.4 | 1678.24 | 3035.16 | 13/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 43
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 14044.92 | 6438.55 | 7606.37 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 67
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 7022.46 | 3219.28 | 3803.19 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 69
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 14044.92 | 6438.55 | 7606.37 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 70
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 14044.92 | 6438.55 | 7606.37 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 71
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 7022.46 | 3219.28 | 3803.19 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 72
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 7022.46 | 3219.28 | 3803.19 | 13/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 73
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 22094.44 | 27201.3 | -5106.85 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 101
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 11047.22 | 13600.65 | -2553.43 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 103
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 22094.44 | 27201.3 | -5106.85 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 104
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 22094.45 | 27201.3 | -5106.85 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 105
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 11047.22 | 13600.65 | -2553.43 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 106
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 11047.22 | 13600.65 | -2553.43 | 13/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 107
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 6108.66 | 7485.95 | -1377.29 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 119
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 3054.33 | 3742.98 | -688.64 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 121
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1151 | 6108.66 | 7485.95 | -1377.29 | 29/01/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 122
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 6108.66 | 7485.95 | -1377.29 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 123
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 3054.33 | 3742.98 | -688.64 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 124
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | JA Electrical INV 1154 | 3054.33 | 3742.98 | -688.64 | 13/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 125
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | Matriarch - INV-6234 | 22597.74 | 25059.23 | -2461.49 | 26/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 139
Jan-26 | 31/01/2026 | Shoprite Mini_Citrusdal | Realised | Expense Claim | 0 | 136.46 | -136.46 | 05/02/2026 |  |  | Shoprite Mini_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 149
Jan-26 | 31/01/2026 | Sibasa | Realised | Cosmic Sun - CS_SRS_012 | 0 | 14690 | -14690 | 26/02/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 85
Jan-26 | 31/01/2026 | Sibasa | Realised | Engineering Hub INV/2026/01/0246 | 0 | 31876 | -31876 | 26/02/2026 |  | PO4582-DSS-20260127 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 90
Jan-26 | 31/01/2026 | Sibasa | Realised | Expense Claim | 0 | 0 | 0 | 05/02/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 153
Jan-26 | 31/01/2026 | STD GQ | Realised | Allocated to superspar Despatch - PH2 | -2704.84 | -56000 | 53295.16 | 31/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 33
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0699 | 2574.42 | 4239.98 | -1665.55 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 40
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0706 | 2574.42 | 4239.98 | -1665.55 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 41
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0702 | 1287.21 | 2119.99 | -832.78 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 42
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0705 | 1287.21 | 2119.99 | -832.78 | 12/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 43
Jan-26 | 31/01/2026 | STD GQ | Realised | Matriarch Inv: 6200 | 13841.3 | 11169 | 2672.3 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 50
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0699 | 2571.43 | 1728.25 | 843.18 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 68
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0706 | 2571.43 | 1728.25 | 843.18 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 69
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0702 | 1285.71 | 864.13 | 421.59 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 70
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0705 | 1285.71 | 864.13 | 421.59 | 12/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 71
Jan-26 | 31/01/2026 | STD GQ | Realised | Matriarch - iNV-6240 | 125017.3 | 90120 | 34897.3 | 26/02/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 87
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0699 | 55120.78 | 46374.76 | 8746.02 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 101
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0706 | 55120.78 | 46374.76 | 8746.02 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 102
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0702 | 27560.39 | 23187.38 | 4373.01 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 103
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0705 | 27560.39 | 23187.38 | 4373.01 | 12/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 104
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0699 | 7306.27 | 2857.01 | 4449.26 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 118
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0706 | 7306.25 | 2857.01 | 4449.24 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 119
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0702 | 3653.11 | 1428.5 | 2224.61 | 29/01/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 120
Jan-26 | 31/01/2026 | STD GQ | Realised | Luken Solar INV-0705 | 3653.11 | 1428.5 | 2224.61 | 12/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 121
Jan-26 | 31/01/2026 | STD GQ | Realised | Matriarch - INV-6235 | 22825.07 | 6000 | 16825.07 | 26/02/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 129
Jan-26 | 31/01/2026 | STD GQ | Realised | Customized Maintenance Agreement | 15923.53 | 0 | 15923.53 | 02/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 135
Jan-26 | 31/01/2026 | STD GQ | Realised | Expense Claim | 2546.53 | 199.92 | 2346.61 | 05/02/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 145
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from PE Storetoom | 61736.99 | 15882 | 45854.99 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 21
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from PE Storetoom | 7899.85 | 2474.31 | 5425.54 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 22
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from PE Storeroom | 8336.14 | 2610.96 | 5725.18 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 23
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from PE Storetoom | 4048.41 | 1268 | 2780.41 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 24
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from Std Bank GQ | 55267.94 | 28000 | 27267.94 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 31
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Allocated from Std Bank GQ | 55267.94 | 28000 | 27267.94 | 31/01/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 32
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | DSV Inv:180161978 | 969.91 | 664.97 | 304.94 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 33
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | DSV Inv: 180163669 | 0 | 361.85 | -361.85 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 48
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Eastern Switchgear - 17043 | 98500.82 | 81076 | 17424.82 | 19/03/2026 |  | PO4533-SSDPH2-20251209 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 56
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Performance Monitoring Contract | 15121.33 | 0 | 15121.33 | 28/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 130
Jan-26 | 31/01/2026 | Superspar Ph2 | Realised | Expense Claim | 558.81 | 913.92 | -355.11 | 05/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 139
Jan-26 | 31/01/2026 | Topsteel | Realised | MSA Energy INV0003560 | 746843.5 | 546560 | 200283.5 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 6
Jan-26 | 31/01/2026 | Topsteel | Realised | MSA Energy INV0003560 | 262500 | 206611.05 | 55888.95 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 14
Jan-26 | 31/01/2026 | Topsteel | Realised | Schletter Inv: INV002586 | 136640 | 45028 | 91612 | 26/02/2026 |  | PO4564-TPS-20260121 - RV Approved | Topsteel_Tracker.xlsx | Expenditure Breakdown | 21
Jan-26 | 31/01/2026 | Topsteel | Realised | MSA Energy INV0003560 | 100958.2 | 83940 | 17018.2 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 28
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_001 | 16137.53 | 13417.28 | 2720.25 | 29/01/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 32
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_002 | 24206.29 | 20125.92 | 4080.38 | 05/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 33
Jan-26 | 31/01/2026 | Topsteel | Realised | MSA Energy INV0003560 | 14013 | 8598.34 | 5414.66 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 44
Jan-26 | 31/01/2026 | Topsteel | Realised | Accuenergy Inv: ASAI-007261 | 22791 | 13984.5 | 8806.5 | 26/02/2026 |  | PO4576-TPS-20260126 - RV Approved | Topsteel_Tracker.xlsx | Expenditure Breakdown | 45
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_001 | 21328.62 | 7950 | 13378.62 | 29/01/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 58
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_002 | 31992.93 | 11925 | 20067.93 | 05/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 59
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_001 | 24142.22 | 28665 | -4522.78 | 29/01/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 90
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_002 | 36213.33 | 42997.5 | -6784.17 | 05/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 91
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_001 | 2457.64 | 1880 | 577.64 | 29/01/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 106
Jan-26 | 31/01/2026 | Topsteel | Realised | Cosmic Sun - CS_TPS_002 | 3686.46 | 2820 | 866.46 | 05/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 107
Jan-26 | 31/01/2026 | Topsteel | Realised | Expense Claim | 1070.89 | 1003.41 | 67.48 | 05/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 136
Jan-26 | 31/01/2026 | Trident Steel GP | Realised | Cosmic Sun: CS_TRS_999 | 0 | 17160 | -17160 | 05/02/2026 |  | PO4584-TSG-20260127 - RV Approved | Trident Steel GP_Tracker.xlsx | Expenditure Breakdown | 171
Jan-26 | 31/01/2026 | Tsakana Corner | Realised | Plumryt INV 024 | 0 | 16160 | -16160 | 29/01/2026 |  | PO4549-DTC-20260108 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 86
Jan-26 | 31/01/2026 | Tsakana Corner | Realised | Plumryt INV 024 | 0 | 4040 | -4040 | 26/02/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 87
Jan-26 | 31/01/2026 | Tsakana Corner | Realised | Expense Claim | 0 | 0 | 0 | 26/02/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 156
Jan-26 | 31/01/2026 | Umzimkhulu | Realised | Expense Claim | 0 | 0 | 0 | 30/01/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 154
Jan-26 | 31/01/2026 | Upper_East_Side_Hotel | Realised | Rubicon INVRED-0137860 | 0 | 126000 | -126000 | 28/02/2026 |  | PO4570-UESH-20260122 - RV Approved | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 29
Jan-26 | 31/01/2026 | Upper_East_Side_Hotel | Realised | Expense Claim | 0 | 0 | 0 | 05/02/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 150
Jan-26 | 31/01/2026 | Waterside | Realised | SunSpot - E038 | 13185.19 | 10500 | 2685.19 | 16/04/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 118
Jan-26 | 31/01/2026 | Waterside | Realised | Expense Claim | 404.58 | 0 | 404.58 | 05/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 139
Feb-26 | 28/02/2026 | 1 Bolt Ave | Realised | Matriarch - INV-6571 | 49401.13 | 6000 | 43401.13 | 27/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 124
Feb-26 | 28/02/2026 | 1 Bolt Ave | Realised | Matriarch - INV-6570 | 35569.06 | 41047.63 | -5478.57 | 27/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 130
Feb-26 | 28/02/2026 | 1 Bolt Ave | Realised | Expense Claims | 2326.68 | 328.44 | 1998.24 | 05/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 142
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | MSA Energy - INV0003571 | 577060.68 | 357460 | 219600.68 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 6
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | MSA Energy - INV0003571 | 175000 | 137740.7 | 37259.3 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 14
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Schletter - INV002624 | 41064.48 | 35671.7 | 5392.78 | 27/03/2026 |  | PO4605-7AP-20260204 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 23
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Schletter - INV002624 | 101106.13 | 87650.85 | 13455.28 | 30/03/2026 |  | PO4605-7AP-20260204 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 24
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Schletter - INV002650 | 5986.73 | 5052.5 | 934.23 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 25
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | MSA Energy - INV0003571 | 66505.4 | 55960 | 10545.4 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 28
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0163 | 12397.97 | 10432.5 | 1965.47 | 13/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 33
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0168 | 16530.62 | 13910 | 2620.62 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0169 | 20663.28 | 17387.5 | 3275.78 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 35
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | MSA Energy - INV0003571 | 15593.23 | 8598.34 | 6994.89 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 44
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Matriarch - INV-6577 | 22825.27 | 11169 | 11656.27 | 31/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 46
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Uber | 40.5 | 22.33 | 18.17 | 03/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 47
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Switchboard - 2-SOI002860 | 217088.32 | 89859.36 | 127228.96 | 26/02/2026 |  | PO4539-7AP-20251212 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 53
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0163 | 7049.02 | 2917.8 | 4131.22 | 13/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 59
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0168 | 9398.69 | 3890.4 | 5508.29 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 60
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0169 | 11748.36 | 4863 | 6885.36 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 61
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | AC Direct - ACQuote00075849 | 31677.3 | 11999.13 | 19678.17 | 26/02/2026 |  | PO4639-7AP-2026223 - RV Approved | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 84
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0163 | 22751.67 | 22800 | -48.33 | 13/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 93
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0168 | 30335.56 | 30400 | -64.44 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 94
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0169 | 37919.44 | 38000 | -80.56 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 95
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0163 | 4253.98 | 4132.5 | 121.48 | 13/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 109
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0168 | 5671.98 | 5510 | 161.98 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 110
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Photon Solar INV-0169 | 7089.97 | 6887.5 | 202.47 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 111
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Sunspo Inv: E044 | 13628.38 | 8750 | 4878.38 | 23/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 120
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Rubicon - INVRED-0139196 | 67413.98 | 50000 | 17413.98 | 27/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 122
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Uber | 29.66 | 22 | 7.66 | 14/02/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 123
Feb-26 | 28/02/2026 | 7th Avenue Park | Realised | Expense Claim | 358.47 | 257.04 | 101.43 | 05/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 138
Feb-26 | 28/02/2026 | Black Heath | Realised | Cosmic Sun Inv: CS_BLA_999 | 0 | 18270 | -18270 | 26/02/2026 |  |  | Black Heath_Tracker.xlsx | Expenditure Breakdown | 124
Feb-26 | 28/02/2026 | Blackheath Park | Realised | Rubicon - INVRED-0138814 | 0 | 252000 | -252000 | 27/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | Blackheath Park | Realised | Container World - C609335 | 0 | 620 | -620 | 31/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 123
Feb-26 | 28/02/2026 | Blackheath Park | Realised | Matriarch - INV-6570 | 72845.4 | 79441.87 | -6596.48 | 31/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 147
Feb-26 | 28/02/2026 | Blackheath Park | Realised | Expense Claim | 0 | 0 | 0 | 07/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 162
Feb-26 | 28/02/2026 | BMG Fluid Tech | Realised | Allocated to Magic Company | 0 | -2790 | 2790 | 28/02/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 60
Feb-26 | 28/02/2026 | BMG Fluid Tech | Realised | Expense Claim | 0 | 0 | 0 |  |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 174
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -5000.8 | 5000.8 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -5033.6 | 5033.6 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 38
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -52000 | 52000 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 63
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -62270 | 62270 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 64
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -900 | 900 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 68
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -261 | 261 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 69
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -8016 | 8016 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 70
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -7200 | 7200 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 71
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -711 | 711 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 72
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -234 | 234 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 73
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -492 | 492 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 74
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -750 | 750 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 75
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -378 | 378 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 76
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -360 | 360 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 77
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -1410 | 1410 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 78
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -540 | 540 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 79
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -491 | 491 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 80
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -249390 | 249390 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 127
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -73000 | 73000 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 130
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -9800 | 9800 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 132
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -13860 | 13860 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 133
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -18875 | 18875 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 134
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -16065 | 16065 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 135
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -604.65 | 604.65 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 136
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Allocated to Ziegler Warehouse | 0 | -10740 | 10740 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 137
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Luken Solar INV-0714 | 47805.18 | 9531.6 | 38273.58 | 05/03/2026 |  | PO4631-CSPH2-20260219 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 211
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Omega - OM041678 | 0 | 41470 | -41470 | 30/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 270
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Container World P611940 | 0 | 1550 | -1550 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 309
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Container World P611942 | 0 | 1550 | -1550 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 310
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Container World P611950 | 0 | 2635 | -2635 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 311
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Talisman Hire - 00220052 | 0 | 2434.78 | -2434.78 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 324
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Talisman Hire - 00220066 | 0 | 1217.39 | -1217.39 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 325
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | 2XTwo - EME-262 | 193606.68 | 35600 | 158006.68 | 26/02/2026 |  | PO4372-CSPH2-20251020 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 330
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6571 | 11581.17 | 10000 | 1581.17 | 27/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 341
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6571 | 11581.17 | 10000 | 1581.17 | 27/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 342
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 27/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 347
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 07/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 348
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 04/06/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 349
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 30/06/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 350
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 31/07/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 351
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 31/08/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 352
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 30/09/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 353
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 31/10/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 354
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 30/11/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 355
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 31/12/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 356
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.76 | 82140.67 | 4756.09 | 31/01/2027 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 357
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6572 | 86896.8 | 82140.67 | 4756.13 | 25/02/2027 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 358
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Matriarch - INV-6568 | 0 | -8737.26 | 8737.26 | 28/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 366
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 52616.57 | -52616.57 | 05/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 380
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Coega Development Corporation - 06-02-26 | 0 | 5215.61 | -5215.61 | 12/03/2026 |  | PO4613-CSPH2-20260206 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 405
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Coega Development Corporation - INV79872 | 0 | 7051.28 | -7051.28 | 02/04/2026 |  | PO4649-CSPH2-20260227 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 406
Feb-26 | 28/02/2026 | Coega Steels Ph2 | Realised | Fedgroup - 1110788_260217 | 0 | 496745.53 | -496745.53 | 26/02/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 443
Feb-26 | 28/02/2026 | Corporate Park | Realised | Greenway Solar INV0001631 | 0 | 3880.43 | -3880.43 | 19/03/2026 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 175
Feb-26 | 28/02/2026 | Dobsonpoint | Realised | Expense Claim | 0 | 66.16 | -66.16 | 05/03/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 157
Feb-26 | 28/02/2026 | FY 2026 Adhoc | Realised | Allocated from BMG Fluid Tech | 12510 | 2790 | 9720 | 28/02/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 6
Feb-26 | 28/02/2026 | FY 2026 Adhoc | Realised | Cosmic Sun Inv: CS_BLA_999 | 0 | 18270 | -18270 | 26/02/2026 |  | PO4637-DBH-20260220 - RV Apporved | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 68
Feb-26 | 28/02/2026 | FY 2026 Adhoc | Realised | Cosmic Sun Inv: CS_KPG_001 | 0 | 30195 | -30195 | 12/03/2026 |  | PO4635-DIP_KK-20260219 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 80
Feb-26 | 28/02/2026 | FY 2026 Adhoc | Realised | CS_SSK_001 | 0 | 27075 | -27075 | 12/03/2026 |  | PO4634-DSS-20260219 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 85
Feb-26 | 28/02/2026 | Gezina Galleries | Realised | Allocated from Joburg Storeroom | 0 | 68870 | -68870 | 28/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 14
Feb-26 | 28/02/2026 | Gezina Galleries | Realised | Switchboard - 2-ARI001536 | 0 | -1728.1 | 1728.1 | 28/02/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 82
Feb-26 | 28/02/2026 | Gezina Galleries | Realised | Matriarch - INV-6571 | 11769.59 | 8000 | 3769.59 | 27/03/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 130
Feb-26 | 28/02/2026 | Gezina Galleries | Realised | Expense Claim | 349.3 | 617.74 | -268.44 | 05/03/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 153
Feb-26 | 28/02/2026 | Gezina Galleries | Realised | PowerTech - INV0001463 | 0 | 4400 | -4400 | 19/03/2026 |  | PO4652-DIP-Ph2-Gezi-20260303 - RV Approved | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 165
Feb-26 | 28/02/2026 | Klein Karoo | Realised | Cosmic Sun - CS_KKM_006 | 0 | 9500 | -9500 | 26/02/2026 |  |  | Klein Karoo_Tracker.xlsx | Expenditure Breakdown | 125
Feb-26 | 28/02/2026 | Kopanong Kudube | Realised | Cosmic Sun - CS_KPG_001 | 0 | 30195 | -30195 | 12/03/2026 |  | PO4635-DIP_KK-20260219 | Kopanong Kudube_Tracker.xlsx | Expenditure Breakdown | 135
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -4613.76 | 4613.76 | 28/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 23
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -3033.88 | 3033.88 | 28/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 24
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -1800.37 | 1800.37 | 28/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 25
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -12285 | 12285 | 28/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 31
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Allocated to Joburg Storeroom | 0 | -12967.5 | 12967.5 | 28/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 32
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | The Greenway - INV0001641 | 6984.56 | 5791.35 | 1193.21 | 30/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 41
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | The Greenway - INV0001641 | 15833 | 19490.5 | -3657.5 | 30/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 68
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | The Greenway - INV0001641 | 11047.2 | 18066.7 | -7019.5 | 30/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 124
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | The Greenway - INV0001641 | 2656.48 | 7407.53 | -4751.05 | 30/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 140
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Matriarch - INV-6571 | 1362.23 | 6000 | -4637.77 | 27/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 149
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | WAGMA - INV-000023 | 0 | 19200 | -19200 | 13/02/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 152
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Matriarch - INV-6570 | 25308 | 32269.14 | -6961.14 | 27/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 157
Feb-26 | 28/02/2026 | Mahikeng Builders Express | Realised | Expense Claim | 500.48 | 0 | 500.48 | 05/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 168
Feb-26 | 28/02/2026 | Malvern Ph2 | Realised | Expense claim | 892.58 | 0 | 892.58 | 05/03/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 145
Feb-26 | 28/02/2026 | Mayo Macs | Realised | Matthews Group - INV-1595 | 0 | 17157.5 | -17157.5 | 26/02/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 149
Feb-26 | 28/02/2026 | Mayo Macs | Realised | Herholdts - INV1236863 | 0 | 42619 | -42619 | 27/03/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 155
Feb-26 | 28/02/2026 | Milkwood_Square | Realised | Airvent - Emergent | 0 | 24840 | -24840 | 26/02/2026 |  | PO4623-MLW-20260213 - RV Approved | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 82
Feb-26 | 28/02/2026 | Pimville | Realised | Expense Claim | 785.4 | 66.16 | 719.24 | 05/03/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 158
Feb-26 | 28/02/2026 | PnP Bethal | Realised | Expense Claim | 3020.4 | 3962.03 | -941.63 | 05/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 159
Feb-26 | 28/02/2026 | Pretoria North | Realised | Matriarch - INV-6570 | 188915.91 | 59518.41 | 129397.5 | 27/03/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 139
Feb-26 | 28/02/2026 | Pretoria North | Realised | Expense Claim | 0 | 249.49 | -249.49 | 05/03/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 156
Feb-26 | 28/02/2026 | Randfontein | Realised | Schletter - INV002603 | 0 | 1252 | -1252 | 27/03/2026 |  | PO4595-DRS-20260202 - RV Approved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 22
Feb-26 | 28/02/2026 | Randfontein | Realised | Accuenergy - ASAI-007333 | 0 | 7197.5 | -7197.5 | 27/03/2026 |  | PO4603-DRS-20260204 - RV Approved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 50
Feb-26 | 28/02/2026 | Randfontein | Realised | Thula Moya - IN05020 | 0 | 16725 | -16725 | 30/03/2026 |  | PO4618-DRS-20260211 - RV Approved | Randfontein_Tracker.xlsx | Expenditure Breakdown | 89
Feb-26 | 28/02/2026 | Randfontein | Realised | Thula Moya IN05042 | 33935.57 | 48312.06 | -14376.49 | 30/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 98
Feb-26 | 28/02/2026 | Randfontein | Realised | Thula Moya IN05041 | 33935.57 | 48312.06 | -14376.49 | 30/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 99
Feb-26 | 28/02/2026 | Randfontein | Realised | Thula Moya IN05043 | 16967.81 | 24156.04 | -7188.23 | 30/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 100
Feb-26 | 28/02/2026 | Randfontein | Realised | Thula Moya IN05044 | 16967.81 | 24156.04 | -7188.23 | 18/06/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 101
Feb-26 | 28/02/2026 | Randfontein | Realised | Matriarch - INV-6571 | 27902.95 | 6000 | 21902.95 | 27/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 132
Feb-26 | 28/02/2026 | Randfontein | Realised | Expense Claim | 369.36 | 946.29 | -576.93 | 05/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 154
Feb-26 | 28/02/2026 | Randfontein | Unrealised |  | 442507 | 0 | 442507 |  |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 167
Feb-26 | 28/02/2026 | Red Rocket | Realised | PnP | 0 | 234.77 | -234.77 | 28/02/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 114
Feb-26 | 28/02/2026 | Red Rocket | Realised | Gadget Time | 0 | 130.39 | -130.39 | 12/02/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 118
Feb-26 | 28/02/2026 | Red Rocket | Realised | Expense Claim | 1838.4 | 1357.32 | 481.08 | 05/03/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 202
Feb-26 | 28/02/2026 | Red Rocket | Realised | JA Electrical - INV 1158 | 0 | 52687.97 | -52687.97 | 20/02/2026 |  | PO4513-RR-20251202 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 207
Feb-26 | 28/02/2026 | Red Rocket | Realised | HappySolar - INV-0353 | 0 | 7000 | -7000 | 26/02/2026 |  | JP Approved (no PO) | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 215
Feb-26 | 28/02/2026 | Red Rocket | Realised | JA Electrical - 1159 | 0 | 3531.8 | -3531.8 | 26/02/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 216
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0188 | 18611.09 | 14935.17 | 3675.92 | 12/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0189 | 18611.09 | 14935.17 | 3675.92 | 19/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 35
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Matriarch - INV-6577 | 16323.32 | 11169 | 5154.32 | 27/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 47
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Uber | 27.59 | 22.33 | 5.26 | 03/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 48
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Switchboard Inv: 2-SOI002863 | 172720.98 | 88515.02 | 84205.96 | 26/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 54
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0188 | 20471.25 | 10323.47 | 10147.77 | 12/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 61
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0189 | 20471.25 | 10323.47 | 10147.77 | 19/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 62
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Ascend Inv-4989 | 53617.21 | 33715.45 | 19901.76 | 13/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 86
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0188 | 24537.5 | 29137.5 | -4600 | 12/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 96
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0189 | 24537.5 | 29137.5 | -4600 | 19/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 97
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0188 | 5727.71 | 6624.94 | -897.23 | 12/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 112
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Leading Edge - INV-0189 | 5727.72 | 6624.94 | -897.22 | 19/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 113
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Sunspot Inv: E044 | 13331.93 | 8750 | 4581.93 | 23/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 122
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Rubicon - INVRED-0139197 | 67413.98 | 50000 | 17413.98 | 27/03/2026 |  | PO4608-RSM020260204 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 124
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Uber | 29.66 | 22 | 7.66 | 14/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 125
Feb-26 | 28/02/2026 | Riverside Mall | Realised | Expense Claim | 137.8 | 128.52 | 9.28 | 05/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 141
Feb-26 | 28/02/2026 | Sam Sekhoti | Realised | Cosmic Sun Inv:CS_SSK_001 | 0 | 27075 | -27075 | 12/03/2026 |  | PO4634-DSS-20260219 | Sam Sekhoti_Tracker.xlsx | Expenditure Breakdown | 143
Feb-26 | 28/02/2026 | Seshego Circle | Realised | K2 Systems - SAI1382026 | 0 | 2283.7 | -2283.7 | 06/02/2026 |  | PO4616-DSHC-20260211 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 27
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 7142.66 | 4241.63 | 2901.03 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 39
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 7142.66 | 4241.63 | 2901.03 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 42
Feb-26 | 28/02/2026 | Seshego Circle | Realised | DSV Inv: 180167184 | 0 | 226.34 | -226.34 | 27/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 63
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 16035.29 | 5787.72 | 10247.57 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 78
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 16035.29 | 5787.72 | 10247.57 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 80
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 30117.41 | 27632.31 | 2485.1 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 114
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 30117.4 | 27632.28 | 2485.12 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 117
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 3403.96 | 4913.6 | -1509.64 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 138
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 3403.96 | 4913.6 | -1509.64 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 141
Feb-26 | 28/02/2026 | Seshego Circle | Realised | Expense Claim | 2330.77 | 3538.03 | -1207.26 | 05/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 171
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 0 | 21393.95 | -21393.95 | 19/03/2026 |  | PO4610-DSHC-20260205 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 186
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 0 | 237957.79 | -237957.79 | 19/03/2026 |  | PO4626-DSHC-20260217 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 188
Feb-26 | 28/02/2026 | Seshego Circle | Realised | JA Electrical Inv 1161 | 0 | 2608.69 | -2608.69 | 19/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 189
Feb-26 | 28/02/2026 | Sibasa | Realised | MSA Energy INV0003591 | 0 | 3701.4 | -3701.4 | 09/04/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 7
Feb-26 | 28/02/2026 | Sibasa | Realised | MSA Energy INV0003591 | 0 | 500 | -500 | 09/04/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 8
Feb-26 | 28/02/2026 | Sibasa | Realised | Cosmic Sun - CS_SRS_013 | 0 | 112080 | -112080 | 20/02/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 88
Feb-26 | 28/02/2026 | Sibasa | Realised | Expense Claim | 0 | 3538 | -3538 | 05/03/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 154
Feb-26 | 28/02/2026 | STD GQ | Realised | Luken INV-0716 | 391520.65 | 102616.93 | 288903.72 | 05/03/2026 |  | PO4648-STD -20260227 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 85
Feb-26 | 28/02/2026 | STD GQ | Realised | Luken Solar - INV-0708 | 2061 | 1129.28 | 931.72 | 13/02/2026 |  | PO4609-STD-20260204 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 92
Feb-26 | 28/02/2026 | STD GQ | Unrealised |  | 3753.47 | 0 | 3753.47 | 05/03/2026 |  |  | STD GQ_Tracker.xlsx | Expenditure Breakdown | 146
Feb-26 | 28/02/2026 | STD GQ | Realised | Schletter - INV002634 | 0 | 6416.04 | -6416.04 | 27/03/2026 |  | PO4469-STD-20251113 - RV Approved | STD GQ_Tracker.xlsx | Expenditure Breakdown | 156
Feb-26 | 28/02/2026 | Steelpark | Realised | MSA Energy - INV0003648 | 452188.45 | 260780 | 191408.45 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 6
Feb-26 | 28/02/2026 | Steelpark | Realised | MSA Energy INV0003653 | 0 | 0 | 0 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 7
Feb-26 | 28/02/2026 | Steelpark | Realised | MSA Energy - INV0003648 | 115853.66 | 68870.35 | 46983.31 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 14
Feb-26 | 28/02/2026 | Steelpark | Realised | Solarworld SASIV-26-00115 | 22588.99 | 5700 | 16888.99 | 30/03/2026 |  | PO4642-SSP-20260225 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 21
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Joburg Storeroom | 10272.05 | 2592 | 7680.05 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 22
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Joburg Streroom | 7026.52 | 1773.04 | 5253.48 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 23
Feb-26 | 28/02/2026 | Steelpark | Realised | Joburg Storeroom | 0 | 0 | 0 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 24
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Cpt Storeroom | 4339.46 | 1095 | 3244.46 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 25
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Cpt Storeroom | 4339.46 | 1095 | 3244.46 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 26
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocared from Stockroom | 8235.07 | 2078 | 6157.07 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 27
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Joburg Streroom | 4989.39 | 1259 | 3730.39 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 28
Feb-26 | 28/02/2026 | Steelpark | Realised | Joburg Storeroom | 0 | 0 | 0 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 29
Feb-26 | 28/02/2026 | Steelpark | Realised | Joburg Storeroom | 0 | 0 | 0 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 30
Feb-26 | 28/02/2026 | Steelpark | Realised | DSV Inv: 180167184 | 9528.55 | 2404.39 | 7124.16 | 27/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 31
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Joburg Streroom | 12057.02 | 13650 | -1592.98 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | Steelpark | Realised | Allocated from Joburg Streroom | 12057.02 | 13650 | -1592.98 | 28/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 35
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0186 | 6053.81 | 6853.65 | -799.83 | 20/02/2026 |  | PO4620-SSP-20260212 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 38
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0187 | 9080.72 | 10280.47 | -1199.75 | 26/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 39
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy INV-0190 | 12107.63 | 13707.29 | -1599.66 | 12/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 40
Feb-26 | 28/02/2026 | Steelpark | Realised | MSA Energy - INV0003648 | 13375.84 | 8598.34 | 4777.5 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 50
Feb-26 | 28/02/2026 | Steelpark | Realised | Accueenergy Inv: ASAI-007396 | 23620.7 | 15184 | 8436.7 | 27/03/2026 |  | PO4617-SSP-20260211 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 51
Feb-26 | 28/02/2026 | Steelpark | Realised | Matriarch - INV-6577 | 17374.84 | 11169 | 6205.84 | 30/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 53
Feb-26 | 28/02/2026 | Steelpark | Realised | DSV Inv: 180167184 | 656.99 | 422.33 | 234.66 | 31/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 55
Feb-26 | 28/02/2026 | Steelpark | Realised | Red Pole:SO-35689 | 2839.03 | 1825 | 1014.03 | 30/08/2025 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 56
Feb-26 | 28/02/2026 | Steelpark | Realised | current Automation Inv: SOQ324142 | 1888.69 | 1214.1 | 674.59 | 10/09/2025 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 57
Feb-26 | 28/02/2026 | Steelpark | Realised | Switchboard Inv: 2-SOI002868 | 84942.08 | 24740.64 | 60201.44 | 26/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 61
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0186 | 11521.23 | 3355.73 | 8165.5 | 20/02/2026 |  | PO4620-SSP-20260212 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 66
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0187 | 17281.85 | 5033.59 | 12248.25 | 26/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 67
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy INV-0190 | 23042.46 | 6711.46 | 16331 | 12/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 68
Feb-26 | 28/02/2026 | Steelpark | Realised | CBB Inv: CBB-5722 | 2500.74 | 3600 | -1099.26 | 11/09/2025 |  | PO4051-STLP-20250627 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 87
Feb-26 | 28/02/2026 | Steelpark | Realised | Accuenergy Inv: ASAI-006974 | 1993.64 | 2870 | -876.36 | 12/12/2025 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 88
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0186 | 12741.18 | 11922.82 | 818.36 | 20/02/2026 |  | PO4620-SSP-20260212 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 98
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0187 | 19111.76 | 17884.23 | 1227.54 | 26/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 99
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy INV-0190 | 25482.35 | 23845.64 | 1636.71 | 12/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 100
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0186 | 6946.09 | 4984.43 | 1961.66 | 20/02/2026 |  | PO4620-SSP-20260212 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 114
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy Inv: INV-0187 | 10419.18 | 7476.68 | 2942.5 | 26/02/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 115
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge Energy INV-0190 | 13892.21 | 9968.89 | 3923.33 | 12/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 116
Feb-26 | 28/02/2026 | Steelpark | Realised | L&B Consulting: Inv 1701 | 9577.24 | 7690.9 | 1886.34 | 22/08/2024 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 127
Feb-26 | 28/02/2026 | Steelpark | Realised | Rubicon - INVRED-0139914 | 62263.42 | 50000 | 12263.42 | 27/03/2026 |  | PO4627-SSP-20260217 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 128
Feb-26 | 28/02/2026 | Steelpark | Realised | HappySolar Inv: 0346 | 12328.16 | 9900 | 2428.16 | 24/12/2025 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 130
Feb-26 | 28/02/2026 | Steelpark | Realised | Leading Edge INV0171 | 2169.36 | 1742.08 | 427.28 | 28/11/2025 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 131
Feb-26 | 28/02/2026 | Steelpark | Realised | Expense Claims | 522.16 | 422.08 | 100.08 | 05/03/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 143
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000765 | 15532.26 | 7869 | 7663.26 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 37
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000766 | 19415.33 | 9836.25 | 9579.08 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 38
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000767 | 7766.13 | 3934.5 | 3831.63 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 39
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000768 | 7766.13 | 3934.5 | 3831.63 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 40
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000769 | 3883.07 | 1967.25 | 1915.82 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 41
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000770 | 3883.07 | 1967.25 | 1915.82 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 42
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | Matriarch - INV-6577 | 0 | 11169 | -11169 | 27/03/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 47
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000765 | 15296.32 | 12590.4 | 2705.92 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 63
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000766 | 19120.4 | 15738 | 3382.4 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 64
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000767 | 7648.16 | 6295.2 | 1352.96 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 65
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000768 | 7648.16 | 6295.2 | 1352.96 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 66
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000769 | 3824.08 | 3147.6 | 676.48 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 67
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000770 | 3824.08 | 3147.6 | 676.48 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 68
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | AccEnergy ASAI-007327 | 2255.76 | 2120 | 135.76 | 27/03/2026 |  | PO4601-SSDPH2-20260203 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 84
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | The Engineering Hub Inv: INV/2026/02/0303 | 4146.55 | 3897 | 249.55 | 27/03/2026 |  | PO4597-SSDPH2-20260203 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 85
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000765 | 27806.67 | 27069.36 | 737.31 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 95
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000766 | 34758.33 | 33836.7 | 921.63 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 96
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000767 | 13903.33 | 13534.68 | 368.65 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 97
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000768 | 13903.33 | 13534.68 | 368.65 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 98
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000769 | 6951.67 | 6767.34 | 184.33 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 99
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000770 | 6951.67 | 6767.34 | 184.33 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 100
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000765 | 8737.48 | 4462.36 | 4275.12 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 111
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000766 | 10921.85 | 5577.95 | 5343.9 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 112
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000767 | 4368.74 | 2231.18 | 2137.56 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 113
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000768 | 4368.74 | 2231.18 | 2137.56 | 26/02/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 114
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000769 | 2184.37 | 1115.59 | 1068.78 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 115
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | BDL Solar - IN000770 | 2184.37 | 1115.59 | 1068.78 | 16/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 116
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | Sunspot E041 | 24186.76 | 18060 | 6126.76 | 27/03/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 121
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | Matriarch - INV-6571 | 8035.47 | 6000 | 2035.47 | 27/03/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 124
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | Expense Claim | 248.29 | 228.48 | 19.81 | 05/03/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 140
Feb-26 | 28/02/2026 | Superspar Ph2 | Realised | Infinity Inv: IN002354 | 0 | 30000 | -30000 | 20/02/2026 |  | PO4599-SSDPH2-20260203 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 151
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_004 | 32275.06 | 26834.56 | 5440.5 | 05/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 34
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_003 | 40343.82 | 33543.19 | 6800.63 | 12/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 35
Feb-26 | 28/02/2026 | Topsteel | Realised | Matriarch - INV-6577 | 24405.48 | 11169 | 13236.48 | 27/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 46
Feb-26 | 28/02/2026 | Topsteel | Realised | Uber | 40.51 | 22.34 | 18.17 | 03/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 47
Feb-26 | 28/02/2026 | Topsteel | Realised | Swithboard - 2-SOI002862 | 223619.5 | 83351.62 | 140267.88 | 26/02/2026 |  | PO4591-TPS-20260129 - RV Approved | Topsteel_Tracker.xlsx | Expenditure Breakdown | 53
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_004 | 42657.24 | 15900 | 26757.24 | 05/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 60
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_003 | 53321.55 | 19875 | 33446.55 | 12/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 61
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_004 | 48284.44 | 57330 | -9045.56 | 05/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 92
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_003 | 60355.56 | 71662.5 | -11306.94 | 12/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 93
Feb-26 | 28/02/2026 | Topsteel | Unrealised |  | 10588.76 | 0 | 10588.76 |  |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 102
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_004 | 13386.28 | 3760 | 9626.28 | 05/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 108
Feb-26 | 28/02/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_003 | 16732.85 | 4700 | 12032.85 | 12/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 109
Feb-26 | 28/02/2026 | Topsteel | Realised | Sunspot Inv: E044 | 13457.56 | 8750 | 4707.56 | 24/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 118
Feb-26 | 28/02/2026 | Topsteel | Realised | Rubicon - INVRED-0139200 | 68414.39 | 50000 | 18414.39 | 27/03/2026 |  | PO4607-TPS-20260204 - RV Approved | Topsteel_Tracker.xlsx | Expenditure Breakdown | 120
Feb-26 | 28/02/2026 | Topsteel | Realised | Uber | 30.1 | 22 | 8.1 | 14/02/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 121
Feb-26 | 28/02/2026 | Topsteel | Realised | Expense Claim | 279.21 | 214.2 | 65.01 | 07/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 137
Feb-26 | 28/02/2026 | Tsakana Corner | Realised | Matriarch - INV-6571 | 9029.65 | 6000 | 3029.65 | 27/03/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 133
Feb-26 | 28/02/2026 | Tsakana Corner | Realised | Expense Claim | 1410.44 | 1378.91 | 31.53 | 05/03/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 157
Feb-26 | 28/02/2026 | Tsakana Corner | Realised | Cosmic Sun: CS_TSK_013 | 0 | 30384.37 | -30384.37 | 13/02/2026 |  | PO4604-DTC-20260204 - RV Approved | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 167
Feb-26 | 28/02/2026 | Tsakana Corner | Realised | Cosmic Sun - CS_TSK_014 | 0 | 30384.37 | -30384.37 | 26/03/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 168
Feb-26 | 28/02/2026 | Umzimkhulu | Realised | Switchboard - 2-ARI001536 | 0 | -4825.5 | 4825.5 | 28/02/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 59
Feb-26 | 28/02/2026 | Umzimkhulu | Realised | Thula Moya - IN05028 | 0 | 3472.56 | -3472.56 | 26/03/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 163
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | MSA Energy INV0003593 | 0 | 2301 | -2301 | 09/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 7
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | MSA Energy INV0003593 | 0 | 400 | -400 | 09/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 8
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 109267.65 | 119175 | -9907.35 | 26/02/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 98
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 43707.06 | 47670 | -3962.94 | 12/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 99
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 43707.06 | 47670 | -3962.94 | 19/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 100
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 21853.53 | 23835 | -1981.47 | 02/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 101
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 21853.53 | 23835 | -1981.47 | 23/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 102
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 17090.15 | 37761.88 | -20671.73 | 26/02/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 116
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 6836.06 | 15104.75 | -8268.69 | 12/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 117
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 6836.06 | 15104.75 | -8268.69 | 19/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 118
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 3418.03 | 7552.38 | -4134.35 | 02/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 119
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Cosmic Sun - CS_UES_003 | 3418.03 | 7552.38 | -4134.35 | 23/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 120
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | SunSpot Investments E041 | 11797.35 | 7875 | 3922.35 | 27/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 125
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Matriarch - INV-6571 | 14291.77 | 8000 | 6291.77 | 27/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 128
Feb-26 | 28/02/2026 | Upper_East_Side_Hotel | Realised | Expense Claim | 0 | 0 | 0 | 07/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 151
Feb-26 | 28/02/2026 | Waterside | Realised | Matthews Group - INV-1572 | 5364.71 | 8873.2 | -3508.49 | 12/02/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 94
Feb-26 | 28/02/2026 | Waterside | Realised | Matriarch - INV-6570 | 54596.53 | 10354.59 | 44241.94 | 27/03/2026 |  |  | Waterside_Tracker.xlsx | Expenditure Breakdown | 127
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018722 | 98686.93 | 69250 | 29436.93 | 10/04/2026 |  | PO4615-WWB-20260209 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 71
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018722 | 438925.27 | 308000 | 130925.27 | 10/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 72
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018722 | 10403.1 | 7300 | 3103.1 | 10/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 73
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018722 | 82369.74 | 57800 | 24569.74 | 10/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 74
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018722 | 41754.9 | 29300 | 12454.9 | 10/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 75
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar : IN000774 | 50281.88 | 35283.5 | 14998.38 | 05/03/2026 |  | PO4630-WWB-20260219 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 77
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar : IN000775 | 30169.13 | 21170.1 | 8999.03 | 05/03/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 78
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar - IN000776 | 20112.75 | 14113.4 | 5999.35 | 16/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 79
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar : IN000774 | 19661.86 | 13797 | 5864.86 | 05/03/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 82
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar : IN000775 | 11796.83 | 8278 | 3518.83 | 05/03/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 83
Feb-26 | 28/02/2026 | Westway BESS | Realised | BDL Solar - IN000776 | 7864.74 | 5518.8 | 2345.94 | 16/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 84
Feb-26 | 28/02/2026 | Westway BESS | Realised | Accuenergy Invoice: ASAI-007441 | 5657.58 | 3970 | 1687.58 | 27/03/2026 |  | PO4628-WWB-20260217 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 88
Feb-26 | 28/02/2026 | Westway BESS | Realised | SIAAC - CINV018880 | 5201.55 | 3650 | 1551.55 | 09/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 90
Feb-26 | 28/02/2026 | Westway BESS | Realised | Expense Claim | 243.67 | 195.16 | 48.51 | 05/03/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 155
Mar-26 | 31/03/2026 | 1 Bolt Ave | Realised | UMFA - INV-11242 | 0 | 6621.08 | -6621.08 | 16/04/2026 |  | PO4714-BOLT-20260330 - PV Approved | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 80
Mar-26 | 31/03/2026 | 1 Bolt Ave | Unrealised |  | 93594.2 | 0 | 93594.2 | 31/03/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 86
Mar-26 | 31/03/2026 | 1 Bolt Ave | Realised | Expense Claims | 3188.77 | 0 | 3188.77 | 09/04/2026 |  |  | 1 Bolt Ave_Tracker.xlsx | Expenditure Breakdown | 143
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0171 | 8265.31 | 6955 | 1310.31 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 36
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0172 | 8265.31 | 6955 | 1310.31 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 37
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0173 | 4132.66 | 3477.5 | 655.16 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 38
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0174 | 4132.66 | 3477.5 | 655.16 | 16/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 39
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0171 | 4700.02 | 1945 | 2755.02 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 62
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0172 | 4698.88 | 1945 | 2753.88 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 63
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0173 | 2349.44 | 972.5 | 1376.94 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 64
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0174 | 2349.68 | 972.6 | 1377.08 | 16/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 65
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0171 | 15167.78 | 15200 | -32.22 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 96
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0172 | 15167.78 | 15200 | -32.22 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 97
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0173 | 7583.89 | 7600 | -16.11 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 98
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0174 | 7583.89 | 7600 | -16.11 | 16/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 99
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0171 | 2835.99 | 2755 | 80.99 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 112
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0172 | 2835.99 | 2755 | 80.99 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 113
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0173 | 1417.99 | 1377.5 | 40.49 | 30/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 114
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar INV-0174 | 1417.99 | 1377.5 | 40.49 | 16/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 115
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Happy Solar INV-0357 | 8089.68 | 7300 | 789.68 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 124
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Matriarch -INV-6901 | 19649.81 | 23490.94 | -3841.13 | 07/05/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 130
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Expense Claim | 458.42 | 287.1 | 171.32 | 03/04/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 139
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | Photon Solar Inv: 0170 | 12420 | 35853 | -23433 | 12/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 151
Mar-26 | 31/03/2026 | 7th Avenue Park | Realised | ABL Transport - INV0320 | 0 | 4600 | -4600 | 19/03/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 153
Mar-26 | 31/03/2026 | Black Heath | Realised | Cosmic Sun Inv: CS_BLA_1000 | 0 | 18270 | -18270 | 19/03/2026 |  |  | Black Heath_Tracker.xlsx | Expenditure Breakdown | 125
Mar-26 | 31/03/2026 | Blackheath Park | Realised | Container World - CC44264 | 0 | -400 | 400 | 31/03/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 124
Mar-26 | 31/03/2026 | Blackheath Park | Realised | Expense Claim | 5197.9 | 0 | 5197.9 | 07/04/2026 |  |  | Blackheath Park_Tracker.xlsx | Expenditure Breakdown | 163
Mar-26 | 31/03/2026 | BMG Fluid Tech | Realised | Otto Wireless Solutions - IO129580 | 0 | 895 | -895 | 02/04/2026 |  | PO4666-BMGFT-20260309 - RV Approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 112
Mar-26 | 31/03/2026 | BMG Fluid Tech | Realised | Cosmic Sun - CS_BMG_011 | 7850.28 | 11016 | -3165.72 | 16/04/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 126
Mar-26 | 31/03/2026 | BMG Fluid Tech | Realised | Matriarch -INV-6901 | 35315.71 | 49800.87 | -14485.16 | 07/05/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 156
Mar-26 | 31/03/2026 | BMG Fluid Tech | Realised | Expense Claim | -1752.92 | 590.54 | -2343.46 | 07/04/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 175
Mar-26 | 31/03/2026 | Bochum Plaza | Realised | Sunspot Investments E027 | 0 | 2314.29 | -2314.29 | 27/03/2026 |  |  | Bochum Plaza_Tracker.xlsx | Expenditure Breakdown | 125
Mar-26 | 31/03/2026 | China Town Adhoc | Realised | Happy Solar INV-0359 | 0 | 60950 | -60950 | 19/03/2026 |  |  | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 152
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | MSA Energy INV000681 | 0 | 13640 | -13640 | 07/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 20
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | MSA Energy INV000681 | 0 | 1600 | -1600 | 07/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 21
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | Oemga - OM042216 | 0 | 7855.19 | -7855.19 | 21/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 271
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | Container World - PC44252 | 0 | -1300 | 1300 | 31/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 312
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | Container World - PC44221 | 0 | -1350 | 1350 | 31/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 313
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | Container World - PC44222 | 0 | -2295 | 2295 | 31/03/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 314
Mar-26 | 31/03/2026 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 14045.67 | -14045.67 | 03/04/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 381
Mar-26 | 31/03/2026 | Corporate Park | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 137
Mar-26 | 31/03/2026 | De Drift | Realised | MSA Energy- INV0003678 | 2183668.42 | 1600840 | 582828.42 | 07/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 6
Mar-26 | 31/03/2026 | De Drift | Realised | MSA Energy- INV0003678 | 576470.59 | 482092.45 | 94378.14 | 07/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 14
Mar-26 | 31/03/2026 | De Drift | Realised | Schletter - INV002774 | 376621.18 | 123543 | 253078.18 | 30/04/2026 |  | PO4687-DDSC-20260319 -RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 21
Mar-26 | 31/03/2026 | De Drift | Realised | Allocated from Seshego | 62891.62 | 54600 | 8291.62 | 31/03/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 30
Mar-26 | 31/03/2026 | De Drift | Realised | Allocated from Seshego | 55030.17 | 47775 | 7255.17 | 31/03/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 31
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_001 | 40070.37 | 34787.5 | 5282.87 | 09/04/2026 |  | PO4688-DDSC-20260319 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 41
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_002 | 60105.55 | 52181.25 | 7924.3 | 09/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 42
Mar-26 | 31/03/2026 | De Drift | Realised | MSA Energy- INV0003678 | 11524.74 | 8598.34 | 2926.4 | 07/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 53
Mar-26 | 31/03/2026 | De Drift | Realised | AccuEnergy - ASAI-007737 | 26536.14 | 19798 | 6738.14 | 30/04/2026 |  | PO4690-DDSC-20260319 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 55
Mar-26 | 31/03/2026 | De Drift | Realised | Switchboard - 2-SOI002927 | 462897.41 | 253044.65 | 209852.76 | 29/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 68
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_001 | 28994.58 | 15850 | 13144.58 | 09/04/2026 |  | PO4688-DDSC-20260319 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 73
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_002 | 43491.87 | 23775 | 19716.87 | 09/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 74
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_001 | 70702.22 | 93300 | -22597.78 | 09/04/2026 |  | PO4688-DDSC-20260319 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 105
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_002 | 106053.33 | 139950 | -33896.67 | 09/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 106
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_001 | 17387.48 | 7435 | 9952.48 | 09/04/2026 |  | PO4688-DDSC-20260319 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 121
Mar-26 | 31/03/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_002 | 26081.22 | 11152.5 | 14928.72 | 09/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 122
Mar-26 | 31/03/2026 | De Drift | Realised | Okusha - EE25 | 107389.67 | 91380 | 16009.67 | 29/06/2026 |  | PO4636-DDSC-20260220 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 135
Mar-26 | 31/03/2026 | De Drift | Realised | Auxilio Dei Inv: 032 | 0 | 21002.22 | -21002.22 | 30/10/2025 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 139
Mar-26 | 31/03/2026 | De Drift | Realised | Auxilio Dei Inv: 032 | 0 | 21002.22 | -21002.22 | 19/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 140
Mar-26 | 31/03/2026 | De Drift | Realised | Expense Claim | 1927.41 | 1485 | 442.41 | 03/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 149
Mar-26 | 31/03/2026 | Dobsonpoint | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 130
Mar-26 | 31/03/2026 | Dobsonpoint | Realised | Matriarch -INV-6901 | 198531.6 | 48677.6 | 149854 | 07/05/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 139
Mar-26 | 31/03/2026 | Dobsonpoint | Realised | Expense Claim | 0.45 | 50.49 | -50.04 | 03/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 158
Mar-26 | 31/03/2026 | FY 2026 Adhoc | Unrealised |  | 0 | 116.14 | -116.14 | 04/12/2025 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 65
Mar-26 | 31/03/2026 | FY 2026 Adhoc | Realised | Cosmic Sun Inv: CS_BLA_1000 | 0 | 18270 | -18270 | 19/03/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 69
Mar-26 | 31/03/2026 | Gezina Galleries | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 126
Mar-26 | 31/03/2026 | Gezina Galleries | Realised | Matriarch -INV-6901 | 325616.75 | 108660.61 | 216956.14 | 07/05/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 135
Mar-26 | 31/03/2026 | Gezina Galleries | Realised | Expense Claim | 0 | 356.4 | -356.4 | 03/04/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 154
Mar-26 | 31/03/2026 | Gillwell | Realised | Allocated from Upper Eastside | 0 | 54000 | -54000 | 31/03/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 53
Mar-26 | 31/03/2026 | Gillwell | Realised | DSV Inv: 180169937 + 180170816 | 0 | 409.54 | -409.54 | 30/04/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 55
Mar-26 | 31/03/2026 | Gillwell | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 125
Mar-26 | 31/03/2026 | Gillwell | Realised | Expense Claim | 0 | 4121.69 | -4121.69 | 03/04/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 151
Mar-26 | 31/03/2026 | Gillwell | Realised | Camtech Services - INV1449 | 0 | 4250 | -4250 | 12/03/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 161
Mar-26 | 31/03/2026 | IconsSA_KZN | Realised | ASI connect"PMQ000015117 | 0 | 2430 | -2430 | 02/04/2026 |  | PO4681-IKZN-20260317 - RV Approved | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 151
Mar-26 | 31/03/2026 | Kroonstad | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 130
Mar-26 | 31/03/2026 | Mahikeng Builders Express | Realised | Allocated to PnP Bethal | 0 | -11898.6 | 11898.6 | 31/03/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 85
Mar-26 | 31/03/2026 | Mahikeng Builders Express | Realised | Expense Claim | 0 | 3465 | -3465 | 03/04/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 169
Mar-26 | 31/03/2026 | Mahikeng Builders Express | Unrealised |  | 2725 | 0 | 2725 |  |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 181
Mar-26 | 31/03/2026 | Malvern Ph2 | Realised | Matriarch -INV-6901 | 14309.7 | 17082.2 | -2772.5 | 07/05/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 134
Mar-26 | 31/03/2026 | Malvern Ph2 | Realised | Expense claim | 0 | 215.82 | -215.82 | 03/04/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 146
Mar-26 | 31/03/2026 | Marikana Old Church | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 126
Mar-26 | 31/03/2026 | Marikana Old Church | Realised | Expense Claim | 0 | 2077.89 | -2077.89 | 03/04/2026 |  |  | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 152
Mar-26 | 31/03/2026 | Marikana Shoprite | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 128
Mar-26 | 31/03/2026 | Marikana Shoprite | Realised | Expense Claim | 0 | 1606.51 | -1606.51 | 03/04/2026 |  |  | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 154
Mar-26 | 31/03/2026 | Mayo Macs | Realised | MG INV-1600 | 0 | 88678.15 | -88678.15 | 26/02/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 145
Mar-26 | 31/03/2026 | Mayo Macs | Realised | CN-1601 | 0 | -20449.01 | 20449.01 | 28/02/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 146
Mar-26 | 31/03/2026 | Mayo Macs | Realised | Herholdts: INV124564 | 0 | 2500 | -2500 | 30/04/2026 |  | PO4656-MMS-20260305 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 156
Mar-26 | 31/03/2026 | Milkwood_Square | Realised | Airvent - TJR06179 | 0 | 16560 | -16560 | 30/03/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 83
Mar-26 | 31/03/2026 | Mondi | Realised | ABB South Africa - 2680009044 | 685548.03 | 619498.8 | 66049.23 | 16/04/2026 |  | PO4632-MON-20260219 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 115
Mar-26 | 31/03/2026 | Mondi | Realised | Switchboard - 2-SOI002846 | 1823850.1 | 1648130.98 | 175719.12 | 06/02/2026 |  | PO4611-MON-20260205 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 127
Mar-26 | 31/03/2026 | Mondi | Realised | Switchboard - 2-SOI002970 | 1215900.07 | 1098753.98 | 117146.08 | 29/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 128
Mar-26 | 31/03/2026 | Mondi | Realised | IEP South Africa Inv: 202502235 | 4292161.74 | 3900000 | 392161.74 | 20/03/2025 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 157
Mar-26 | 31/03/2026 | Mondi | Realised | IEP South Africa Inv: 202505271 | 1650831.44 | 1500000 | 150831.44 | 19/06/2025 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 158
Mar-26 | 31/03/2026 | Mondi | Realised | Fiducia Construction CC - INV05456 | 285201.66 | 259143.65 | 26058.01 | 26/02/2026 |  | PO4612-MON-20260205 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 160
Mar-26 | 31/03/2026 | Mondi | Realised | Security Fencing IN102434 | 1155279.25 | 990815.49 | 164463.76 | 07/05/2026 |  | PO4625-MON-20260216 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 164
Mar-26 | 31/03/2026 | Mondi | Realised | Security Fencing IN102434 | 63857.01 | 58909.42 | 4947.59 | 11/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 165
Mar-26 | 31/03/2026 | Mondi | Realised | Kwickspace - DC-INV8188K | 175109.67 | 159110.43 | 15999.24 | 12/03/2026 |  | PO4619-MON-20260212 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 168
Mar-26 | 31/03/2026 | Mondi | Realised | Kwickspace - DC-INV8188K | 175109.67 | 159110.43 | 15999.24 | 15/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 169
Mar-26 | 31/03/2026 | Mondi | Realised | Richards Bay Medical - INV0027827 | 494.28 | 713.04 | -218.76 | 27/02/2026 |  | PO4647-MON-20260227 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 390
Mar-26 | 31/03/2026 | Mondi | Realised | Olea Training - OTS0570 | 2356.86 | 3400 | -1043.14 | 03/03/2026 |  | PO4650-MON-20260302 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 391
Mar-26 | 31/03/2026 | Mondi | Realised | SafetySA INV - 315INV-009346 | 21523.69 | 31050 | -9526.31 | 19/03/2026 |  | PO4624-MON-20260213 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 392
Mar-26 | 31/03/2026 | Mondi | Realised | Amkhoid - IN014375 | 4505.77 | 6500 | -1994.23 | 13/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 397
Mar-26 | 31/03/2026 | Mondi | Realised | Amkhoib IN014747 | 4505.77 | 6500 | -1994.23 | 30/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 399
Mar-26 | 31/03/2026 | Mondi | Realised | Amkhoid - IN014644 | 13344 | 19250 | -5906 | 01/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 407
Mar-26 | 31/03/2026 | Mondi | Realised | Amkhoib IN014747 | 35352.93 | 51000 | -15647.07 | 30/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 408
Mar-26 | 31/03/2026 | Mondi | Realised | L&B Consulting INV-1964 | 10834.63 | 15630 | -4795.37 | 08/05/2025 |  | PO3801-MONDI-20240411 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 426
Mar-26 | 31/03/2026 | Mondi | Realised | Okusha Engineering Inv EE15 | 71329.73 | 102900 | -31570.27 | 02/04/2026 |  | PO3816-MONDI-20250422 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 427
Mar-26 | 31/03/2026 | Mondi | Realised | RSLP Inv0011533 | 1663.67 | 2400 | -736.33 | 08/05/2025 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 428
Mar-26 | 31/03/2026 | Mondi | Realised | Test a Relay - OEINV0001195 | 116678.52 | 168320 | -51641.48 | 02/04/2026 |  | PO4362-MON-20251010 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 431
Mar-26 | 31/03/2026 | Mondi | Realised | L&B Consulting INV-2233 | 48350.33 | 69750 | -21399.67 | 26/02/2026 |  | PO4622-MON-20260213 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 434
Mar-26 | 31/03/2026 | Mondi | Realised | Payroll | 396504.8 | 242685.6 | 153819.2 | 28/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 457
Mar-26 | 31/03/2026 | Mondi | Realised | Payroll | 141967.06 | 100079.51 | 41887.55 | 26/03/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 458
Mar-26 | 31/03/2026 | Mondi | Realised | Expense Claims | 35069.14 | 81634.15 | -46565.01 | 28/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 469
Mar-26 | 31/03/2026 | Mondi | Realised | Fedgroup: SPVL000526 | 27873.97 | 80000 | -52126.03 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 514
Mar-26 | 31/03/2026 | Mondi | Realised | Fedgroup: SPVL000526 | 12212.18 | 35049.7 | -22837.52 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 515
Mar-26 | 31/03/2026 | Mondi | Realised | Fedgroup: SPVL000526 | 57114.3 | 163921.52 | -106807.22 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 516
Mar-26 | 31/03/2026 | Mondi | Realised | Fedgroup: SPVL000526 | 63876.42 | 183329.22 | -119452.8 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 517
Mar-26 | 31/03/2026 | Pimville | Realised | Sunspot Investments E027 | 0 | 2314.29 | -2314.29 | 27/03/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 132
Mar-26 | 31/03/2026 | Pimville | Realised | Matriarch -INV-6901 | 178695.31 | 42501.33 | 136193.99 | 07/05/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 141
Mar-26 | 31/03/2026 | Pimville | Realised | Expense Claim | 0 | 72.27 | -72.27 | 03/04/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 159
Mar-26 | 31/03/2026 | PnP Bethal | Realised | MSA Energy - INV0003752 | 79216.69 | 59040 | 20176.69 | 29/05/2026 |  | PO4660-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 6
Mar-26 | 31/03/2026 | PnP Bethal | Realised | MSA Energy - INV0003693 | 1049272.31 | 782020 | 267252.31 | 14/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 7
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts Inv: INV1246410 | 248963.41 | 194970 | 53993.41 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 14
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Schletter Inv: INV002732 | 186004 | 74923.5 | 111080.5 | 30/04/2026 |  | PO4641-PNPB-20260224 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 21
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Schletter - INV002767 | 24227.55 | 9759 | 14468.55 | 30/04/2026 |  | PO4698-PNPB-20260323 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 22
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Warehouse | 12414.91 | 5000.8 | 7414.11 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 25
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Warehouse | 46472.51 | 52000 | -5527.49 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 29
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Warehouse | 46472.51 | 52000 | -5527.49 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 30
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Joburg Storeroom | 12199.03 | 13650 | -1450.97 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 31
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Joburg Storeroom | 12199.03 | 13650 | -1450.97 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 32
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Ziegler - W00213967 | 1995.99 | 2233.4 | -237.41 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 33
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Joburg Storeroom | 10979.13 | 12285 | -1305.87 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 34
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Joburg Storeroom | 11589.08 | 12967.5 | -1378.42 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 35
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_001 | 13089.85 | 14646.78 | -1556.92 | 12/03/2026 |  | PO4654-PNPB-20260304'- RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 40
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_002 | 19634.78 | 21970.16 | -2335.38 | 19/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 41
Mar-26 | 31/03/2026 | PnP Bethal | Realised | AccuEnergy -ASAI-007607 | 43477.75 | 32125 | 11352.75 | 30/04/2026 |  | PO4663-PNPB-20260309 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 53
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts - INV1248884 | 6117.34 | 4520 | 1597.34 | 30/04/2026 |  | PO4671-PNPB-20260310 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 56
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Accuenergy - ASAI-007778 | 4537.25 | 3352.5 | 1184.75 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 59
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Switchboard 2-SOI003001 | 216987.62 | 144759.82 | 72227.8 | 29/04/2026 |  | PO4653-PNPB-20260304 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 62
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Switchboard - 2-SOI002991 | 43740.76 | 29180.95 | 14559.81 | 29/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 64
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Switchboard - 2-SOI002992 | 11176.08 | 7455.94 | 3720.14 | 29/04/2026 |  | PO4694-PNPB-20260320 - RV Apporved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 65
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_001 | 23223.79 | 15493.38 | 7730.41 | 12/03/2026 |  | PO4654-PNPB-20260304'- RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 67
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_002 | 34835.68 | 23240.07 | 11595.61 | 19/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 68
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts Inv: INV1246410 | 129616.45 | 83080 | 46536.45 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 79
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts Inv: INV1246410 | 450568.51 | 288800 | 161768.51 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 81
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts- INV1246570 | 23558.12 | 15100 | 8458.12 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 82
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Onvlee Engineering - ONV1833 | 74616.03 | 64599.76 | 10016.27 | 30/04/2026 |  | PO4719-PNPB-20260331 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 88
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Mahikeng Builders Express | 13543.18 | 11898.6 | 1644.58 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 91
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Plumbridge QUO226 | 5658.97 | 4899.32 | 759.65 | 20/04/2026 |  | PO4703-PNPB-20260324 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 95
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Chabo & Joubert - INV-1391 | 23193.73 | 20080.26 | 3113.47 | 02/04/2026 |  | PO4702-PNPB-20260324 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 99
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Chabo & Joubert - INV-1391 | 23193.73 | 20080.26 | 3113.47 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 100
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts Inv: INV1249516 | 34236.41 | 29640.6 | 4595.81 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 104
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Herholdts Inv: INV1249516 | 13860.61 | 12000 | 1860.61 | 30/04/2026 |  | PO4661-PNPB-20260306 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 105
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Storeroom | 1024.39 | 900 | 124.39 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 106
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Storeroom | 297.07 | 261 | 36.07 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 107
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Storeroom | 9123.94 | 8016 | 1107.94 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 108
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Storeroom | 8195.16 | 7200 | 995.16 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 109
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Allocated from Ziegler Storeroom | 16617.96 | 14600 | 2017.96 | 31/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 110
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_001 | 37075.56 | 52920 | -15844.44 | 12/03/2026 |  | PO4654-PNPB-20260304'- RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 114
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_002 | 55613.33 | 79380 | -23766.67 | 19/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 115
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_001 | 5468.57 | 3695 | 1773.57 | 12/03/2026 |  | PO4654-PNPB-20260304'- RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 130
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_002 | 8202.85 | 5542.5 | 2660.35 | 19/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 131
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Okusha - EE24 | 94330.3 | 79700 | 14630.3 | 30/06/2026 |  | PO4645-PNPB-20260226 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 144
Mar-26 | 31/03/2026 | PnP Bethal | Realised | LPS - IN307786 | 5326.05 | 4500 | 826.05 | 07/05/2026 |  | PO4669-PNPB-20260310 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 147
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Expense Claim | 1643.16 | 4415.66 | -2772.5 | 03/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 160
Mar-26 | 31/03/2026 | PnP Bethal | Realised | Ziegler T00037720 | 0 | 780 | -780 | 27/03/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 172
Mar-26 | 31/03/2026 | PnP Bethal | Realised | COSMIC SUN - CS_BET_009 | 0 | 3950 | -3950 | 02/04/2026 |  | PO4706-PNPB-20260325 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 173
Mar-26 | 31/03/2026 | PnP Bethal | Realised | ABL Transport - Inv 0365 | 0 | 9800 | -9800 | 02/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 174
Mar-26 | 31/03/2026 | Pretoria North | Realised | Sunspot E027 | 0 | 2314.3 | -2314.3 | 27/03/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 130
Mar-26 | 31/03/2026 | Pretoria North | Realised | Expense Claim | 0 | 653.4 | -653.4 | 03/04/2026 |  |  | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 157
Mar-26 | 31/03/2026 | Randfontein | Realised | Accuenergy - ASAI-007629 | 0 | 95 | -95 | 30/04/2026 |  | PO4667-DRS-20260309 | Randfontein_Tracker.xlsx | Expenditure Breakdown | 51
Mar-26 | 31/03/2026 | Randfontein | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 128
Mar-26 | 31/03/2026 | Randfontein | Realised | Expense Claim | 274.49 | 1043.02 | -768.53 | 03/04/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 155
Mar-26 | 31/03/2026 | Red Rocket | Realised | Expense Claim | 5093.37 | 0 | 5093.37 | 09/04/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 203
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0192 | 12407.4 | 9956.79 | 2450.61 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 36
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0193 | 12407.39 | 9956.78 | 2450.61 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 37
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0194 | 6203.7 | 4978.39 | 1225.31 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 38
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0195 | 6203.7 | 4978.39 | 1225.31 | 23/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 39
Mar-26 | 31/03/2026 | Riverside Mall | Realised | DSV Inv: 180168193 | 238.93 | 422.33 | -183.4 | 30/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 49
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Accuenergy - ASAI-007713 | 282.89 | 500 | -217.11 | 30/04/2026 |  | PO4686-RSM-20260318 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 50
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0192 | 13647.5 | 6882.32 | 6765.18 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 63
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0193 | 13647.5 | 6882.32 | 6765.18 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 64
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0194 | 6823.75 | 3441.16 | 3382.59 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 65
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0195 | 6823.75 | 3441.16 | 3382.59 | 23/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 66
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Coastal Aircon - EME22026 | 35701.56 | 18988 | 16713.56 | 12/03/2026 |  | PO4653-RSM-20260303 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 81
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Hisafe - 00360 | 0 | -67474.56 | 67474.56 | 28/02/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 85
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Acscend Inv-5020 | 91439.01 | 33715.45 | 57723.56 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 87
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0192 | 16358.33 | 19425 | -3066.67 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 98
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0193 | 16358.33 | 19425 | -3066.67 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 99
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0194 | 8179.17 | 9712.5 | -1533.33 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 100
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0195 | 8179.17 | 9712.5 | -1533.33 | 23/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 101
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0192 | 3818.47 | 4416.62 | -598.15 | 30/03/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 114
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0193 | 3818.47 | 4416.62 | -598.15 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 115
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0194 | 1909.24 | 2208.31 | -299.07 | 16/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 116
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Leading Edge - INV-0195 | 1909.24 | 2208.31 | -299.07 | 23/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 117
Mar-26 | 31/03/2026 | Riverside Mall | Realised | HappySolar - INV-0360 | 8948.07 | 6700 | 2248.07 | 09/04/2026 |  | PO4672-7AP/TPS-20260310 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 126
Mar-26 | 31/03/2026 | Riverside Mall | Realised | Expense Claim | 0 | 0 | 0 | 07/04/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 142
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Allocated to De Drift | 0 | -54600 | 54600 | 31/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 33
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Allocated to De Drift | 0 | -47775 | 47775 | 31/03/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 34
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 18999.41 | 16966.52 | 2032.89 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 43
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 33356.24 | 16966.52 | 16389.72 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 44
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 16678.12 | 8483.26 | 8194.86 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 45
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 64141.17 | 23150.88 | 40990.29 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 82
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 64141.17 | 23150.88 | 40990.29 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 83
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 32070.59 | 11575.44 | 20495.15 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 84
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Toys 4 Boys Inv12692 | 0 | 20100 | -20100 | 30/03/2026 |  | PO4678-DSHC-20260316 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 99
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 120469.59 | 110529.12 | 9940.47 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 118
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 120469.59 | 110529.12 | 9940.47 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 119
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 60234.8 | 55264.56 | 4970.24 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 120
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 13615.86 | 19654.4 | -6038.54 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 142
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 13615.86 | 19654.4 | -6038.54 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 143
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 6807.93 | 9827.2 | -3019.27 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 144
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Sunspot - E045 | 31175.18 | 29014 | 2161.18 | 02/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 150
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Arefa Isago Group | 23120.71 | 19660 | 3460.71 | 05/03/2026 |  | PO4651-DSHC-20260302 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 154
Mar-26 | 31/03/2026 | Seshego Circle | Realised | Expense Claim | 1165.38 | 4099.6 | -2934.22 | 03/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 172
Mar-26 | 31/03/2026 | Seshego Circle | Realised | JA Electrical Inv 1183 | 0 | 12358.2 | -12358.2 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 179
Mar-26 | 31/03/2026 | Seshego Circle | Realised | DSV Inv:180168193 | 0 | 221.68 | -221.68 | 30/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 198
Mar-26 | 31/03/2026 | Sibasa | Realised | MSA Energy:INV0003686 | 0 | 68870.35 | -68870.35 | 07/05/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 14
Mar-26 | 31/03/2026 | Sibasa | Realised | Sunspot Investments E027 | 0 | 2314.28 | -2314.28 | 27/03/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 129
Mar-26 | 31/03/2026 | Sibasa | Realised | Expense Claim | 0 | 4614.42 | -4614.42 | 03/04/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 155
Mar-26 | 31/03/2026 | Sibasa | Realised | Cosmic Sun: CS_SRS_014 | 0 | 8000 | -8000 | 12/03/2026 |  | PO4670-DSS-20260310 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 162
Mar-26 | 31/03/2026 | Sibasa | Realised | Cosmic Sun: CS_SRS_015 | 0 | 6800 | -6800 | 31/03/2026 |  | PO4680-DSS-20260317 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 163
Mar-26 | 31/03/2026 | Steelpark | Realised | MSA Energy - INV0003700 | 0 | 68870 | -68870 | 14/05/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 15
Mar-26 | 31/03/2026 | Steelpark | Realised | Leading Edge Energy INV-0197 | 15134.54 | 17134.11 | -1999.58 | 16/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 41
Mar-26 | 31/03/2026 | Steelpark | Realised | Leading Edge Energy INV-0197 | 28803.08 | 8389.32 | 20413.75 | 16/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 69
Mar-26 | 31/03/2026 | Steelpark | Realised | Leading Edge Energy INV-0197 | 31852.94 | 29807.05 | 2045.89 | 16/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 101
Mar-26 | 31/03/2026 | Steelpark | Realised | Leading Edge Energy INV-0197 | 17365.28 | 12461.11 | 4904.17 | 16/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 117
Mar-26 | 31/03/2026 | Steelpark | Realised | Sunspot Inv: E044 | 10896.1 | 8750 | 2146.1 | 21/05/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 126
Mar-26 | 31/03/2026 | Steelpark | Realised | Expense Claims | 0 | 0 | 0 | 07/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 144
Mar-26 | 31/03/2026 | SupaStore | Realised | Greenway: INV0001650 | 0 | 5263.03 | -5263.03 |  |  | PO4726-SSS-20260331 | SupaStore_Tracker.xlsx | Expenditure Breakdown | 158
Mar-26 | 31/03/2026 | Superspar Ph2 | Unrealised |  | 981.92 | 0 | 981.92 | 09/04/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 141
Mar-26 | 31/03/2026 | The Avenues | Realised | Sunspot E026 | 0 | -917.9 | 917.9 | 31/03/2026 |  |  | The Avenues_Tracker.xlsx | Expenditure Breakdown | 200
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_005 | 16137.53 | 13417.28 | 2720.25 | 19/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 36
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_006 | 16137.53 | 13417.28 | 2720.25 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 37
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_007 | 8068.76 | 6708.64 | 1360.13 | 25/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 38
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_005 | 21328.62 | 7950 | 13378.62 | 19/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 62
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_006 | 21328.62 | 7950 | 13378.62 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 63
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_007 | 10664.31 | 3975 | 6689.31 | 25/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 64
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_005 | 24142.22 | 28665 | -4522.78 | 19/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 94
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_006 | 24142.22 | 28665 | -4522.78 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 95
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_007 | 12071.11 | 14332.5 | -2261.39 | 25/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 96
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_005 | 6693.14 | 1880 | 4813.14 | 19/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 110
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_006 | 6693.14 | 1880 | 4813.14 | 30/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 111
Mar-26 | 31/03/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_007 | 3346.57 | 940 | 2406.57 | 25/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 112
Mar-26 | 31/03/2026 | Topsteel | Realised | Happy Solar INV-0357 | 8209.73 | 6700 | 1509.73 | 19/03/2026 |  | PO4672-7AP/TPS-20260310 - RV Approved | Topsteel_Tracker.xlsx | Expenditure Breakdown | 122
Mar-26 | 31/03/2026 | Topsteel | Realised | Matriarch -INV-6901 | 26870.69 | 29322.95 | -2452.26 | 07/05/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 128
Mar-26 | 31/03/2026 | Topsteel | Realised | Expense Claim | 784.38 | 499.95 | 284.43 | 03/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 138
Mar-26 | 31/03/2026 | Topsteel | Realised | Uber: C/C TV 040301 | 0 | 96 | -96 | 04/03/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 148
Mar-26 | 31/03/2026 | Tsakana Corner | Realised | MSA Energy Inv: INV0003730 | 0 | 2319.37 | -2319.37 | 21/05/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 12
Mar-26 | 31/03/2026 | Tsakana Corner | Realised | Sunspot Investments E027 | 0 | 2314.3 | -2314.3 | 27/03/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 131
Mar-26 | 31/03/2026 | Tsakana Corner | Realised | Expense Claim | 0 | 733.1 | -733.1 | 03/04/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 158
Mar-26 | 31/03/2026 | Umzimkhulu | Realised | Sunspot E027 | 0 | 2314.3 | -2314.3 | 27/03/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 129
Mar-26 | 31/03/2026 | Umzimkhulu | Realised | Expense Claim | 0 | 3264.91 | -3264.91 | 03/04/2026 |  |  | Umzimkhulu_Tracker.xlsx | Expenditure Breakdown | 155
Mar-26 | 31/03/2026 | Upper_East_Side_Hotel | Realised | Allocated to Gillwell Mall | 48475.19 | -54000 | 102475.19 | 31/03/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 48
Mar-26 | 31/03/2026 | Upper_East_Side_Hotel | Realised | Expense Claim | 1153.14 | 217.8 | 935.34 | 03/04/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 152
Mar-26 | 31/03/2026 | Waterside | Realised | MG INV-1550 | 0 | 3985 | -3985 | 16/04/2026 |  | PO4536-WSD-20251212 - RV Approved | Waterside_Tracker.xlsx | Expenditure Breakdown | 148
Mar-26 | 31/03/2026 | Westway BESS | Realised | Transfire - IN-19701 | 0 | 5193.45 | -5193.45 | 25/03/2026 |  | PO4675-WWB-20260312 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 93
Mar-26 | 31/03/2026 | Westway BESS | Realised | Matriarch -INV-6901 | 0 | 10298.23 | -10298.23 | 07/05/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 148
Mar-26 | 31/03/2026 | Westway BESS | Realised | Expense Claim | 327.39 | 247.25 | 80.14 | 03/04/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 156
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | MSA Invoice - INV0003835 | 524210.15 | 323290.5 | 200919.65 | 19/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 6
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | AccuEnergy - ASAI-007987 | 20957.86 | 20004 | 953.86 | 29/05/2026 |  | PO4785-261BS-20260424 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 45
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | Barrier Projects - Inv 622 | 72560.98 | 33215 | 39345.98 | 07/05/2026 |  | PO4780-261BS-20260423 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 79
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | Barrier Projects - Inv 622 | 31097.56 | 14235 | 16862.56 | 31/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 80
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | L&B Inv: 2040 | 15127.12 | 12100 | 3027.12 | 04/09/2025 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 119
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | Rubicon INVRED-0144561 | 62508.78 | 50000 | 12508.78 | 30/05/2026 |  | PO4787-261BS-20260428 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 120
Apr-26 | 30/04/2026 | 261 Bree Street | Realised | Expense Claim | 0 | 0 | 0 | 07/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 134
Apr-26 | 30/04/2026 | 7th Avenue Park | Realised | Expense Claim | 939.76 | 94.05 | 845.71 | 07/05/2026 |  |  | 7th Avenue Park_Tracker.xlsx | Expenditure Breakdown | 140
Apr-26 | 30/04/2026 | BMG Fluid Tech | Realised | Expense Claim | 0 | 235.62 | -235.62 | 07/05/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 176
Apr-26 | 30/04/2026 | BMG Fluid Tech | Realised | Cosmic Sun: CS_BMG_012 | 0 | 8250 | -8250 | 09/04/2026 |  | PO4709-BMGFT-20260326 - RV Approved | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 180
Apr-26 | 30/04/2026 | Chili on Top | Realised | Takealot - Ord 208552553 | 0 | 416.52 | -416.52 | 04/04/2026 |  |  | Chili on Top_Tracker.xlsx | Expenditure Breakdown | 74
Apr-26 | 30/04/2026 | China Town Adhoc | Realised | Happy Solar INV-0364 | 0 | 30900 | -30900 | 16/04/2026 |  |  | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 153
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Allocated from Ziegler Warehouse | 0 | 249390 | -249390 | 30/04/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 128
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 905.85 | -905.85 | 07/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 382
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV-0733 | 0 | 52714.32 | -52714.32 | 17/06/2026 |  | PO4779-CSPH2-20260423 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 421
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Helukabel - InvPSI0054674 | 0 | 55420 | -55420 | 29/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 427
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Helukabel - InvPSI0054675 | 0 | 14710.19 | -14710.19 | 29/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 428
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV0731 | 0 | 87500 | -87500 | 23/04/2026 |  | PO4759-CSPH2-20260420 - PV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 429
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV0731 | 0 | 47814.17 | -47814.17 | 28/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 430
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV0732 | 0 | 67657.09 | -67657.09 | 23/04/2026 |  | PO4760-CSPH2-20260420 - PV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 431
Apr-26 | 30/04/2026 | Coega Steels Ph2 | Realised | Luken Solar - INV0732 | 0 | 107342.91 | -107342.91 | 28/05/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 432
Apr-26 | 30/04/2026 | Corporate Park | Realised | Toys 4Boys - 12748 | 0 | 1750 | -1750 | 16/04/2026 |  | PO4721-DCP-20260331 - RV Approved | Corporate Park_Tracker.xlsx | Expenditure Breakdown | 177
Apr-26 | 30/04/2026 | De Drift | Realised | Schletter - INV002844 | 0 | 6066 | -6066 | 30/05/2026 |  | PO4786-DDSC-20260428 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 22
Apr-26 | 30/04/2026 | De Drift | Realised | MSA Energy - INV0003826 | 71576.74 | 127200 | -55623.26 | 15/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 29
Apr-26 | 30/04/2026 | De Drift | Realised | Allocated to PnP Bethal | -62891.62 | -54600 | -8291.62 | 30/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 32
Apr-26 | 30/04/2026 | De Drift | Realised | Allocated to PnP Bethal | -55030.17 | -47775 | -7255.17 | 30/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 33
Apr-26 | 30/04/2026 | De Drift | Realised | Rubicon INVRED-0143639 | 59153.42 | 56500 | 2653.42 | 31/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 34
Apr-26 | 30/04/2026 | De Drift | Realised | ABL Transport - 0385 | 4711.33 | 4500 | 211.33 | 29/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 35
Apr-26 | 30/04/2026 | De Drift | Realised | MSA Energy - INV0003811 | 326.6 | 300 | 26.6 | 04/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 54
Apr-26 | 30/04/2026 | De Drift | Realised | Matriarch - INV-7284 | 19972.63 | 14934 | 5038.63 | 29/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 56
Apr-26 | 30/04/2026 | De Drift | Realised | Rubicon Inv: 0143104 | 140417.11 | 105000 | 35417.11 | 30/05/2026 |  | PO4728-DDSC-20260331 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 58
Apr-26 | 30/04/2026 | De Drift | Realised | Uber | 97.63 | 73 | 24.63 | 14/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 59
Apr-26 | 30/04/2026 | De Drift | Realised | Accuenergy Inv: ASAI-007878 | 5790.91 | 4330 | 1460.91 | 29/05/2026 |  | PO4744-DDSC-20260410 - MI Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 60
Apr-26 | 30/04/2026 | De Drift | Realised | Uber | 40.12 | 30 | 10.12 | 02/04/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 61
Apr-26 | 30/04/2026 | De Drift | Realised | Expense Claim | 0 | 0 | 0 | 07/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 150
Apr-26 | 30/04/2026 | Dobsonpoint | Realised | Takealot - Ord 208552553 | 0 | 416.52 | -416.52 | 04/04/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 89
Apr-26 | 30/04/2026 | Dobsonpoint | Realised | Expense Claim | 0 | 55.94 | -55.94 | 07/05/2026 |  |  | Dobsonpoint_Tracker.xlsx | Expenditure Breakdown | 159
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Accuenergy Inv: ASAI-007319 | 0 | 7694 | -7694 | 27/03/2026 |  | PO4596-BHM-20260203 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 12
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Allocated from jHB Storeroom | 0 | 24757 | -24757 | 31/03/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 13
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Accuenergy Inv: ASAI-007296 | 0 | 7080 | -7080 | 28/02/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 14
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | DSV Inv: 180164634 | 0 | 426.65 | -426.65 | 27/03/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 15
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Cosmic Sun - CS_LEAH_001 | 30344.4 | 53596.64 | -23252.23 | 30/04/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 29
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Matthews Group Inv: 1596 | 0 | 25749 | -25749 | 06/02/2026 |  | PO4598-BHM-20260203 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 72
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Matthews Group Inv: 1596 | 0 | 25749 | -25749 | 31/03/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 73
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Expense Claim | 0 | 7340.94 | -7340.94 | 28/02/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 75
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Tier Power Solutions Inv: INV1188 | 0 | 25400 | -25400 | 09/01/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 76
Apr-26 | 30/04/2026 | FY 2026 Adhoc | Realised | Cosmic Sun - CS_LEAH_001 | 0 | 8400 | -8400 | 30/04/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 91
Apr-26 | 30/04/2026 | Gillwell | Realised | Camtech Services - INV1506 | 0 | 4570 | -4570 | 30/04/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 163
Apr-26 | 30/04/2026 | Hungry Lion_Citrusdal | Realised | DCI Electrical - INV0013 | 0 | 4375.2 | -4375.2 | 23/04/2026 |  | PO4764-HLCD-20260420 - PV Approved | Hungry Lion_Citrusdal_Tracker.xlsx | Expenditure Breakdown | 164
Apr-26 | 30/04/2026 | Klein Karoo Phase 2 | Realised | Accuenergy Inv: ASAI-007986 | 0 | 6010 | -6010 | 29/05/2026 |  | PO4765-KKM2-20260421 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 45
Apr-26 | 30/04/2026 | Klein Karoo Phase 2 | Realised | Okusha - EE26 | 81368.51 | 56870 | 24498.51 | 24/06/2026 |  | PO4747-KKM2-20260410 - MI Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 122
Apr-26 | 30/04/2026 | Klein Karoo Phase 2 | Realised | Expense Claim | 0 | 0 | 0 | 07/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 135
Apr-26 | 30/04/2026 | Kroonstad | Realised | Takealot - Ord 208552553 | 0 | 416.52 | -416.52 | 04/04/2026 |  |  | Kroonstad_Tracker.xlsx | Expenditure Breakdown | 92
Apr-26 | 30/04/2026 | Mahikeng Builders Express | Realised | JJL Steel & Construction INV26070 | 0 | 6123 | -6123 | 29/04/2026 |  | PO4583-MBE-20260127 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 106
Apr-26 | 30/04/2026 | Mahikeng Builders Express | Realised | Expense Claim | 0 | 3465 | -3465 | 07/05/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 170
Apr-26 | 30/04/2026 | Mahikeng Builders Express | Realised | ABL Transport - Invoice 0373 | 0 | 7500 | -7500 | 09/04/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 184
Apr-26 | 30/04/2026 | Mahikeng Builders Express | Realised | Evolution Coatings - INV0000168 | 0 | 650 | -650 | 16/04/2026 |  | PO4749-MBE-20260414 - PV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 185
Apr-26 | 30/04/2026 | Malvern Ph2 | Realised | Expense claim | 0 | 233.64 | -233.64 | 07/05/2026 |  |  | Malvern Ph2_Tracker.xlsx | Expenditure Breakdown | 147
Apr-26 | 30/04/2026 | Marikana Old Church | Realised | City Solar - INV0000191 | 0 | 6450 | -6450 | 29/04/2026 |  | PO4708-MAROC-20260326 - RV Approved | Marikana Old Church_Tracker.xlsx | Expenditure Breakdown | 155
Apr-26 | 30/04/2026 | Marikana Shoprite | Realised | City Solar - INV0000190 | 0 | 7450 | -7450 | 29/04/2026 |  | PO4707-MARSR-20260326 - RV Approved | Marikana Shoprite_Tracker.xlsx | Expenditure Breakdown | 160
Apr-26 | 30/04/2026 | Mayo Macs | Realised | Expense Claim | 0 | 1655.17 | -1655.17 | 07/05/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 128
Apr-26 | 30/04/2026 | Mayo Macs | Realised | Matthews - MG INV-1619 | 0 | 12814 | -12814 | 04/06/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 151
Apr-26 | 30/04/2026 | Milkwood_Square | Realised | Arccon INV-1320 | 0 | 7173.54 | -7173.54 | 09/04/2026 |  |  | Milkwood_Square_Tracker.xlsx | Expenditure Breakdown | 84
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 180550.7 | 167876.24 | 12674.46 | 30/01/2026 |  | PO4520-MON-20251203 - JP Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 21
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 902753.5 | 839381.2 | 63372.29 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 22
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 631927.45 | 587566.84 | 44360.6 | 27/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 23
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 631927.45 | 587566.84 | 44360.6 | 27/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 24
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 631927.45 | 587566.84 | 44360.6 | 27/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 25
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 631927.45 | 587566.84 | 44360.6 | 27/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 26
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 15930.94 | 14812.61 | 1118.33 | 30/01/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 32
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 79654.72 | 74063.05 | 5591.67 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 33
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003864 | 223033.22 | 207376.53 | 15656.68 | 27/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 34
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 307710.73 | 278064.29 | 29646.44 | 29/01/2026 |  | PO4520-MON-20251203 - JP Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 103
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 1538553.66 | 1390321.47 | 148232.19 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 104
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 4307950.26 | 3892900.12 | 415050.14 | 29/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 105
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 6039.67 | 5457.77 | 581.89 | 29/01/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 107
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 30198.33 | 27288.87 | 2909.46 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 108
Apr-26 | 30/04/2026 | Mondi | Realised | MSA Energy Inv: INV0003865 | 84555.32 | 76408.82 | 8146.5 | 29/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 109
Apr-26 | 30/04/2026 | Mondi | Realised | ABB South Africa - 2680013491 | 254724.58 | 230183.1 | 24541.48 | 28/05/2026 |  | PO4633-MON-20260219 -RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 124
Apr-26 | 30/04/2026 | Mondi | Realised | Switchboard - 2-SOI003052 | 1215900.04 | 1098753.96 | 117146.08 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 129
Apr-26 | 30/04/2026 | Mondi | Realised | Fiducia Construction CC -INV05476 | 120389.29 | 111061.62 | 9327.67 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 161
Apr-26 | 30/04/2026 | Mondi | Realised | Fiducia Construction CC - INV05475 | 36899.66 | 200353.55 | -163453.89 | 14/05/2026 |  | PO4725-MON-20260331 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 162
Apr-26 | 30/04/2026 | Mondi | Realised | Encore Maintenance Inv: INV0007059 | 50876.9 | 46935 | 3941.9 | 23/04/2026 |  | PO4756-MON-20260415 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 201
Apr-26 | 30/04/2026 | Mondi | Realised | Onvlee Engineering - 01052389 | 179192.88 | 165309.16 | 13883.73 | 23/04/2026 |  | PO4717-MON-20260330 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 204
Apr-26 | 30/04/2026 | Mondi | Realised | Onvlee Engineering - 01052389 | 397124.82 | 366355.89 | 30768.92 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 205
Apr-26 | 30/04/2026 | Mondi | Realised | Logivest INV-10661 | 1736406.98 | 1605653.4 | 130753.58 | 16/04/2026 |  | PO4730-MON-20260331 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 211
Apr-26 | 30/04/2026 | Mondi | Realised | GIG Network Solutions PI7968 | 72216.26 | 66621 | 5595.26 | 16/04/2026 |  | PO4727-MON-20260331 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 217
Apr-26 | 30/04/2026 | Mondi | Realised | SAK Services - SS5968 | 170572.85 | 157357 | 13215.85 | 04/06/2026 |  | PO4753-MON-20260415 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 227
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 130061.86 | 116808.85 | 13253.02 | 07/05/2026 |  | PO4768-MON-20260421 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 234
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 130061.86 | 116808.85 | 13253.02 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 235
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 635766.39 | 570983.19 | 64783.2 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 244
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 635766.39 | 570983.19 | 64783.2 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 245
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 146279.27 | 131373.73 | 14905.54 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 254
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 146279.27 | 131373.73 | 14905.54 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 255
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 12336.62 | 11079.55 | 1257.07 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 264
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 12336.62 | 11079.55 | 1257.07 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 265
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 658692.83 | 1017174.01 | -358481.18 | 07/05/2026 |  | PO4768-MON-20260421 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 273
Apr-26 | 30/04/2026 | Mondi | Realised | JA Electrical - INV1199 | 658692.83 | 1017174.01 | -358481.18 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 274
Apr-26 | 30/04/2026 | Mondi | Realised | Container world - D615587 | 19362.39 | 3150 | 16212.39 | 09/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 292
Apr-26 | 30/04/2026 | Mondi | Realised | Container World - D616952 | 1018.91 | 1520 | -501.09 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 293
Apr-26 | 30/04/2026 | Mondi | Realised | Container world - D615587 | 0 | 26750 | -26750 | 09/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 299
Apr-26 | 30/04/2026 | Mondi | Realised | Container world - D615587 | 8450.81 | 4050 | 4400.81 | 09/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 304
Apr-26 | 30/04/2026 | Mondi | Realised | Container World - D616952 | 621.67 | 960 | -338.33 | 09/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 305
Apr-26 | 30/04/2026 | Mondi | Realised | Container world - D615587 | 0 | 9000 | -9000 | 09/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 313
Apr-26 | 30/04/2026 | Mondi | Realised | Sanitech - RBY1682207 | 1491.69 | 2246 | -754.31 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 318
Apr-26 | 30/04/2026 | Mondi | Realised | Takealot - Ord 210833461 | 9434.8 | 14074.77 | -4639.97 | 30/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 327
Apr-26 | 30/04/2026 | Mondi | Realised | Supply Chain Optimizers - SCO05788 | 0 | 38500 | -38500 | 29/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 333
Apr-26 | 30/04/2026 | Mondi | Realised | DSV Inv: 180173212 | 228.09 | 340.26 | -112.17 | 29/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 377
Apr-26 | 30/04/2026 | Mondi | Realised | Pienaar & Sons Inv: 070-SOG32401 | 2524 | 3646 | -1122 | 30/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 393
Apr-26 | 30/04/2026 | Mondi | Realised | Cairnmead - IN038064 | 7862.97 | 12000 | -4137.03 | 28/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 416
Apr-26 | 30/04/2026 | Mondi | Realised | Cairnmead - IN038064 | 6922.64 | 10000 | -3077.36 | 28/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 417
Apr-26 | 30/04/2026 | Mondi | Realised | TJA Architects - PM0101 | 27345 | 39500.81 | -12155.81 | 30/05/2026 |  | PO4701-MON-20260323 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 442
Apr-26 | 30/04/2026 | Mondi | Realised | RB Print and Signs : IN19291 | 9556.82 | 13739.86 | -4183.04 | 16/04/2026 |  | PO4750-MON-20260414 - PV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 447
Apr-26 | 30/04/2026 | Mondi | Realised | Payroll | 159872.44 | 115300.92 | 44571.52 | 23/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 459
Apr-26 | 30/04/2026 | Mondi | Realised | Expense Claim | 6587.98 | 14935.07 | -8347.09 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 470
Apr-26 | 30/04/2026 | Mondi | Realised | 8 Flamboyant - 2026/Marius/01 | 6549.75 | 12716.66 | -6166.91 | 07/05/2026 |  | PO4697-MON-20260323 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 478
Apr-26 | 30/04/2026 | Mondi | Realised | Specialist ¦ Construction & Engineering Inv: MZAR15879-CAR | 63219.38 | 204319.37 | -141099.99 | 30/04/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 500
Apr-26 | 30/04/2026 | Mondi | Realised | Fedgroup: 1114168_260504 | 60366.37 | 179411.9 | -119045.53 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 518
Apr-26 | 30/04/2026 | Pimville | Realised | Takealot - Ord 208552553 | 0 | 416.52 | -416.52 | 04/04/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 86
Apr-26 | 30/04/2026 | Pimville | Realised | Expense Claim | 0 | 81.68 | -81.68 | 07/05/2026 |  |  | Pimville_Tracker.xlsx | Expenditure Breakdown | 160
Apr-26 | 30/04/2026 | PnP Bethal | Realised | MSA Energy - INV0003801 | 8251.74 | 6150 | 2101.74 | 04/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 8
Apr-26 | 30/04/2026 | PnP Bethal | Realised | MSA Energy - INV0003801 | 2951.84 | 2200 | 751.84 | 04/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 9
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Schletter - INV002801 | 7665.73 | 3087.8 | 4577.93 | 29/05/2026 |  | PO4720-PNPB-20260331 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 23
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Allocated from De Drift | 11763.36 | 54600 | -42836.64 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 36
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Allocated from De Drift | 10292.95 | 47775 | -37482.05 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 37
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_004 | 19348.98 | 29293.55 | -9944.57 | 28/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 42
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_003 | 24186.22 | 36616.94 | -12430.71 | 23/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 43
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Matriarch - INV-7284 | 16544.96 | 11169 | 5375.96 | 29/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 54
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Rubicon - INV0141972 | 131030.02 | 85000 | 46030.02 | 07/05/2026 |  | PO4674-PNPB-20260312 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 55
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Accuergy Inv: ASAI-007877 | 4636.56 | 3130 | 1506.56 | 29/05/2026 |  | PO4745-PNPB-20260410 - MI Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 58
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_004 | 46447.58 | 30986.76 | 15460.82 | 28/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 69
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_003 | 58059.47 | 38733.45 | 19326.02 | 23/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 70
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Onvlee Engineering Credit - ONV1833 | 0 | -64599.76 | 64599.76 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 89
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Onvlee Engineering - 1052268 | 0 | 64599.71 | -64599.71 | 30/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 90
Apr-26 | 30/04/2026 | PnP Bethal | Realised | DSV Inv: 180173212 | 1973.49 | 1715.95 | 257.54 | 29/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 92
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Onvlee Engineering - 01052337 | 4158.02 | 3826.5 | 331.52 | 04/06/2026 |  | PO4758-PNPB-20260417 - PV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 93
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Erasmus Steelworks - INV0002339 | 29082.75 | 25287.5 | 3795.25 | 30/04/2026 |  | PO4770-PNPB-20260422 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 97
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Herholdts - INV1264348 | 10971.8 | 9540 | 1431.8 | 29/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 111
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_004 | 74151.11 | 105840 | -31688.89 | 28/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 116
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_003 | 92688.89 | 132300 | -39611.11 | 23/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 117
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_004 | 10937.14 | 7390 | 3547.14 | 28/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 132
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_003 | 13671.42 | 9237.5 | 4433.92 | 23/04/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 133
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Expense Claim | 858.73 | 2061.8 | -1203.07 | 07/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 161
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_011 | 0 | 6890 | -6890 | 23/04/2026 |  | PO4739-PNPB-20260407 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 175
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_010 | 0 | 77567.52 | -77567.52 | 23/04/2026 |  | PO4752-PNPB-20260414 - PV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 176
Apr-26 | 30/04/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_012 | 0 | 3500 | -3500 | 23/04/2026 |  | PO4771-PNPB-20260422 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 177
Apr-26 | 30/04/2026 | Randfontein | Realised | Takealot - Ord 208552553 | 0 | 416.52 | -416.52 | 04/04/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 83
Apr-26 | 30/04/2026 | Randfontein | Realised | Matriarch - INV-7247 | 139101.49 | 41942.99 | 97158.5 | 28/05/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 137
Apr-26 | 30/04/2026 | Randfontein | Realised | Expense Claim | 0 | 273.24 | -273.24 | 06/07/2026 |  |  | Randfontein_Tracker.xlsx | Expenditure Breakdown | 156
Apr-26 | 30/04/2026 | Red Rocket | Realised | Opt-x Project - 15293 | 0 | 54589.5 | -54589.5 | 07/05/2026 |  |  | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 126
Apr-26 | 30/04/2026 | Riverside Mall | Realised | MSA Energy - INV0003820 | 0 | 7572.5 | -7572.5 | 14/06/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 7
Apr-26 | 30/04/2026 | Riverside Mall | Realised | Matriarch - INV-7247 | 18692.89 | 23286.96 | -4594.08 | 29/05/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 132
Apr-26 | 30/04/2026 | Riverside Mall | Realised | Expense Claim | 105.32 | 97.02 | 8.3 | 07/05/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 143
Apr-26 | 30/04/2026 | Riverside Mall | Realised | Hooper Projects - FF005 | 0 | 3500 | -3500 | 09/04/2026 |  | PO4736-RSM-20260407 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 155
Apr-26 | 30/04/2026 | Riverside Mall | Realised | Leading Edge - INV-0202 | 0 | 11087.94 | -11087.94 | 07/05/2026 |  | PO4761-RSM-20260420 - RV Approved | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 156
Apr-26 | 30/04/2026 | Seshego Circle | Realised | JA Electrical Inv 1205 | 16678.12 | 8483.26 | 8194.86 | 14/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 46
Apr-26 | 30/04/2026 | Seshego Circle | Realised | JA Electrical Inv 1205 | 32070.59 | 11575.44 | 20495.15 | 14/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 85
Apr-26 | 30/04/2026 | Seshego Circle | Realised | Shanduko - 2655 | 0 | 600 | -600 | 09/04/2026 |  | PO4696-DSHC-20260323 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 100
Apr-26 | 30/04/2026 | Seshego Circle | Realised | Accuenergy Inv: ASAI-007913 | 0 | 300 | -300 | 29/05/2026 |  | PO4755-DSHC-20260415 - PV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 105
Apr-26 | 30/04/2026 | Seshego Circle | Realised | JA Electrical Inv 1205 | 60234.8 | 55264.56 | 4970.24 | 14/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 121
Apr-26 | 30/04/2026 | Seshego Circle | Realised | JA Electrical Inv 1205 | 6807.93 | 9827.2 | -3019.27 | 14/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 145
Apr-26 | 30/04/2026 | Seshego Circle | Realised | Matriarch - INV-7247 | 487762.08 | 130354.3 | 357407.78 | 29/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 159
Apr-26 | 30/04/2026 | Seshego Circle | Realised | Expense Claim | 0 | 0 | 0 | 07/05/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 173
Apr-26 | 30/04/2026 | Seshego Circle | Realised | Toys 4 Boys Inv 12747 | 0 | 2250 | -2250 | 16/04/2026 |  | PO4715-DSHC-20260330 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 196
Apr-26 | 30/04/2026 | Seshego Circle | Realised | ABL Transport- Invoice 0371 | 0 | 10850 | -10850 | 09/04/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 197
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0204 | 9650.91 | 9600 | 50.91 | 30/04/2026 |  | PO4775-SMR-20260423 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 32
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0205 | 14476.36 | 14400 | 76.36 | 14/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 33
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | AccuEnergy - ASAI-007988 | 20283.78 | 10909 | 9374.78 | 29/05/2026 |  | PO4786-SMR-20260424 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 45
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Allocated from M5 Freeway | 232340.4 | 103902.28 | 128438.12 | 29/04/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 53
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Switchboard Credit: 2-ARI001588 | -10215.51 | -4568.36 | -5647.15 | 31/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 55
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0204 | 18448.18 | 8250 | 10198.18 | 30/04/2026 |  | PO4775-SMR-20260423 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 58
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0205 | 27672.27 | 12375 | 15297.27 | 14/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 59
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0204 | 19283.33 | 20400 | -1116.67 | 30/04/2026 |  | PO4775-SMR-20260423 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 90
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0205 | 28925 | 30600 | -1675 | 14/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 91
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0204 | 3885.57 | 11750 | -7864.43 | 30/04/2026 |  | PO4775-SMR-20260423 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 106
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0205 | 5828.35 | 17625 | -11796.65 | 14/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 107
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Expense Claim | 0 | 0 | 0 | 07/05/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 134
Apr-26 | 30/04/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0196 | 0 | 3207.6 | -3207.6 | 30/03/2026 |  | PO4704-SMR-20260324 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 148
Apr-26 | 30/04/2026 | Sibasa | Realised | Shanduka Projects - QT2681 | 0 | 2860 | -2860 | 16/04/2026 |  | PO4735-DSS-20260407 - RV Approved | Sibasa_Tracker.xlsx | Expenditure Breakdown | 92
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0198 | 6053.81 | 6853.65 | -799.83 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 42
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0199 | 6053.81 | 6853.65 | -799.83 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 43
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0200 | 3026.91 | 3426.82 | -399.92 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 44
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0201 | 3026.91 | 3426.82 | -399.92 | 30/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 45
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0198 | 11521.23 | 3355.73 | 8165.5 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 70
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0199 | 11521.23 | 3355.73 | 8165.5 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 71
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0200 | 5760.62 | 1677.86 | 4082.75 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 72
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0201 | 5760.62 | 1677.86 | 4082.75 | 30/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 73
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0198 | 12741.18 | 11922.82 | 818.36 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 102
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0199 | 12741.18 | 11922.82 | 818.36 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 103
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0200 | 6370.59 | 5961.41 | 409.18 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 104
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0201 | 6370.59 | 5961.41 | 409.18 | 30/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 105
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0198 | 6946.1 | 4984.44 | 1961.66 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 118
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0199 | 6946.1 | 4984.44 | 1961.66 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 119
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0200 | 3473.05 | 2492.22 | 980.83 | 23/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 120
Apr-26 | 30/04/2026 | Steelpark | Realised | Leading Edge Energy INV-0201 | 3473.05 | 2492.22 | 980.83 | 30/04/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 121
Apr-26 | 30/04/2026 | Steelpark | Realised | Matriarch - INV-7248 | 7471.61 | 6000 | 1471.61 | 29/05/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 129
Apr-26 | 30/04/2026 | Steelpark | Realised | Matriarch - INV-7247 | 106912.63 | 17492.26 | 89420.37 | 29/05/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 136
Apr-26 | 30/04/2026 | Steelpark | Realised | Expense Claims | 487.22 | 232.65 | 254.57 | 07/05/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 145
Apr-26 | 30/04/2026 | Steelpark | Realised | Spear REIT - 5484/202603/60963/I | 0 | 14300 | -14300 | 30/04/2026 |  | PO4722-SSP-20260331 - RV Approved | Steelpark_Tracker.xlsx | Expenditure Breakdown | 156
Apr-26 | 30/04/2026 | Superspar Ph2 | Realised | BDL Solar IN000785 | 0 | 3409.81 | -3409.81 | 30/04/2026 |  | PO4772-SSDPH2-20260422 - RV Approved | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 152
Apr-26 | 30/04/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_008 | 8068.76 | 6708.64 | 1360.13 | 23/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 39
Apr-26 | 30/04/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_008 | 10664.31 | 3975 | 6689.31 | 23/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 65
Apr-26 | 30/04/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_008 | 12071.11 | 14332.5 | -2261.39 | 23/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 97
Apr-26 | 30/04/2026 | Topsteel | Realised | Cosmic Sun: CS_TPS_008 | 3346.57 | 940 | 2406.57 | 23/04/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 113
Apr-26 | 30/04/2026 | Topsteel | Realised | Expense Claim | 2661.36 | 0 | 2661.36 | 08/05/2026 |  |  | Topsteel_Tracker.xlsx | Expenditure Breakdown | 139
Apr-26 | 30/04/2026 | Tsakana Corner | Unrealised |  | 187500 | 0 | 187500 |  |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 90
Apr-26 | 30/04/2026 | Tsakana Corner | Realised | Cosmic Sun - CS_TSK_015 | 0 | 8061.46 | -8061.46 | 16/04/2026 |  | PO4742-DTC-20260409 | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 93
Apr-26 | 30/04/2026 | Tsakana Corner | Realised | Matriarch - INV-7247 | 106117.66 | 33706.81 | 72410.85 | 29/05/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 140
Apr-26 | 30/04/2026 | Tsakana Corner | Realised | Expense Claim | 0 | 588.06 | -588.06 | 07/05/2026 |  |  | Tsakana Corner_Tracker.xlsx | Expenditure Breakdown | 159
Apr-26 | 30/04/2026 | Unitrans Brackenfell | Realised | WC Solutions- INV0504 | 276691.79 | 184043.5 | 92648.29 | 09/04/2026 |  | PO4737-UNB-20260407 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 22
Apr-26 | 30/04/2026 | Unitrans Brackenfell | Realised | Accuenergy Inv: ASAI-008001 | 3737.4 | 10882.5 | -7145.1 | 29/05/2026 |  | PO4792-UNB-20260429 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 45
Apr-26 | 30/04/2026 | Unitrans Brackenfell | Realised | Expense Claim | 0 | 826.64 | -826.64 | 07/05/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 171
Apr-26 | 30/04/2026 | Unitrans Brackenfell | Realised | Robyn Simson Inv: 230 | 0 | 28105 | -28105 | 16/04/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 185
Apr-26 | 30/04/2026 | Upper_East_Side_Hotel | Realised | Matriarch - INV-7247 | 266056.79 | 58003.72 | 208053.07 | 29/05/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 134
Apr-26 | 30/04/2026 | Upper_East_Side_Hotel | Realised | Expense Claim | 6418.99 | 108.9 | 6310.09 | 07/05/2026 |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 153
Apr-26 | 30/04/2026 | Volvo Moffet | Realised | Expense Claim | 35.33 | 24.75 | 10.58 | 07/05/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 136
Apr-26 | 30/04/2026 | Westway BESS | Realised | SIAAC - CINV019159 | 0 | 38500 | -38500 | 30/04/2026 |  | PO4729-WWB-20260331 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 95
Apr-26 | 30/04/2026 | Westway BESS | Realised | Expense Claim | 400.94 | 0 | 400.94 | 07/05/2026 |  |  | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 157
Apr-26 | 30/04/2026 | Westway BESS | Realised | BDL Solar - IN000784 | 0 | 1500 | -1500 | 30/04/2026 |  | PO4773-WWB-20260422 - RV Approved | Westway BESS_Tracker.xlsx | Expenditure Breakdown | 169
May-26 | 31/05/2026 | 12 Nourse | Realised | L&B Consulting Inv: INV-2288 | 7464.85 | 11525 | -4060.15 | 28/05/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 119
May-26 | 31/05/2026 | 261 Bree Street | Realised | MSA Invoice - INV0003961 | 1865.52 | 26461.5 | -24595.98 | 26/07/2026 |  | PO4796-261BS-20260430 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 7
May-26 | 31/05/2026 | 261 Bree Street | Realised | MSA Energy - INV-0003948 | 115853.66 | 89688.73 | 26164.93 | 19/07/2026 |  | PO4796-261BS-20260430 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 14
May-26 | 31/05/2026 | 261 Bree Street | Realised | Schletter - INV002863 | 58883.39 | 54959.5 | 3923.89 | 30/06/2026 |  | PO4778-261BS-20260423 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 21
May-26 | 31/05/2026 | 261 Bree Street | Realised | Schletter - INV002891 | 32170.27 | 30026.5 | 2143.77 | 30/06/2026 |  | PO4831-261BS-20260518 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 24
May-26 | 31/05/2026 | 261 Bree Street | Realised | Helukabel- PSI0055541 | 73735.04 | 62000 | 11735.04 | 30/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 28
May-26 | 31/05/2026 | 261 Bree Street | Realised | ABL Transport- 0398 | 5649.06 | 4750 | 899.06 | 14/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 29
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0177 | 8215.27 | 6907.8 | 1307.47 | 07/05/2026 |  | PO4804-261BS-20260506 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 32
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0178 | 12322.91 | 10361.7 | 1961.21 | 21/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 33
May-26 | 31/05/2026 | 261 Bree Street | Realised | MSA Energy - INV-0003915 | 8446.61 | 7032.41 | 1414.2 | 19/07/2026 |  | PO4796-261BS-20260430 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 44
May-26 | 31/05/2026 | 261 Bree Street | Realised | Matriarch - INV-7617 | 29899 | 22338 | 7561 | 30/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | 261 Bree Street | Realised | DSV Inv: 180177377 | 452.63 | 376.85 | 75.78 | 30/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | 261 Bree Street | Realised | Switchboard - 2-SOI003226 | 178241.14 | 98126.51 | 80114.63 | 30/06/2026 |  | PO4777-261BS-20260423 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 53
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0177 | 3564.59 | 1962.4 | 1602.19 | 07/05/2026 |  | PO4804-261BS-20260506 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 58
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0178 | 5346.88 | 2943.6 | 2403.28 | 21/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 59
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0177 | 14657.78 | 15200 | -542.22 | 07/05/2026 |  | PO4804-261BS-20260506 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 90
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0178 | 21986.67 | 22800 | -813.33 | 21/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 91
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0177 | 3418.83 | 6500 | -3081.17 | 07/05/2026 |  | PO4804-261BS-20260506 - RV Approved | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 106
May-26 | 31/05/2026 | 261 Bree Street | Realised | Photon Solar - INV-0178 | 5128.24 | 9750 | -4621.76 | 21/05/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 107
May-26 | 31/05/2026 | 261 Bree Street | Realised | Expense Claim | 239.78 | 133.65 | 106.13 | 05/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 135
May-26 | 31/05/2026 | BMG Fluid Tech | Realised | L&B Structural - INV-2305 | 0 | 7500 | -7500 | 28/05/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 148
May-26 | 31/05/2026 | BMG Fluid Tech | Realised | Expense Claim | 0 | 386.1 | -386.1 | 05/06/2026 |  |  | BMG Fluid Tech_Tracker.xlsx | Expenditure Breakdown | 177
May-26 | 31/05/2026 | China Town Adhoc | Unrealised |  | 12500 | 0 | 12500 |  |  |  | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 83
May-26 | 31/05/2026 | Coega Steels Ph2 | Realised | Schletter : INV2870 | 0 | 37000 | -37000 | 19/06/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 54
May-26 | 31/05/2026 | Coega Steels Ph2 | Realised | Schletter : INV2870 | 0 | 37000 | -37000 | 30/09/2025 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 55
May-26 | 31/05/2026 | Coega Steels Ph2 | Realised | Expense Claim | 0 | 306.9 | -306.9 | 05/06/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 383
May-26 | 31/05/2026 | Coega Steels Ph2 | Realised | Ziegler - W00216980 | 0 | 8835.8 | -8835.8 | 30/06/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 426
May-26 | 31/05/2026 | De Drift | Realised | MSA Energy - INV-00003957 | 0 | 8556 | -8556 | 25/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 7
May-26 | 31/05/2026 | De Drift | Realised | MSA Energy - INV-00003957 | 0 | 3500 | -3500 | 25/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 8
May-26 | 31/05/2026 | De Drift | Realised | Schletter - INV002898 | 0 | 912.9 | -912.9 | 30/06/2026 |  | PO4834-DDSC-20260519 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 23
May-26 | 31/05/2026 | De Drift | Realised | Helukabel - PSI0055244 | 377032.71 | 310000 | 67032.71 | 30/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 36
May-26 | 31/05/2026 | De Drift | Realised | ABL Transport - 0392 | 15233.31 | 14550 | 683.31 | 07/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 38
May-26 | 31/05/2026 | De Drift | Realised | Rubicon - INVRED-0146126 | 36120.23 | 34500 | 1620.23 | 30/06/2026 |  | PO4846-DDSC-20260522 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 39
May-26 | 31/05/2026 | De Drift | Realised | ABL Transport - 0410 | 10155.54 | 9700 | 455.54 | 04/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 40
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_003 | 72842.46 | 69575 | 3267.46 | 21/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 43
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_004 | 91053.08 | 86968.75 | 4084.33 | 14/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 44
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_005 | 36421.23 | 34787.5 | 1633.73 | 19/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 45
May-26 | 31/05/2026 | De Drift | Realised | DSV Inv: 180175712 | 0 | 387.11 | -387.11 | 30/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 57
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_003 | 57989.17 | 31700 | 26289.17 | 21/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 75
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_004 | 72486.46 | 39625 | 32861.46 | 14/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 76
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_005 | 28994.58 | 15850 | 13144.58 | 19/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 77
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_003 | 141404.44 | 186600 | -45195.56 | 21/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 107
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_004 | 176755.56 | 233250 | -56494.44 | 14/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 108
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_005 | 70702.22 | 93300 | -22597.78 | 19/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 109
May-26 | 31/05/2026 | De Drift | Realised | SJC SECURITY - INV018418 | 26542.21 | 19000 | 7542.21 | 31/05/2026 |  | PO4789-DDSC-20260428 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 117
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_003 | 27697.04 | 14870 | 12827.04 | 21/05/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 123
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_004 | 34621.3 | 18587.5 | 16033.8 | 14/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 124
May-26 | 31/05/2026 | De Drift | Realised | Cosmic Sun - CS_DDT_005 | 13848.52 | 7435 | 6413.52 | 19/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 125
May-26 | 31/05/2026 | De Drift | Realised | Expense Claim | 0 | 0 | 0 | 05/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 151
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Cosmic Sun - CS_LEAH_005 | 2179.73 | 3850 | -1670.27 | 28/05/2026 |  | PO4814-LEAH-20260511 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 33
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Allocated from Cpt Storeroom | 23810.79 | 13650 | 10160.79 | 31/05/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 35
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Allocated from Cpt Storeroom | 30954.03 | 17745 | 13209.03 | 31/05/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 36
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Cosmic Sun - CS_CSV_001 | 73539.59 | 42158 | 31381.59 | 28/05/2026 |  | PO4838-CON-20260521 | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 38
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Cosmic Sun - CS_CSV_002 | 73539.59 | 42158 | 31381.59 | 04/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 39
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | MSA Energy - INV-0003927 | 7182.3 | 7182.3 | 0 | 30/06/2026 |  | PO4818-RSC-20260513 - RV Approved | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 42
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Switchboard Inv: 2-SOI003127 | 0 | 8440.68 | -8440.68 | 30/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 59
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Matthews Group Inv: 1632 | 0 | 15347.6 | -15347.6 | 14/05/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 74
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Expense Claim | 15232.99 | 452.2 | 14780.79 | 04/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 101
May-26 | 31/05/2026 | FY 2026 Adhoc | Realised | Happysolar Inv: INV-0350 | 10500 | 21000 | -10500 | 28/05/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 121
May-26 | 31/05/2026 | Gezina Galleries | Realised | MSA Energy Credit: CN-0000400 | 0 | -68870 | 68870 | 14/05/2026 |  |  | Gezina Galleries_Tracker.xlsx | Expenditure Breakdown | 15
May-26 | 31/05/2026 | Gillwell | Realised | Rubicon Credit: CMWCRE-0008924 | 0 | -4000 | 4000 | 30/06/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 51
May-26 | 31/05/2026 | Gillwell | Realised | Allocated to Upper Eastisde | 0 | -50000 | 50000 | 31/05/2026 |  |  | Gillwell_Tracker.xlsx | Expenditure Breakdown | 54
May-26 | 31/05/2026 | IconSA | Realised | Switchboard - 2-SOI003127 | 0 | 8440.68 | -8440.68 | 30/06/2026 |  |  | IconSA_Tracker.xlsx | Expenditure Breakdown | 67
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | MSA Energy - INV-0003933 | 1674145.2 | 1310011.5 | 364133.7 | 14/07/2026 |  | PO4803-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 6
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | MSA Energy - INV-0003933 | 409836.07 | 341137.95 | 68698.12 | 14/07/2026 |  | PO4803-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 14
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Schletter Inv: INV002854 | 225639.34 | 84253 | 141386.34 | 30/06/2026 |  | PO4800-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 21
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Helukabel- PSI0055868 | 306014.46 | 279000 | 27014.46 | 11/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 28
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | ABL Transport - 0393 | 12284.45 | 11200 | 1084.45 | 07/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 29
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Ziegler I00005706 | 7692.45 | 7013.37 | 679.08 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 30
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_001 | 24974.73 | 22770 | 2204.73 | 07/05/2026 |  | PO4798-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 32
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_002 | 37462.09 | 34155 | 3307.09 | 14/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 33
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Matriarch - INV-7566 | 0 | 22338 | -22338 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | DSV Inv: 1801765542 | 0 | 607.11 | -607.11 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Switchboard - 2-SOI003224 | 485714.04 | 165178.59 | 320535.45 | 30/06/2026 |  | PO4762-KKM2-20260420 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 53
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_001 | 72925.36 | 24800 | 48125.36 | 07/05/2026 |  | PO4798-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 58
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_002 | 109388.04 | 37200 | 72188.04 | 14/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 59
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_001 | 48100 | 64750 | -16650 | 07/05/2026 |  | PO4798-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 90
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_002 | 72150 | 97125 | -24975 | 14/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 91
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_001 | 8549.5 | 7435 | 1114.5 | 07/05/2026 |  | PO4798-KKM2-20260504 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 106
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Cosmic Sun - CS_KKM2_002 | 12824.24 | 11152.5 | 1671.74 | 14/05/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 107
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Rubicon - INVRED-0145411 | 319772.27 | 210000 | 109772.27 | 30/06/2026 |  | PO4788-KKM2-20260428 - RV Approved | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 120
May-26 | 31/05/2026 | Klein Karoo Phase 2 | Realised | Expense Claim | 5780.83 | 2890.35 | 2890.48 | 05/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 136
May-26 | 31/05/2026 | Life Changers | Realised | Matriarch - INV-7569 | 14899.04 | 11169 | 3730.04 | 30/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Life Changers | Realised | Accuenergy Inv: ASAI-008263 | 2747.96 | 2060 | 687.96 | 30/06/2026 |  | PO4850-LCHR-20260529 - RV Approved | Life Changers_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Life Changers | Realised | CBB - 5881 | 17983.39 | 18900 | -916.61 | 28/05/2026 |  | PO4841-LCHR-20260522 - RV Approved | Life Changers_Tracker.xlsm | Expenditure Breakdown | 53
May-26 | 31/05/2026 | Life Changers | Realised | WEG - 94417629 | 319833.72 | 276279 | 43554.72 | 14/05/2026 |  | PO4975-LCHR-20260429 - RV Approved | Life Changers_Tracker.xlsm | Expenditure Breakdown | 71
May-26 | 31/05/2026 | Life Changers | Realised | WEG - 94417855 | 68680.92 | 59328 | 9352.92 | 21/05/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 72
May-26 | 31/05/2026 | Life Changers | Realised | Ask Fritz - 2605_010 | 62499.75 | 36675 | 25824.75 | 04/06/2026 |  | PO4807-LCHR-20260506 - RV Approved | Life Changers_Tracker.xlsm | Expenditure Breakdown | 81
May-26 | 31/05/2026 | Life Changers | Realised | Ask Fritz - 2605_010 | 20833.25 | 12225 | 8608.25 | 04/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 82
May-26 | 31/05/2026 | Life Changers | Unrealised |  | 75000 | 0 | 75000 | 31/05/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 91
May-26 | 31/05/2026 | Life Changers | Realised | Expense Claim | 0 | 0 | 0 | 07/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 135
May-26 | 31/05/2026 | Mahikeng Builders Express | Realised | MSA Energy - INV-0003974 | 0 | 2301 | -2301 | 31/05/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 7
May-26 | 31/05/2026 | Mahikeng Builders Express | Realised | MSA Energy - INV-0003974 | 0 | 5500 | -5500 | 28/07/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 8
May-26 | 31/05/2026 | Mahikeng Builders Express | Realised | MSA Energy - CRN-0000403 | 0 | -2301 | 2301 | 31/05/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 9
May-26 | 31/05/2026 | Mahikeng Builders Express | Realised | IBC Solar - ZA22601361 | 0 | 22288 | -22288 | 27/05/2026 |  | PO4848-MBE-20260525 - RV Approved | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 187
May-26 | 31/05/2026 | Maynard Mall Extension | Realised | L&B Inv: INV-2288 | 9330.08 | 10600 | -1269.92 | 28/05/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 124
May-26 | 31/05/2026 | Mayo Macs | Realised | Expense Claim | 0 | 2261.82 | -2261.82 | 05/06/2026 |  |  | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 129
May-26 | 31/05/2026 | Mayo Macs | Realised | Matthews MG INV-1642 | 0 | 54356 | -54356 | 04/06/2026 |  | PO4813-MMS-20260511 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 153
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2566 | 1126318.71 | 894801.85 | 231516.86 | 26/02/2026 |  | PO4521-MON-20251203 - JP Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 38
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1350504.88 | 1072906.15 | 277598.74 | 21/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 39
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1350504.88 | 1072906.15 | 277598.74 | 18/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 40
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2566 | 1126315.05 | 894798.94 | 231516.11 | 26/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 42
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1350504.88 | 1072906.15 | 277598.74 | 21/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 43
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1350504.88 | 1072906.15 | 277598.74 | 18/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 44
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2566 | 1267104.43 | 1006648.81 | 260455.62 | 26/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1514759.16 | 1203397.66 | 311361.5 | 21/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Mondi | Realised | Schletter Inv: FIN2597 | 1514759.16 | 1203397.66 | 311361.5 | 18/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 48
May-26 | 31/05/2026 | Mondi | Realised | Schletter - INV002886 | 678183.94 | 538782 | 139401.94 | 30/06/2026 |  | PO4716-MON-20260330 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 52
May-26 | 31/05/2026 | Mondi | Realised | Schletter IVQ0215 | 541193.26 | 429950 | 111243.26 | 14/05/2026 |  | PO4790-MON-20260429 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 55
May-26 | 31/05/2026 | Mondi | Realised | NRB Piping - PI000674 | 268797.94 | 268082.1 | 715.84 | 14/05/2026 |  | PO4815-MON-20260512 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 77
May-26 | 31/05/2026 | Mondi | Realised | Switchboard - 2-SOI003212 | 1741154.47 | 1648130.98 | 93023.49 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 130
May-26 | 31/05/2026 | Mondi | Realised | Power Transformer - INV22605 | 111727.88 | 100775 | 10952.88 | 04/06/2026 |  | PO4685-MON-20260318 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 136
May-26 | 31/05/2026 | Mondi | Realised | Security Fencing IN102451 | 0 | 368536.34 | -368536.34 | 11/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 166
May-26 | 31/05/2026 | Mondi | Realised | Leomat - 13820 | 1117337.99 | 1106663.44 | 10674.55 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 187
May-26 | 31/05/2026 | Mondi | Realised | SME LIGHTING - INC01109 | 607883.84 | 562109.44 | 45774.4 | 28/05/2026 |  | PO4816-MON-20260512 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 208
May-26 | 31/05/2026 | Mondi | Realised | ML Technologies Inv: INV23259 | 354195.43 | 327524.08 | 26671.35 | 04/06/2026 |  | PO4695-MON-20260320 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 214
May-26 | 31/05/2026 | Mondi | Realised | ARB - DBN-3791745 | 319931.21 | 295840 | 24091.21 | 06/07/2026 |  | PO4724-MON-20260331 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 224
May-26 | 31/05/2026 | Mondi | Realised | Container World - D619069 | 8312.15 | 12400 | -4087.85 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 294
May-26 | 31/05/2026 | Mondi | Realised | Container world - D620368 | 1206.6 | 1800 | -593.4 | 07/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 295
May-26 | 31/05/2026 | Mondi | Realised | Container World - D620391 | 2356.23 | 3515 | -1158.77 | 07/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 296
May-26 | 31/05/2026 | Mondi | Realised | Container World - D619069 | 71725.78 | 107000 | -35274.22 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 300
May-26 | 31/05/2026 | Mondi | Realised | Container World - D619069 | 2714.85 | 4050 | -1335.15 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 306
May-26 | 31/05/2026 | Mondi | Realised | Container World - D620368 | 1910.45 | 2850 | -939.55 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 307
May-26 | 31/05/2026 | Mondi | Realised | Container World - D620391 | 482.64 | 720 | -237.36 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 308
May-26 | 31/05/2026 | Mondi | Realised | Container World - D619069 | 6033.01 | 9000 | -2966.99 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 314
May-26 | 31/05/2026 | Mondi | Realised | Sanitech - RBY1688869 | 5410.94 | 8072 | -2661.06 | 14/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 319
May-26 | 31/05/2026 | Mondi | Realised | Expense Claim | 2336.17 | 3485.08 | -1148.91 | 05/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 328
May-26 | 31/05/2026 | Mondi | Realised | Diversified Power - INV18668 | 15119.89 | 22555.74 | -7435.85 | 04/06/2026 |  | PO4819-MON-20260513 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 330
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain Optimisers - SCO05817 | 25244.79 | 37660 | -12415.21 | 11/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 334
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain Optimizers - SCO05833 | 10021.5 | 14950 | -4928.5 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 335
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain Optimizers - SCO05830 | 13875.92 | 20700 | -6824.08 | 18/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 336
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain Optimisers - SCO05872 | 78277.48 | 116773.78 | -38496.3 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 337
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain - SCO05834 | 63346.6 | 94500 | -31153.4 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 343
May-26 | 31/05/2026 | Mondi | Realised | Supply Chain - SCO05841 | 22623.78 | 33750 | -11126.22 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 344
May-26 | 31/05/2026 | Mondi | Realised | Matriarch Inv: 7608 | 253.56 | 378.26 | -124.7 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 378
May-26 | 31/05/2026 | Mondi | Realised | Matriarch Inv: 7608 | 472.15 | 704.35 | -232.2 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 379
May-26 | 31/05/2026 | Mondi | Realised | Expense Claim | 279.32 | 404 | -124.68 | 05/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 394
May-26 | 31/05/2026 | Mondi | Realised | Amkhoib - IN014956 | 4494.08 | 6500 | -2005.92 | 29/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 400
May-26 | 31/05/2026 | Mondi | Realised | Amkhoid - IN015047 | 4494.08 | 6500 | -2005.92 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 401
May-26 | 31/05/2026 | Mondi | Realised | Amkhoib - IN014956 | 57653.85 | 84150 | -26496.15 | 29/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 409
May-26 | 31/05/2026 | Mondi | Realised | Amkhoid - IN015047 | 70522.56 | 102000 | -31477.44 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 410
May-26 | 31/05/2026 | Mondi | Realised | Cairnmead - IN038536 | 12622.71 | 18256.8 | -5634.09 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 418
May-26 | 31/05/2026 | Mondi | Realised | Payroll | 112885.73 | 69362.12 | 43523.61 | 22/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 460
May-26 | 31/05/2026 | Mondi | Realised | Expense Claim | 1383.93 | 2474.3 | -1090.37 | 05/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 471
May-26 | 31/05/2026 | Mondi | Realised | 8 Flamboyant - 2026/Marius/02 | 10627.11 | 19000 | -8372.89 | 04/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 479
May-26 | 31/05/2026 | Mondi | Realised | Fedgroup: 1114168_260603 | 57659.99 | 174654.18 | -116994.19 | 19/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 519
May-26 | 31/05/2026 | Nquthu | Realised | Rubicon Credit: CMCRE-0008944 | 0 | -40000 | 40000 | 30/06/2026 |  |  | Nquthu_Tracker.xlsx | Expenditure Breakdown | 87
May-26 | 31/05/2026 | PnP Bethal | Realised | Ziegler I00005644 | 3558.94 | 5388.08 | -1829.14 | 30/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 38
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_005 | 9674.49 | 14646.78 | -4972.29 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 44
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_006 | 9674.49 | 14646.78 | -4972.29 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 45
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_007 | 4837.24 | 7323.39 | -2486.14 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 46
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_005 | 23223.79 | 15493.38 | 7730.41 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 71
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_006 | 23223.79 | 15493.38 | 7730.41 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 72
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_007 | 11611.89 | 7746.69 | 3865.2 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 73
May-26 | 31/05/2026 | PnP Bethal | Realised | Erasmus Steelworks - INV0002351 | 29082.75 | 25287.5 | 3795.25 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 98
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_005 | 37075.56 | 52920 | -15844.44 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 118
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_006 | 37075.56 | 52920 | -15844.44 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 119
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_007 | 18537.78 | 26460 | -7922.22 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 120
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_005 | 5468.57 | 3695 | 1773.57 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 134
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_006 | 5468.57 | 3695 | 1773.57 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 135
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun: CS_BET_007 | 2734.28 | 1847.5 | 886.78 | 11/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 136
May-26 | 31/05/2026 | PnP Bethal | Realised | Sunspot Inv: E044 | 18098.85 | 21500 | -3401.15 | 21/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 142
May-26 | 31/05/2026 | PnP Bethal | Realised | Arefa Isago Group - INV0000354 | 7224.62 | 6485 | 739.62 | 21/05/2026 |  | PO4812-PNPB-20260511 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 145
May-26 | 31/05/2026 | PnP Bethal | Realised | Arefa Isago Group - INV0000354 | 7224.62 | 6485 | 739.62 | 04/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 146
May-26 | 31/05/2026 | PnP Bethal | Realised | Expense Claim | 0 | 0 | 0 | 07/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 162
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_013 | 0 | 18041.72 | -18041.72 | 08/06/2026 |  | PO4817-PNPB-20260513 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 178
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_013 | 0 | 18041.72 | -18041.72 | 14/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 179
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_014 | 0 | 9312.1 | -9312.1 | 29/05/2026 |  | PO4849-PNPB-20260526 - RV Approved | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 180
May-26 | 31/05/2026 | PnP Bethal | Realised | Cosmic Sun - CS_BET_014 | 0 | 9312.1 | -9312.1 | 29/05/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 181
May-26 | 31/05/2026 | Pretoria North | Realised | Okusha Engineering - EE22 | 0 | 79700 | -79700 | 30/06/2026 |  | PO4447-DIP-Ph2-Shoprite-20251106 - RV Approved | Pretoria North_Tracker.xlsx | Expenditure Breakdown | 132
May-26 | 31/05/2026 | Red Rocket | Realised | Happy Solar - INV-0369 | 0 | 11000 | -11000 | 15/06/2026 |  | PO4740-RR-20260408 - MI Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 217
May-26 | 31/05/2026 | Red Rocket | Realised | AccuEnergy - ASAI-008149 | 0 | 6010 | -6010 | 30/06/2026 |  | PO4832-RR-20260518 - RV Approved | Red Rocket_Tracker.xlsx | Expenditure Breakdown | 218
May-26 | 31/05/2026 | Seshego Circle | Realised | Accuenergy Inv :ASAI-008139 | 0 | 2880 | -2880 | 30/06/2026 |  | PO4829-DSHC-20260515 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 53
May-26 | 31/05/2026 | Seshego Circle | Realised | Rubicon Inv: INVRED-0145187 | 0 | 40000 | -40000 | 30/06/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 60
May-26 | 31/05/2026 | Seshego Circle | Realised | Expense Claim | 1165.38 | 634.89 | 530.49 | 05/06/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 174
May-26 | 31/05/2026 | Seshego Circle | Realised | JA Electrical- 1218 | 0 | 11911.8 | -11911.8 | 04/06/2026 |  | PO4769-DSHC-20260422 - RV Approved | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 200
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | MSA Energy - INV-003914 | 657489.71 | 526932 | 130557.71 | 14/07/2026 |  | PO4797-SMR-20260430 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 6
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | MSA Energy - INV-003914 | 175000 | 136555.18 | 38444.82 | 14/07/2026 |  | PO4797-SMR-20260430 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 14
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Schletter - INV002862 | 110360 | 55635.5 | 54724.5 | 30/06/2026 |  | PO4781-SMR-20260423 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 21
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Helukabel- PSI0055537 | 47739.33 | 62000 | -14260.67 | 30/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 28
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Helukabel- PSI0055537 | 2506.97 | 3000 | -493.03 | 30/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 29
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | MSA Energy - INV-0003913 | 17170.11 | 7032.41 | 10137.7 | 11/07/2026 |  | PO4797-SMR-20260430 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 44
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Matriarch - INV-7617 | 22880.55 | 11169 | 11711.55 | 30/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | DSV Inv: 180176542 | 915.55 | 441.74 | 473.81 | 30/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Switchboard - 2-SOI003225 | 30721.77 | 13005.77 | 17716 | 30/06/2026 |  | PO4833-RSM-20260519 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 56
May-26 | 31/05/2026 | Shoprite Mini Riversdal | Realised | Expense Claim | 12763.67 | 1367.86 | 11395.81 | 05/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 135
May-26 | 31/05/2026 | Steelpark | Realised | Expense Claims | 1461.22 | 0 | 1461.22 | 07/06/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 146
May-26 | 31/05/2026 | Swellengrebel | Realised | Schletter - INV002925 | 164555.29 | 27848 | 136707.29 | 30/06/2026 |  | PO4845-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 21
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_001 | 13473.24 | 13464 | 9.24 | 28/05/2026 |  | PO4842-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 32
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_002 | 20209.87 | 20196 | 13.87 | 04/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 33
May-26 | 31/05/2026 | Swellengrebel | Realised | Matriarch - INV-7569 | 25548.56 | 22338 | 3210.56 | 30/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Swellengrebel | Realised | Switchboard - 2-SOI002960 | 288594.45 | 134235.32 | 154359.13 | 29/04/2026 |  | PO4592-SWG-20260129 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 53
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_001 | 20596.18 | 9580 | 11016.18 | 28/05/2026 |  | PO4842-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 58
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_002 | 30894.27 | 14370 | 16524.27 | 04/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 59
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 44120.2 | 38360 | 5760.2 | 28/05/2026 |  | PO4844-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 79
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 18908.66 | 16440 | 2468.66 | 07/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 80
May-26 | 31/05/2026 | Swellengrebel | Realised | Ascend Rope - INV5064 | 13961.37 | 12138.61 | 1822.75 | 28/05/2026 |  | PO4843-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 81
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 59135.56 | 51415 | 7720.56 | 28/05/2026 |  | PO4844-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 83
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 25343.81 | 22035 | 3308.81 | 07/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 84
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 4387.87 | 3815 | 572.87 | 28/05/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 85
May-26 | 31/05/2026 | Swellengrebel | Realised | Barrier Projects - INV634 | 1880.51 | 1635 | 245.51 | 07/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 86
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_001 | 30550 | 37750 | -7200 | 28/05/2026 |  | PO4842-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 90
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_002 | 45825 | 56625 | -10800 | 04/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 91
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_001 | 2478.89 | 12452.85 | -9973.96 | 28/05/2026 |  | PO4842-SWG-20260522 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 106
May-26 | 31/05/2026 | Swellengrebel | Realised | Cosmic Sun Inv: CS_SGL_002 | 3718.34 | 18679.27 | -14960.94 | 04/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 107
May-26 | 31/05/2026 | Swellengrebel | Realised | L&B Inv: 2124 | 2431.72 | 8572.5 | -6140.78 | 13/11/2025 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 119
May-26 | 31/05/2026 | Swellengrebel | Realised | Okusha Engineering - EE27 | 23833.54 | 84020 | -60186.46 | 29/08/2026 |  | PO4754-SWG-20260415 - PV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 120
May-26 | 31/05/2026 | Swellengrebel | Realised | Expense Claim | 177.38 | 121.28 | 56.1 | 05/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 135
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003964 | 820825.28 | 667306 | 153519.28 | 26/07/2026 |  | PO4810-UNB-20250507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 6
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Schletter - INV002883 | 117901.67 | 81064 | 36837.67 | 30/06/2026 |  | PO4793-UNB-20260429 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 21
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | WC Solutions - INV0506 | 280662.09 | 184043.5 | 96618.59 | 29/05/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 23
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | WC Solutions - INV0508 | 9075 | 7562.5 | 1512.5 | 04/06/2026 |  | PO4757-UNB-20260417 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 24
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | WC Solutions - INV0512 | 9075 | 7562.5 | 1512.5 | 04/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 25
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Helukabel - PSI0055768 | 87728.63 | 62000 | 25728.63 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 28
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | ABL Transport- 0398 | 6721.15 | 4750 | 1971.15 | 14/05/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 29
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1633 | 9073.24 | 6412.29 | 2660.96 | 14/05/2026 |  | PO4809-UNB-20260507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 32
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1635 | 13609.87 | 9618.43 | 3991.44 | 10/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 33
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matriarch - INV-7617 | 4944.87 | 11169 | -6224.13 | 29/05/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | DSV Inv: 180176542 | 206.62 | 524.77 | -318.15 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Switchboard - 2-SOI003124 | 33923.28 | 65600.24 | -31676.96 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 59
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1633 | 4342.39 | 8397.24 | -4054.85 | 14/05/2026 |  | PO4809-UNB-20260507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 65
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1635 | 6513.59 | 12595.86 | -6082.27 | 10/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 66
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003934 | 308738.27 | 204832.77 | 103905.5 | 17/07/2026 |  | PO4810-UNB-20250507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 77
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003934 | 2245647.43 | 1489877.44 | 755769.99 | 17/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 79
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003934 | 27774.4 | 18426.96 | 9347.44 | 17/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 81
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003934 | 1836.26 | 1218.27 | 617.99 | 17/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 82
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | MSA Energy - INV-0003934 | 6789.98 | 4504.82 | 2285.16 | 17/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 83
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Lightning Protection - IN307932 | 7305.3 | 28996.13 | -21690.83 | 21/05/2026 |  | PO4799-UNB-20260504 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 97
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Switchboard - 2-SOI003124 | 36310.59 | 144123.57 | -107812.98 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 111
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Fast Fire & Security - 111989 | 6950.67 | 27588.51 | -20637.85 | 14/05/2026 |  | PO4805-UNB-20260506 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 116
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Ask Fritz - 2605_009 | 66191.11 | 262725 | -196533.89 | 14/05/2026 |  | PO4801-UNB-20260504 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 119
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Ask Fritz - 2605_009 | 22063.7 | 87575 | -65511.3 | 18/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 120
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1633 | 22073.33 | 26409.23 | -4335.9 | 14/05/2026 |  | PO4809-UNB-20260507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 127
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1635 | 33110 | 39613.84 | -6503.85 | 10/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 128
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1633 | 286.28 | 2320.01 | -2033.73 | 14/05/2026 |  | PO4809-UNB-20260507 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 143
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Matthews Group - INV1635 | 429.42 | 3480.01 | -3050.59 | 10/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 144
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Rubicon - INVRED-0145728 | 65467.63 | 52500 | 12967.63 | 30/06/2026 |  | PO4825-UNB-20260514 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 156
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Expense Claim | 0 | 79.2 | -79.2 | 05/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 172
May-26 | 31/05/2026 | Unitrans Brackenfell | Realised | Robyn Simson Inv: 233 | 0 | 44191.4 | -44191.4 | 29/05/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 186
May-26 | 31/05/2026 | Upper_East_Side_Hotel | Realised | Allocated from Gillwell Mall | 0 | 50000 | -50000 |  |  |  | Upper_East_Side_Hotel_Tracker.xlsx | Expenditure Breakdown | 49
May-26 | 31/05/2026 | Volvo Moffet | Realised | MSA Energy - INV-0003945 | 130912.37 | 99200 | 31712.37 | 19/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 6
May-26 | 31/05/2026 | Volvo Moffet | Realised | Schletter Inv: 002884 | 22044.44 | 12159.3 | 9885.14 | 30/06/2026 |  | PO4820-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 21
May-26 | 31/05/2026 | Volvo Moffet | Realised | Rubicon - INVRED-0146047 | 8275.9 | 8450 | -174.1 | 30/06/2026 |  | PO4839-VOLGQ-20260521 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 28
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0734 | 2661.63 | 2717.62 | -55.99 | 21/05/2026 |  | PO4822-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 32
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0735 | 3992.45 | 4076.44 | -83.99 | 21/05/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 33
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0742 | 5323.26 | 5435.25 | -111.99 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 34
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0743 | 6654.08 | 6794.06 | -139.98 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 35
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0744 | 2661.63 | 2717.62 | -55.99 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 36
May-26 | 31/05/2026 | Volvo Moffet | Realised | AccuEnergy - ASAI-008132 | 0 | 8697.5 | -8697.5 | 30/06/2026 |  | PO4824-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 44
May-26 | 31/05/2026 | Volvo Moffet | Realised | DSV Inv: 180178223 | 0 | 291.61 | -291.61 | 30/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 45
May-26 | 31/05/2026 | Volvo Moffet | Realised | Switchboard Inv: 2-SOI003208 | 0 | 3992.8 | -3992.8 | 30/06/2026 |  | PO4830-VOLGQ-20260518 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 46
May-26 | 31/05/2026 | Volvo Moffet | Realised | Matriarch - INV-7566 | 0 | 11169 | -11169 | 30/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 47
May-26 | 31/05/2026 | Volvo Moffet | Realised | DSV Inv: 180178223 | 0 | 391.75 | -391.75 | 30/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 48
May-26 | 31/05/2026 | Volvo Moffet | Realised | Switchboard Inv: 2-SOI003208 | 0 | 4072.07 | -4072.07 | 30/06/2026 |  | PO4840-VOLGQ-20260522 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 49
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0734 | 1575.78 | 2032.19 | -456.42 | 21/05/2026 |  | PO4822-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 60
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0735 | 2363.66 | 3048.29 | -684.62 | 21/05/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 61
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0742 | 3151.55 | 4064.38 | -912.83 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 62
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0743 | 3939.44 | 5080.48 | -1141.04 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 63
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0744 | 1575.78 | 2032.19 | -456.42 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 64
May-26 | 31/05/2026 | Volvo Moffet | Realised | SIAAC : CINV019601 | 398532.61 | 193808.17 | 204724.44 | 24/07/2026 |  | PO4823-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 72
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0734 | 3659.38 | 4723.81 | -1064.43 | 21/05/2026 |  | PO4822-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 92
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0735 | 5489.07 | 7085.71 | -1596.64 | 21/05/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 93
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0742 | 7318.75 | 9447.61 | -2128.86 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 94
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0743 | 9148.45 | 11809.52 | -2661.07 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 95
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0744 | 3659.37 | 4723.8 | -1064.43 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 96
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0734 | 287.69 | 3322.5 | -3034.81 | 21/05/2026 |  | PO4822-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 108
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0735 | 431.54 | 4983.75 | -4552.21 | 21/05/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 109
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0742 | 575.38 | 6645 | -6069.62 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 110
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0743 | 719.23 | 8306.24 | -7587.01 | 04/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 111
May-26 | 31/05/2026 | Volvo Moffet | Realised | Luken Solar - INV-0744 | 287.69 | 3322.49 | -3034.8 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 112
May-26 | 31/05/2026 | Volvo Moffet | Realised | Expense Claim | 297.46 | 202.95 | 94.51 | 05/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 137
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 1320828.14 | 990115.7 | 330712.44 | 22/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 6
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 331707.32 | 250000 | 81707.32 | 22/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 13
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 228643.9 | 70973.5 | 157670.4 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 21
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 211025.49 | 201500 | 9525.49 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 28
Jun-26 | 30/06/2026 | 12 Nourse | Realised | Cosmic Sun - CS_12N_001 | 23292.29 | 22240.9 | 1051.39 | 10/06/2026 |  | 0 | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 32
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 34938.44 | 33361.35 | 1577.09 | 24/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 33
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 9219.79 | 7480 | 1739.79 | 22/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 44
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 32047.41 | 26000 | 6047.41 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 45
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 18488.89 | 15000 | 3488.89 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 46
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 316236.46 | 143738.71 | 172497.75 | 30/07/2026 |  | PO4860-12N-20260601 - RV Approved | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 53
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 33001.18 | 15000 | 18001.18 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 54
Jun-26 | 30/06/2026 | 12 Nourse | Realised | Cosmic Sun - CS_12N_001 | 18387.06 | 8357.45 | 10029.6 | 10/06/2026 |  | 0 | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 58
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 27580.58 | 12536.18 | 15044.4 | 24/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 59
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 38414.63 | 31500 | 6914.63 | 15/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 79
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 29878.05 | 24500 | 5378.05 | 10/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 82
Jun-26 | 30/06/2026 | 12 Nourse | Realised | Cosmic Sun - CS_12N_001 | 36400 | 43680 | -7280 | 10/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 90
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 54600 | 65520 | -10920 | 24/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 91
Jun-26 | 30/06/2026 | 12 Nourse | Realised | Cosmic Sun - CS_12N_001 | 3216.47 | 4394.5 | -1178.03 | 10/06/2026 |  | 0 | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 106
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 4824.71 | 6591.75 | -1767.04 | 24/06/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 107
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 38862.55 | 60000 | -21137.45 | 30/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 120
Jun-26 | 30/06/2026 | 12 Nourse | Planned |  | 262.5 | 236.25 | 26.25 | 07/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 134
Jun-26 | 30/06/2026 | 261 Bree Street | Realised | Photon Solar - INV-0179 | 16430.55 | 13815.6 | 2614.95 | 22/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 34
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 20538.18 | 17269.5 | 3268.68 | 26/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 35
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 8215.27 | 6907.8 | 1307.47 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 36
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 12322.91 | 10361.7 | 1961.21 | 06/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 37
Jun-26 | 30/06/2026 | 261 Bree Street | Realised | Photon Solar - INV-0179 | 7129.17 | 3924.8 | 3204.37 | 22/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 60
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 8911.47 | 4906 | 4005.47 | 26/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 3564.59 | 1962.4 | 1602.19 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 62
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 5346.88 | 2943.6 | 2403.28 | 06/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 63
Jun-26 | 30/06/2026 | 261 Bree Street | Realised | Photon Solar - INV-0179 | 29315.56 | 30400 | -1084.44 | 22/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 92
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 36644.44 | 38000 | -1355.56 | 26/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 93
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 14657.78 | 15200 | -542.22 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 94
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 21986.67 | 22800 | -813.33 | 06/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 95
Jun-26 | 30/06/2026 | 261 Bree Street | Realised | Photon Solar - INV-0179 | 6837.66 | 13000 | -6162.34 | 22/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 108
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 8547.07 | 16250 | -7702.93 | 26/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 109
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 3418.83 | 6500 | -3081.17 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 110
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 5128.24 | 9750 | -4621.76 | 06/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 13751.93 | 11000 | 2751.93 | 08/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 118
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 7501.05 | 6000 | 1501.05 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 121
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 17053.74 | 19622.18 | -2568.45 | 24/06/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 127
Jun-26 | 30/06/2026 | 261 Bree Street | Planned |  | 502.33 | 280 | 222.33 | 07/07/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 136
Jun-26 | 30/06/2026 | Boundary Terraces | Planned |  | 0 | -10499.85 | 10499.85 | 30/07/2026 |  |  | Boundary Terraces_Tracker.xlsx | Expenditure Breakdown | 58
Jun-26 | 30/06/2026 | China Town Adhoc | Planned |  | 0 | 16500 | -16500 | 08/07/2026 |  |  | China Town Adhoc_Tracker.xlsx | Expenditure Breakdown | 154
Jun-26 | 30/06/2026 | Coega Steels Ph2 | Planned |  | 0 | 700 | -700 | 07/07/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 384
Jun-26 | 30/06/2026 | Coega Steels Ph2 | Realised | PLZ-3090183 | 0 | 522105 | -522105 | 30/07/2026 |  | PO4794-CSPH2-20260429 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 418
Jun-26 | 30/06/2026 | Coega Steels Ph2 | Planned |  | 0 | 222381.68 | -222381.68 | 30/06/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 420
Jun-26 | 30/06/2026 | Coega Steels Ph2 | Planned |  | 0 | 24904 | -24904 | 30/07/2026 |  | PO4863-CSPH2-20260603 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 423
Jun-26 | 30/06/2026 | Coega Steels Ph2 | Planned |  | 0 | 2298.1 | -2298.1 | 30/07/2026 |  | PO4866-CSPH2-20260604 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 434
Jun-26 | 30/06/2026 | De Drift | Planned |  | 36421.23 | 34787.5 | 1633.73 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 46
Jun-26 | 30/06/2026 | De Drift | Planned |  | 18210.62 | 17393.75 | 816.87 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 47
Jun-26 | 30/06/2026 | De Drift | Planned |  | 0 | -40000 | 40000 | 30/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 62
Jun-26 | 30/06/2026 | De Drift | Planned |  | 0 | 40000 | -40000 | 30/07/2026 |  | PO4859-DDSC-20260601 - RV Aproved | De Drift_Tracker.xlsx | Expenditure Breakdown | 63
Jun-26 | 30/06/2026 | De Drift | Planned |  | 0 | 700 | -700 | 30/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 64
Jun-26 | 30/06/2026 | De Drift | Planned |  | 0 | 8000 | -8000 | 30/07/2026 |  | PO4861-DDSC-20260601 - RV Approved | De Drift_Tracker.xlsx | Expenditure Breakdown | 65
Jun-26 | 30/06/2026 | De Drift | Planned |  | 28994.58 | 15850 | 13144.58 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 78
Jun-26 | 30/06/2026 | De Drift | Planned |  | 14497.29 | 7925 | 6572.29 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 79
Jun-26 | 30/06/2026 | De Drift | Planned |  | 70702.22 | 93300 | -22597.78 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 110
Jun-26 | 30/06/2026 | De Drift | Planned |  | 35351.11 | 46650 | -11298.89 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | De Drift | Planned |  | 13848.52 | 7435 | 6413.52 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 126
Jun-26 | 30/06/2026 | De Drift | Planned |  | 6924.26 | 3717.5 | 3206.76 | 25/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 127
Jun-26 | 30/06/2026 | De Drift | Planned |  | 23513.38 | 20008 | 3505.38 | 26/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 133
Jun-26 | 30/06/2026 | De Drift | Planned |  | 7051.19 | 6000 | 1051.19 | 12/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 136
Jun-26 | 30/06/2026 | De Drift | Planned |  | 71710.49 | 74570.16 | -2859.67 | 12/06/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 142
Jun-26 | 30/06/2026 | De Drift | Planned |  | 6814.07 | 3500 | 3314.07 | 07/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 152
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 30344.4 | 53596.64 | -23252.23 | 16/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 30
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 30344.4 | 53596.64 | -23252.23 | 30/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 31
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 10114.8 | 17865.55 | -7750.74 | 07/07/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 32
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Realised | EBM - QU101748 | 48120 | 48120 | 0 | 11/06/2026 |  | PO4858-FEN-20260601 - JP approved | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 47
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Realised | EBM - QU101748 | 16040 | 16040 | 0 | 25/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 48
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 0 | 8400 | -8400 | 30/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 92
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 0 | 8400 | -8400 | 30/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 93
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 0 | 2800 | -2800 | 30/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 94
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Realised | Cosmic Sun Inv: CS_CSV_003 | 104583.26 | 8500 | 96083.26 | 15/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 96
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 6151.96 | 500 | 5651.96 | 07/07/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 102
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Committed | Cosmic Sun - CS_FEN_001 DC | 67000 | 67000 | 0 | 04/06/2026 |  | PO4851-FEN-20260529 - JP Approved | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 67000 | 67000 | 0 | 18/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 112
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Committed | Cosmic Sun - CS_FEN_001 AC | 95704.66 | 95704.66 | 0 | 04/06/2026 |  | PO4852-FEN-20260529 - JP Approved | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 113
Jun-26 | 30/06/2026 | FY 2026 Adhoc | Planned |  | 31901.55 | 31901.55 | 0 | 18/06/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 114
Jun-26 | 30/06/2026 | IconsSA_KZN | Realised | Thula Moya - IN05119 | 0 | 3560 | -3560 | 11/06/2026 |  |  | IconsSA_KZN_Tracker.xlsx | Expenditure Breakdown | 152
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 49949.46 | 45540 | 4409.46 | 22/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 34
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 62436.82 | 56925 | 5511.82 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 35
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 145850.72 | 49600 | 96250.72 | 22/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 60
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 182313.4 | 62000 | 120313.4 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 96200 | 129500 | -33300 | 22/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 92
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 120250 | 161875 | -41625 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 93
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 17098.99 | 14870 | 2228.99 | 22/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 108
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 21373.74 | 18587.5 | 2786.24 | 30/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 109
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 20689.11 | 13764 | 6925.11 | 10/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 118
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 24050.11 | 16000 | 8050.11 | 30/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 121
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 61261.6 | 65397.29 | -4135.69 | 26/06/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 128
Jun-26 | 30/06/2026 | Klein Karoo Phase 2 | Planned |  | 26019.59 | 13009.5 | 13010.09 | 07/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 137
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 17983.39 | 18900 | -916.61 | 18/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 54
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 11418.03 | 12000 | -581.97 | 30/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 55
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 13566.6 | 14258.09 | -691.49 | 30/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 59
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 13566.6 | 14258.09 | -691.49 | 30/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 60
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 17364.71 | 15000 | 2364.71 | 30/06/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 74
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 7219.65 | 6236.48 | 983.17 | 10/06/2026 |  | PO4873-LCHR-20260609 - RV Approved | Life Changers_Tracker.xlsm | Expenditure Breakdown | 76
Jun-26 | 30/06/2026 | Life Changers | Planned |  | 364.67 | 218.75 | 145.92 | 07/07/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 136
Jun-26 | 30/06/2026 | Mahikeng Builders Express | Realised | Emergent Energy Inv: 005020 | 0 | 11386.01 | -11386.01 | 22/06/2026 |  |  | Mahikeng Builders Express_Tracker.xlsx | Expenditure Breakdown | 148
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 478884.04 | 371851.2 | 107032.84 | 17/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 6
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 78850 | 63080 | 15770 | 17/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 13
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 113274 | 77026.32 | 36247.68 | 30/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 21
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 73965.9 | 62000 | 11965.9 | 17/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 28
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 6646.78 | 5571.49 | 1075.29 | 17/06/2026 |  | 0 | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 32
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 9970.17 | 8357.24 | 1612.93 | 24/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 33
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 18231.71 | 26000 | -7768.29 | 30/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 45
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 10518.29 | 15000 | -4481.71 | 30/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 46
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 92306.1 | 37993.77 | 54312.33 | 30/07/2026 |  | PO4869-MME-20260608 - RV Approved | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 53
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 22617.58 | 9309.54 | 13308.04 | 17/06/2026 |  | 0 | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 58
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 33926.38 | 13964.31 | 19962.07 | 24/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 59
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 39375 | 31500 | 7875 | 17/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 79
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 43750 | 35000 | 8750 | 17/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 82
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 39375 | 31500 | 7875 | 17/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 85
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 42187.5 | 33750 | 8437.5 | 10/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 88
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 13650 | 10442.25 | 3207.75 | 17/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 95
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 20475 | 15663.38 | 4811.62 | 24/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 96
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 3451.63 | 1620.5 | 1831.13 | 17/06/2026 |  | 0 | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 5177.44 | 2430.74 | 2746.7 | 24/06/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 112
Jun-26 | 30/06/2026 | Maynard Mall Extension | Planned |  | 648.15 | 437.5 | 210.65 | 07/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 140
Jun-26 | 30/06/2026 | Mayo Macs | Realised | Matthews - MG INV-1641 | 0 | 9105 | -9105 | 04/06/2026 |  | PO4857-MMS-20260601 - RV Approved | Mayo Macs_Tracker.xlsx | Expenditure Breakdown | 154
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 2527428.49 | 2365235.52 | 162192.97 | 17/02/2026 |  | PO4642-MON-20260226 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 6
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 7582285.48 | 7095706.56 | 486578.92 | 11/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 7
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 47128.72 | 44104.32 | 3024.4 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 14
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 424158.45 | 396938.88 | 27219.57 | 11/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 15
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy Inv: INV0003997 | 4970.15 | 4651.2 | 318.95 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 19
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy Inv: INV0003684 | 117598.83 | 109343.52 | 8255.31 | 07/05/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 28
Jun-26 | 30/06/2026 | Mondi | Planned |  | -117598.83 | -109343.52 | -8255.31 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 29
Jun-26 | 30/06/2026 | Mondi | Planned |  | 68191.99 | 54175 | 14016.99 | 30/07/2026 |  | PO4870-MON-20260609 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 50
Jun-26 | 30/06/2026 | Mondi | Planned |  | 294693.86 | 234119 | 60574.86 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 53
Jun-26 | 30/06/2026 | Mondi | Planned |  | 541193.26 | 429950 | 111243.26 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 56
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 471896.71 | 470640 | 1256.71 | 19/03/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 4247070.39 | 4235760 | 11310.39 | 11/08/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 62
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 188120.99 | 187620 | 500.99 | 19/03/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 64
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 1693088.87 | 1688580 | 4508.87 | 11/08/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 65
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 9565.47 | 9540 | 25.47 | 19/03/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 67
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy - DM/EC/000006/03/2026 | 86089.26 | 85860 | 229.26 | 11/08/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 68
Jun-26 | 30/06/2026 | Mondi | Planned |  | 33088.12 | 33000 | 88.12 | 29/08/2026 |  | Order Placed | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 70
Jun-26 | 30/06/2026 | Mondi | Realised | Advance Strut Inv: IN161517 | 589244.22 | 587675 | 1569.22 | 30/07/2026 |  | PO4836-MON-20260519 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 74
Jun-26 | 30/06/2026 | Mondi | Planned |  | 109236.78 | 108945.88 | 290.91 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 79
Jun-26 | 30/06/2026 | Mondi | Planned |  | 317481.94 | 316636.45 | 845.49 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 81
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy PIZO/DM/CPT/00011/10/2025 | 154143.06 | 139032.15 | 15110.91 | 29/01/2026 |  | PO4520-MON-20251203 - JP Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy PIZO/DM/CPT/00011/10/2025 | 770715.29 | 695160.73 | 75554.56 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 112
Jun-26 | 30/06/2026 | Mondi | Committed | MSA Energy PIZO/DM/CPT/00011/10/2025 | 2265558.14 | 1946450.06 | 319108.08 | 24/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 113
Jun-26 | 30/06/2026 | Mondi | Planned |  | 1030244.89 | 929248.2 | 100996.69 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 116
Jun-26 | 30/06/2026 | Mondi | Planned |  | 1030244.89 | 929248.2 | 100996.69 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 117
Jun-26 | 30/06/2026 | Mondi | Planned |  | 47995.04 | 43290 | 4705.04 | 30/07/2026 |  | PO4874-MON-20260610 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 132
Jun-26 | 30/06/2026 | Mondi | Planned |  | -47995.04 | -43290 | -4705.04 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 133
Jun-26 | 30/06/2026 | Mondi | Planned |  | 176978.43 | 159628.93 | 17349.5 | 30/07/2026 |  | PO4689-MON-20260319 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 135
Jun-26 | 30/06/2026 | Mondi | Planned |  | 111727.88 | 100775 | 10952.88 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 137
Jun-26 | 30/06/2026 | Mondi | Planned |  | 166302.97 | 150000 | 16302.97 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 139
Jun-26 | 30/06/2026 | Mondi | Planned |  | 1382539.22 | 1278432.32 | 104106.9 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 188
Jun-26 | 30/06/2026 | Mondi | Planned |  | 236130.29 | 218349.39 | 17780.9 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 215
Jun-26 | 30/06/2026 | Mondi | Planned |  | 78386.72 | 72484.1 | 5902.62 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 218
Jun-26 | 30/06/2026 | Mondi | Realised | Diversified Power Inv: INV18688 | 291616.47 | 269657.4 | 21959.08 | 11/06/2026 |  | PO4723-MON-20260331 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 220
Jun-26 | 30/06/2026 | Mondi | Realised | Diversified Power Inv: INV18688 | 291616.47 | 269657.4 | 21959.08 | 26/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 221
Jun-26 | 30/06/2026 | Mondi | Realised | Diversified Power Inv: INV18700 | 330918.57 | 306000 | 24918.57 | 30/07/2026 |  | PO4868-MON-20260606 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 222
Jun-26 | 30/06/2026 | Mondi | Planned |  | 0 | -295840 | 295840 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 225
Jun-26 | 30/06/2026 | Mondi | Planned |  | 142448.71 | 127933.5 | 14515.21 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 236
Jun-26 | 30/06/2026 | Mondi | Planned |  | 696315.57 | 625362.54 | 70953.03 | 21/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 246
Jun-26 | 30/06/2026 | Mondi | Planned |  | 756864.75 | 679741.9 | 77122.86 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 247
Jun-26 | 30/06/2026 | Mondi | Planned |  | 174141.98 | 156397.3 | 17744.69 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 257
Jun-26 | 30/06/2026 | Mondi | Planned |  | 746784.48 | 1114047.72 | -367263.25 | 21/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 275
Jun-26 | 30/06/2026 | Mondi | Planned |  | 16241.59 | 24229.09 | -7987.5 | 07/07/2026 |  | PO4782-MON-20260423 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 283
Jun-26 | 30/06/2026 | Mondi | Planned |  | 45965.79 | 68571.43 | -22605.64 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 284
Jun-26 | 30/06/2026 | Mondi | Planned |  | 11898.44 | 17750 | -5851.56 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 297
Jun-26 | 30/06/2026 | Mondi | Planned |  | 3190.79 | 4760 | -1569.21 |  |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 309
Jun-26 | 30/06/2026 | Mondi | Planned |  | 6703.34 | 10000 | -3296.66 |  |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 320
Jun-26 | 30/06/2026 | Mondi | Realised | Supply Chain Optimisers - SCO05883 | 56817.54 | 84760 | -27942.46 | 02/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 338
Jun-26 | 30/06/2026 | Mondi | Realised | Supply Chain Optimisers - SCO05887 | 22456.2 | 33500 | -11043.8 | 11/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 339
Jun-26 | 30/06/2026 | Mondi | Planned |  | 26813.37 | 40000 | -13186.63 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 346
Jun-26 | 30/06/2026 | Mondi | Planned |  | 40220.06 | 60000 | -19779.94 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 347
Jun-26 | 30/06/2026 | Mondi | Planned |  | -67033.44 | -100000 | 32966.56 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 348
Jun-26 | 30/06/2026 | Mondi | Planned |  | 8295.39 | 12375 | -4079.61 | 30/06/2026 |  | PO4865-MON-20260604 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 356
Jun-26 | 30/06/2026 | Mondi | Planned |  | 56224.09 | 83874.7 | -27650.61 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 362
Jun-26 | 30/06/2026 | Mondi | Planned |  | 35321.26 | 52692 | -17370.74 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 363
Jun-26 | 30/06/2026 | Mondi | Planned |  | 502.75 | 750 | -247.25 | 30/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 380
Jun-26 | 30/06/2026 | Mondi | Planned |  | 4494.08 | 6500 | -2005.92 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 402
Jun-26 | 30/06/2026 | Mondi | Planned |  | 70522.56 | 102000 | -31477.44 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 411
Jun-26 | 30/06/2026 | Mondi | Planned |  | 12623.26 | 18257.6 | -5634.34 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 419
Jun-26 | 30/06/2026 | Mondi | Planned |  | 69367.93 | 100330 | -30962.07 | 30/06/2026 |  | PO4847-MON-20260522 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 439
Jun-26 | 30/06/2026 | Mondi | Planned |  | 54924.63 | 79440 | -24515.37 | 30/06/2026 |  | PO4682-MON-20260318 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 440
Jun-26 | 30/06/2026 | Mondi | Planned |  | 112885.73 | 69362.12 | 43523.61 | 25/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 461
Jun-26 | 30/06/2026 | Mondi | Planned |  | 13983.04 | 25000 | -11016.96 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 472
Jun-26 | 30/06/2026 | Mondi | Planned |  | 17143.21 | 30650 | -13506.79 | 07/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 480
Jun-26 | 30/06/2026 | Mondi | Planned |  | 45464.26 | 135558.47 | -90094.21 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 520
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 4837.24 | 7323.39 | -2486.14 | 18/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 47
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 11611.89 | 7746.69 | 3865.2 | 18/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 74
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 18537.78 | 26460 | -7922.22 | 18/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 121
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 2734.28 | 1847.5 | 886.78 | 18/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 137
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 45054.35 | 51495.09 | -6440.73 | 30/06/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 152
Jun-26 | 30/06/2026 | PnP Bethal | Planned |  | 699.93 | 2000 | -1300.07 | 10/07/2026 |  |  | PnP Bethal_Tracker.xlsx | Expenditure Breakdown | 163
Jun-26 | 30/06/2026 | Riverside Mall | Planned |  | 207.31 | 157.5 | 49.81 | 07/07/2026 |  |  | Riverside Mall_Tracker.xlsx | Expenditure Breakdown | 144
Jun-26 | 30/06/2026 | Seshego Circle | Planned |  | 0 | -3737.49 | 3737.49 | 30/06/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 28
Jun-26 | 30/06/2026 | Seshego Circle | Realised | Rubicon Credit: CMWCRE-0009038 | 0 | -40000 | 40000 | 30/06/2026 |  |  | Seshego Circle_Tracker.xlsx | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Planned |  | 25441.62 | 31000 | -5558.38 | 30/07/2026 |  | PO4855-SMR-20260601 - RV Approved | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 30
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Planned |  | 2872.44 | 3500 | -627.56 | 11/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 31
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0210 | 15757.39 | 19200 | -3442.61 | 15/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 34
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 19696.74 | 24000 | -4303.26 | 11/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 35
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 7878.7 | 9600 | -1721.3 | 29/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 36
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0212 | 11818.05 | 14400 | -2581.95 | 03/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 37
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0214 | 1969.67 | 2400 | -430.33 | 02/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 38
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0213 | 1969.67 | 2400 | -430.33 | 16/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 39
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0210 | 37099.75 | 16500 | 20599.75 | 15/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 60
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 46374.69 | 20625 | 25749.69 | 11/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 18549.88 | 8250 | 10299.88 | 29/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 62
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0212 | 27824.82 | 12375 | 15449.82 | 03/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 63
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0214 | 4637.47 | 2062.5 | 2574.97 | 02/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 64
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0213 | 4637.47 | 2062.5 | 2574.97 | 16/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 65
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0210 | 38566.67 | 40800 | -2233.33 | 15/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 92
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 48208.33 | 51000 | -2791.67 | 11/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 93
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 19283.33 | 20400 | -1116.67 | 29/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 94
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0212 | 28925 | 30600 | -1675 | 03/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 95
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0214 | 4820.83 | 5100 | -279.17 | 02/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 96
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0213 | 4820.83 | 5100 | -279.17 | 16/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 97
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0210 | 8882.24 | 23500 | -14617.76 | 15/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 108
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 12491.68 | 29375 | -16883.32 | 11/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 109
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0211 | 4441.12 | 11750 | -7308.88 | 29/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 110
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0212 | 6661.68 | 17625 | -10963.32 | 03/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 111
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0214 | 1110.28 | 2937.5 | -1827.22 | 02/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 112
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Realised | Leading Edge - INV-0213 | 1110.28 | 2937.5 | -1827.22 | 16/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 113
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Planned |  | 34901.96 | 6000 | 28901.96 | 22/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 121
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Planned |  | 22508.95 | 25572.94 | -3063.99 | 22/06/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 127
Jun-26 | 30/06/2026 | Shoprite Mini Riversdal | Planned |  | 17145.94 | 1837.5 | 15308.44 | 07/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 136
Jun-26 | 30/06/2026 | Sibasa | Planned |  | 0 | -68870.35 | 68870.35 | 30/06/2026 |  |  | Sibasa_Tracker.xlsx | Expenditure Breakdown | 15
Jun-26 | 30/06/2026 | Steelpark | Planned |  | 0 | -68870 | 68870 | 30/06/2026 |  |  | Steelpark_Tracker.xlsx | Expenditure Breakdown | 16
Jun-26 | 30/06/2026 | Superspar Ph2 | Planned |  | 36632.69 | 34428 | 2204.69 | 30/06/2026 |  |  | Superspar Ph2_Tracker.xlsx | Expenditure Breakdown | 82
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 901927.57 | 795181 | 106746.57 | 08/08/2026 |  | PO4853-SWG-20260601 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 6
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 243070.59 | 206611.05 | 36459.54 | 08/08/2026 |  | PO4853-SWG-20260601 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 14
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 124085.14 | 124000 | 85.14 | 30/07/2026 |  | PO4854-SWG-20260601 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 28
Jun-26 | 30/06/2026 | Swellengrebel | Realised | ABL Transport : 0419 | 8505.84 | 8500 | 5.84 | 11/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 29
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 9834.15 | 8598.34 | 1235.81 | 08/08/2026 |  | PO4853-SWG-20260601 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 44
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 10113.4 | 8842.5 | 1270.9 | 30/07/2026 |  | PO4862-SWG-20260602 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 45
Jun-26 | 30/06/2026 | Swellengrebel | Committed | Barrier Projects - INV634 | 13961.37 | 12138.61 | 1822.75 | 07/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 82
Jun-26 | 30/06/2026 | Swellengrebel | Realised | AM Security - INV105468 | 338.41 | 1700 | -1361.59 | 11/06/2026 |  | PO4864-SWG-20260603 - RV Approved | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 102
Jun-26 | 30/06/2026 | Swellengrebel | Realised | AM Security - INV105468 | 338.41 | 1700 | -1361.59 | 25/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 103
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 0 | 9560.26 | -9560.26 | 30/06/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 124
Jun-26 | 30/06/2026 | Swellengrebel | Planned |  | 4568.65 | 3123.75 | 1444.9 | 07/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 136
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 22683.11 | 16030.72 | 6652.39 | 29/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 35
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 22615.52 | 43733.49 | -21117.97 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 60
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 22615.52 | 43733.49 | -21117.97 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 61
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 33923.28 | 65600.24 | -31676.96 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 62
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 10855.98 | 20993.1 | -10137.12 | 29/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 68
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 45218.1 | 30000 | 15218.1 | 07/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 92
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 1984.36 | 8000 | -6015.64 | 07/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 96
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 7192.35 | 28996.13 | -21803.78 | 09/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 98
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 3734.2 | 15054.5 | -11320.3 | 30/06/2026 |  | PO4872-UNB-20260609 - RV Approved | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 99
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 23832.78 | 96082.38 | -72249.6 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 112
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 23832.78 | 96082.38 | -72249.6 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 113
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 35749.18 | 144123.57 | -108374.4 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 114
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 6843.2 | 27588.51 | -20745.31 | 11/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 117
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 930.17 | 3750 | -2819.83 | 14/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 122
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 744.14 | 3000 | -2255.86 | 14/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 123
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 55183.33 | 66023.07 | -10839.74 | 29/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 130
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 7403.84 | 60000 | -52596.16 | 30/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 140
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 715.71 | 5800.02 | -5084.32 | 29/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 146
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Planned |  | 0 | 600 | -600 | 07/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 173
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Realised | Robyn Simson Inv: 234 | 0 | 4015 | -4015 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 187
Jun-26 | 30/06/2026 | Unitrans Brackenfell | Realised | Robyn Simson Inv: 233 | 0 | -4680 | 4680 | 30/06/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 188
Jun-26 | 30/06/2026 | Volvo Moffet | Realised | Luken Solar - INV-0748 | 3992.45 | 4076.44 | -83.99 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 37
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | 17413.32 | 22457 | -5043.68 | 30/07/2026 |  | PO4821-VOLGQ-20260514 - RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 55
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | -3101.63 | -4000 | 898.37 | 30/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 56
Jun-26 | 30/06/2026 | Volvo Moffet | Realised | Luken Solar - INV-0748 | 2363.66 | 3048.29 | -684.62 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 65
Jun-26 | 30/06/2026 | Volvo Moffet | Realised | Luken Solar - INV-0748 | 5489.07 | 7085.71 | -1596.64 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 97
Jun-26 | 30/06/2026 | Volvo Moffet | Realised | Luken Solar - INV-0748 | 431.54 | 4983.74 | -4552.2 | 18/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 113
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | 4888.89 | 4000 | 888.89 | 30/06/2026 |  | PO4867-VOLGQ-20260605`- RV Approved | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 120
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | 7333.33 | 6000 | 1333.33 | 30/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 123
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | 7914.59 | 9330.94 | -1416.35 | 11/06/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 129
Jun-26 | 30/06/2026 | Volvo Moffet | Planned |  | 319.71 | 218.75 | 100.96 | 07/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 138
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 46584.58 | 44481.8 | 2102.78 | 15/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 34
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 58230.73 | 55602.25 | 2628.48 | 22/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 35
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 36774.11 | 16714.91 | 20059.2 | 15/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 60
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 45967.64 | 20893.63 | 25074 | 22/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 61
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 16463.41 | 13500 | 2963.41 | 06/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 80
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 12804.88 | 10500 | 2304.88 | 01/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 83
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 72800 | 87360 | -14560 | 15/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 92
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 91000 | 109200 | -18200 | 22/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 93
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 6432.95 | 8789 | -2356.05 | 15/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 108
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 8041.19 | 10986.25 | -2945.06 | 22/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 109
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 12959.36 | 20008 | -7048.64 | 27/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 118
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 3886.25 | 6000 | -2113.75 | 27/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 121
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 40357.01 | 44439.5 | -4082.49 | 27/07/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 127
Jul-26 | 31/07/2026 | 12 Nourse | Planned |  | 262.5 | 236.25 | 26.25 | 07/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 135
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 2053.82 | 1726.95 | 326.87 | 05/08/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 38
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 891.15 | 490.6 | 400.55 | 05/08/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 64
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 891.15 | 490.6 | 400.55 | 05/08/2027 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 65
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 3664.44 | 3800 | -135.56 | 05/08/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 96
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 3664.44 | 3800 | -135.56 | 05/08/2027 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 97
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 854.71 | 1625 | -770.29 | 05/08/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 112
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 854.71 | 1625 | -770.29 | 05/08/2027 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 113
Jul-26 | 31/07/2026 | 261 Bree Street | Planned |  | 502.33 | 280 | 222.33 | 07/08/2026 |  |  | 261 Bree Street_Tracker.xlsm | Expenditure Breakdown | 137
Jul-26 | 31/07/2026 | Coega Steels Ph2 | Planned |  | 0 | 700 | -700 | 07/08/2026 |  |  | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 385
Jul-26 | 31/07/2026 | De Drift | Unrealised |  | -199760.57 | -190800 | -8960.57 | 31/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 37
Jul-26 | 31/07/2026 | De Drift | Planned |  | 18210.62 | 17393.75 | 816.87 | 18/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 48
Jul-26 | 31/07/2026 | De Drift | Planned |  | 14497.29 | 7925 | 6572.29 | 18/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 80
Jul-26 | 31/07/2026 | De Drift | Planned |  | 35351.11 | 46650 | -11298.89 | 18/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 112
Jul-26 | 31/07/2026 | De Drift | Planned |  | 6924.26 | 3717.5 | 3206.76 | 18/07/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 128
Jul-26 | 31/07/2026 | De Drift | Planned |  | 6814.07 | 3500 | 3314.07 | 07/08/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 153
Jul-26 | 31/07/2026 | FY 2026 Adhoc | Planned |  | 6151.96 | 500 | 5651.96 | 07/08/2026 |  |  | FY 2026 Adhoc_Tracker.xlsx | Expenditure Breakdown | 103
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 24974.73 | 22770 | 2204.73 | 03/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 36
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 37462.09 | 34155 | 3307.09 | 09/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 37
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 72925.36 | 24800 | 48125.36 | 03/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 62
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 109388.04 | 37200 | 72188.04 | 09/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 63
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 48100 | 64750 | -16650 | 03/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 94
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 72150 | 97125 | -24975 | 09/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 95
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 8549.5 | 7435 | 1114.5 | 03/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 110
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 12824.24 | 11152.5 | 1671.74 | 09/07/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 111
Jul-26 | 31/07/2026 | Klein Karoo Phase 2 | Planned |  | 26019.59 | 13009.5 | 13010.09 | 07/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 138
Jul-26 | 31/07/2026 | Life Changers | Planned |  | 364.67 | 218.75 | 145.92 | 07/08/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 137
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 13293.56 | 11142.98 | 2150.58 | 09/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 34
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 16616.95 | 13928.73 | 2688.22 | 20/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 35
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 6646.78 | 5571.49 | 1075.29 | 24/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 36
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 9970.17 | 8357.24 | 1612.93 | 29/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 37
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 45235.17 | 18619.08 | 26616.09 | 09/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 60
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 56543.96 | 23273.85 | 33270.11 | 20/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 61
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 22617.58 | 9309.54 | 13308.04 | 24/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 62
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 33926.38 | 13964.31 | 19962.07 | 29/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 63
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 16875 | 13500 | 3375 | 08/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 80
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 18750 | 15000 | 3750 | 08/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 83
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 16875 | 13500 | 3375 | 01/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 86
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 27300 | 20884.5 | 6415.5 | 09/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 97
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 34125 | 26105.63 | 8019.37 | 20/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 98
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 13650 | 10442.25 | 3207.75 | 24/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 99
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 20475 | 15663.38 | 4811.62 | 29/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 100
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 6903.26 | 3240.99 | 3662.27 | 09/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 113
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 8629.07 | 4051.24 | 4577.83 | 20/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 114
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 3451.63 | 1620.5 | 1831.13 | 24/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 115
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 5177.44 | 2430.74 | 2746.7 | 29/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 116
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 17610.97 | 20008 | -2397.03 | 17/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 123
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 5281.18 | 6000 | -718.82 | 17/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 126
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 15764.97 | 19960.11 | -4195.15 | 17/07/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 132
Jul-26 | 31/07/2026 | Maynard Mall Extension | Planned |  | 648.15 | 437.5 | 210.65 | 07/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 141
Jul-26 | 31/07/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 7582285.48 | 7095706.56 | 486578.92 | 03/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 8
Jul-26 | 31/07/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 967868.81 | 905757.65 | 62111.16 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 11
Jul-26 | 31/07/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 8710819.3 | 8151818.85 | 559000.45 | 11/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 12
Jul-26 | 31/07/2026 | Mondi | Planned |  | 512249.17 | 510885 | 1364.17 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 75
Jul-26 | 31/07/2026 | Mondi | Planned |  | 2188848.43 | 2183019.3 | 5829.13 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 83
Jul-26 | 31/07/2026 | Mondi | Planned |  | 647022.76 | 583594 | 63428.76 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 141
Jul-26 | 31/07/2026 | Mondi | Planned |  | 328418.87 | 296223.4 | 32195.47 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 142
Jul-26 | 31/07/2026 | Mondi | Planned |  | 7375869.24 | 6652800 | 723069.24 | 30/08/2026 |  | PO4734-MON-20260402 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 144
Jul-26 | 31/07/2026 | Mondi | Planned |  | 879676.18 | 793440 | 86236.18 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 145
Jul-26 | 31/07/2026 | Mondi | Planned |  | 38421.16 | 35528 | 2893.16 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 172
Jul-26 | 31/07/2026 | Mondi | Planned |  | 1382539.22 | 1278432.32 | 104106.9 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 189
Jul-26 | 31/07/2026 | Mondi | Planned |  | 865146.6 | 800000 | 65146.6 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 194
Jul-26 | 31/07/2026 | Mondi | Planned |  | 50757.07 | 46935 | 3822.07 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 202
Jul-26 | 31/07/2026 | Mondi | Planned |  | 1157604.65 | 1070435.6 | 87169.05 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 212
Jul-26 | 31/07/2026 | Mondi | Planned |  | 569848.56 | 400000 | 169848.56 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 229
Jul-26 | 31/07/2026 | Mondi | Planned |  | 154835.55 | 139058.15 | 15777.4 | 14/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 237
Jul-26 | 31/07/2026 | Mondi | Planned |  | 154835.55 | 139058.15 | 15777.4 | 28/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 238
Jul-26 | 31/07/2026 | Mondi | Planned |  | 756864.75 | 679741.9 | 77122.86 | 14/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 248
Jul-26 | 31/07/2026 | Mondi | Planned |  | 756864.75 | 679741.9 | 77122.86 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 249
Jul-26 | 31/07/2026 | Mondi | Planned |  | 160210.63 | 143885.51 | 16325.11 | 21/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 256
Jul-26 | 31/07/2026 | Mondi | Planned |  | 174141.98 | 156397.3 | 17744.69 | 14/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 258
Jul-26 | 31/07/2026 | Mondi | Planned |  | 174141.98 | 156397.3 | 17744.69 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 259
Jul-26 | 31/07/2026 | Mondi | Planned |  | 28198 | 25324.68 | 2873.31 | 15/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 266
Jul-26 | 31/07/2026 | Mondi | Planned |  | 35247.5 | 31655.85 | 3591.64 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 267
Jul-26 | 31/07/2026 | Mondi | Planned |  | 811722.26 | 1210921.44 | -399199.18 | 30/06/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 276
Jul-26 | 31/07/2026 | Mondi | Planned |  | 811722.26 | 1210921.44 | -399199.18 | 14/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 277
Jul-26 | 31/07/2026 | Mondi | Planned |  | 45965.79 | 68571.43 | -22605.64 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 285
Jul-26 | 31/07/2026 | Mondi | Planned |  | 11898.44 | 17750 | -5851.56 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 298
Jul-26 | 31/07/2026 | Mondi | Planned |  | 3190.79 | 4760 | -1569.21 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 310
Jul-26 | 31/07/2026 | Mondi | Planned |  | 6703.34 | 10000 | -3296.66 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 321
Jul-26 | 31/07/2026 | Mondi | Planned |  | 8295.39 | 12375 | -4079.61 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 357
Jul-26 | 31/07/2026 | Mondi | Planned |  | 56224.09 | 83874.7 | -27650.61 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 364
Jul-26 | 31/07/2026 | Mondi | Planned |  | 35321.26 | 52692 | -17370.74 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 365
Jul-26 | 31/07/2026 | Mondi | Planned |  | 56224.09 | 83874.7 | -27650.61 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 366
Jul-26 | 31/07/2026 | Mondi | Planned |  | 35321.26 | 52692 | -17370.74 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 367
Jul-26 | 31/07/2026 | Mondi | Planned |  | 20006.48 | 29845.52 | -9839.04 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 370
Jul-26 | 31/07/2026 | Mondi | Planned |  | 35321.26 | 52692 | -17370.74 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 371
Jul-26 | 31/07/2026 | Mondi | Planned |  | 13940.78 | 20796.76 | -6855.98 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 374
Jul-26 | 31/07/2026 | Mondi | Planned |  | 35321.26 | 52692 | -17370.74 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 375
Jul-26 | 31/07/2026 | Mondi | Planned |  | 502.75 | 750 | -247.25 | 30/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 381
Jul-26 | 31/07/2026 | Mondi | Planned |  | 4494.08 | 6500 | -2005.92 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 403
Jul-26 | 31/07/2026 | Mondi | Planned |  | 70522.56 | 102000 | -31477.44 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 412
Jul-26 | 31/07/2026 | Mondi | Planned |  | 12623.26 | 18257.6 | -5634.34 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 420
Jul-26 | 31/07/2026 | Mondi | Planned |  | 112885.73 | 69362.12 | 43523.61 | 25/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 462
Jul-26 | 31/07/2026 | Mondi | Planned |  | 13983.04 | 25000 | -11016.96 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 473
Jul-26 | 31/07/2026 | Mondi | Planned |  | 17143.21 | 30650 | -13506.79 | 07/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 481
Jul-26 | 31/07/2026 | Mondi | Planned |  | 42319.04 | 126180.51 | -83861.47 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 521
Jul-26 | 31/07/2026 | Shoprite Mini Riversdal | Planned |  | 63986.93 | 11000 | 52986.93 | 06/07/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 118
Jul-26 | 31/07/2026 | Shoprite Mini Riversdal | Planned |  | 17145.94 | 1837.5 | 15308.44 | 07/08/2026 |  |  | Shoprite Mini Riversdal_Tracker.xlsm | Expenditure Breakdown | 137
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 26946.49 | 26928 | 18.49 | 13/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 34
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 33683.11 | 33660 | 23.11 | 06/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 35
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 13473.24 | 13464 | 9.24 | 21/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 36
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 13473.24 | 13464 | 9.24 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 37
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 6736.62 | 6732 | 4.62 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 38
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 41192.36 | 19160 | 22032.36 | 13/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 60
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 51490.45 | 23950 | 27540.45 | 06/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 61
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 20596.18 | 9580 | 11016.18 | 21/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 62
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 20596.18 | 9580 | 11016.18 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 63
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 10298.09 | 4790 | 5508.09 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 64
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 61100 | 75500 | -14400 | 13/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 92
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 76375 | 94375 | -18000 | 06/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 93
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 30550 | 37750 | -7200 | 21/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 94
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 30550 | 37750 | -7200 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 95
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 15275 | 18875 | -3600 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 96
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 4957.78 | 24905.7 | -19947.92 | 13/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 108
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 6197.23 | 31132.12 | -24934.9 | 06/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 109
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 2478.89 | 12452.85 | -9973.96 | 21/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 110
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 2478.89 | 12452.85 | -9973.96 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 111
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 1239.45 | 6226.43 | -4986.98 | 20/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 112
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 3120.32 | 11000 | -7879.68 | 28/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 118
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 2836.65 | 10000 | -7163.35 | 28/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 121
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 0 | 9560.26 | -9560.26 | 21/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 125
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 30349.25 | 33977.5 | -3628.25 | 14/07/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 128
Jul-26 | 31/07/2026 | Swellengrebel | Planned |  | 4568.65 | 3123.75 | 1444.9 | 07/08/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 137
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 18146.49 | 12824.57 | 5321.92 | 09/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 34
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 9073.24 | 6412.29 | 2660.96 | 29/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 36
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 13609.87 | 9618.43 | 3991.44 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 37
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 8684.78 | 16794.48 | -8109.7 | 09/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 67
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 4342.39 | 8397.24 | -4054.85 | 29/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 69
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 6513.59 | 12595.86 | -6082.27 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 70
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 51625.09 | 34250.73 | 17374.36 | 29/09/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 78
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 174848.77 | 116003.62 | 58845.15 | 29/09/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 80
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 44146.67 | 52818.46 | -8671.79 | 09/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 129
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 22073.33 | 26409.23 | -4335.9 | 29/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 131
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 33110 | 39613.84 | -6503.85 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 132
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 572.57 | 4640.02 | -4067.45 | 09/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 145
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 286.28 | 2320.01 | -2033.73 | 29/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 147
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 429.42 | 3480.01 | -3050.59 | 31/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 148
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 65482.85 | 66672.49 | -1189.64 | 22/07/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 164
Jul-26 | 31/07/2026 | Unitrans Brackenfell | Planned |  | 0 | 600 | -600 | 07/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 174
Jul-26 | 31/07/2026 | Volvo Moffet | Planned |  | 1330.82 | 1358.81 | -28 | 18/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 38
Jul-26 | 31/07/2026 | Volvo Moffet | Planned |  | 787.89 | 1016.1 | -228.21 | 18/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 66
Jul-26 | 31/07/2026 | Volvo Moffet | Planned |  | 1829.69 | 2361.9 | -532.21 | 18/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 98
Jul-26 | 31/07/2026 | Volvo Moffet | Planned |  | 143.85 | 1661.25 | -1517.4 | 18/07/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 114
Jul-26 | 31/07/2026 | Volvo Moffet | Planned |  | 319.71 | 218.75 | 100.96 | 07/08/2026 |  |  | Volvo Moffet_Tracker.xlsm | Expenditure Breakdown | 139
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 23292.29 | 22240.9 | 1051.39 | 03/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 36
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 34938.44 | 33361.35 | 1577.09 | 06/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 37
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 18387.06 | 8357.45 | 10029.6 | 03/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 62
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 27580.58 | 12536.18 | 15044.4 | 06/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 63
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 36400 | 43680 | -7280 | 03/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 94
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 54600 | 65520 | -10920 | 06/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 95
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 3216.47 | 4394.5 | -1178.03 | 03/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 110
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 4824.71 | 6591.75 | -1767.04 | 06/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 111
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 38862.55 | 60000 | -21137.45 | 31/08/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 122
Aug-26 | 31/08/2026 | 12 Nourse | Planned |  | 262.5 | 236.25 | 26.25 | 07/09/2026 |  |  | 12 Nourse_Tracker.xlsm | Expenditure Breakdown | 136
Aug-26 | 31/08/2026 | Coega Steels Ph2 | Planned |  | 0 | 71895.6 | -71895.6 | 07/09/2026 |  | PO4692-CSPH2-20260320 - RV Approved | Coega Steels Ph2_Tracker.xlsx | Expenditure Breakdown | 445
Aug-26 | 31/08/2026 | De Drift | Planned |  | 0 | 150000 | -150000 | 31/08/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 95
Aug-26 | 31/08/2026 | De Drift | Planned |  | 17627.98 | 15000 | 2627.98 | 31/08/2026 |  |  | De Drift_Tracker.xlsx | Expenditure Breakdown | 137
Aug-26 | 31/08/2026 | Klein Karoo Phase 2 | Planned |  | 12487.36 | 11385 | 1102.36 | 08/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 38
Aug-26 | 31/08/2026 | Klein Karoo Phase 2 | Planned |  | 36462.68 | 12400 | 24062.68 | 08/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 64
Aug-26 | 31/08/2026 | Klein Karoo Phase 2 | Planned |  | 24050 | 32375 | -8325 | 08/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 96
Aug-26 | 31/08/2026 | Klein Karoo Phase 2 | Planned |  | 4274.75 | 3717.5 | 557.25 | 08/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 112
Aug-26 | 31/08/2026 | Klein Karoo Phase 2 | Planned |  | 0 | 15000 | -15000 | 31/08/2026 |  |  | Klein Karoo Phase 2_Tracker.xlsm | Expenditure Breakdown | 149
Aug-26 | 31/08/2026 | Life Changers | Planned |  | 364.67 | 218.75 | 145.92 | 07/09/2026 |  |  | Life Changers_Tracker.xlsm | Expenditure Breakdown | 138
Aug-26 | 31/08/2026 | Maynard Mall Extension | Planned |  | 3323.39 | 2785.75 | 537.64 | 28/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 38
Aug-26 | 31/08/2026 | Maynard Mall Extension | Planned |  | 11308.79 | 4654.77 | 6654.02 | 28/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 64
Aug-26 | 31/08/2026 | Maynard Mall Extension | Planned |  | 6825 | 5221.13 | 1603.87 | 28/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 101
Aug-26 | 31/08/2026 | Maynard Mall Extension | Planned |  | 1725.81 | 810.25 | 915.57 | 28/08/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 117
Aug-26 | 31/08/2026 | Maynard Mall Extension | Planned |  | 648.15 | 437.5 | 210.65 | 07/09/2026 |  |  | Maynard Mall Extension_Tracker.xlsm | Expenditure Breakdown | 142
Aug-26 | 31/08/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 7582285.48 | 7095706.56 | 486578.92 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 9
Aug-26 | 31/08/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 40784.47 | 38167.2 | 2617.27 | 17/02/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 17
Aug-26 | 31/08/2026 | Mondi | Committed | MSA Energy - 000003/02/2026 | 367060.2 | 343504.8 | 23555.4 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 18
Aug-26 | 31/08/2026 | Mondi | Planned |  | 239713.56 | 190440 | 49273.56 | 30/09/2026 |  | PO4521-MON-20251203 - JP Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 58
Aug-26 | 31/08/2026 | Mondi | Planned |  | 444985.04 | 443800 | 1185.04 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 72
Aug-26 | 31/08/2026 | Mondi | Planned |  | 620505.84 | 500000 | 120505.84 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 86
Aug-26 | 31/08/2026 | Mondi | Planned |  | 635397.98 | 512000 | 123397.98 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 89
Aug-26 | 31/08/2026 | Mondi | Planned |  | 651531.13 | 525000 | 126531.13 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 92
Aug-26 | 31/08/2026 | Mondi | Planned |  | 248202.34 | 200000 | 48202.34 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 94
Aug-26 | 31/08/2026 | Mondi | Planned |  | 124101.17 | 100000 | 24101.17 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 97
Aug-26 | 31/08/2026 | Mondi | Planned |  | 343414.96 | 309749.4 | 33665.56 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 118
Aug-26 | 31/08/2026 | Mondi | Planned |  | 343414.96 | 309749.4 | 33665.56 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 119
Aug-26 | 31/08/2026 | Mondi | Planned |  | 17738.98 | 16000 | 1738.98 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 120
Aug-26 | 31/08/2026 | Mondi | Planned |  | 221482.29 | 199770 | 21712.29 | 30/09/2026 |  | PO4871-MON-20260609 - RV Approved | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 122
Aug-26 | 31/08/2026 | Mondi | Planned |  | 595468.73 | 537093.9 | 58374.83 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 125
Aug-26 | 31/08/2026 | Mondi | Planned |  | 0 | 75000 | -75000 | 03/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 148
Aug-26 | 31/08/2026 | Mondi | Planned |  | 0 | 75000 | -75000 | 25/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 149
Aug-26 | 31/08/2026 | Mondi | Planned |  | 0 | 400000 | -400000 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 151
Aug-26 | 31/08/2026 | Mondi | Planned |  | 864300.57 | 799217.68 | 65082.89 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 176
Aug-26 | 31/08/2026 | Mondi | Planned |  | 646602.98 | 597912.98 | 48690 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 190
Aug-26 | 31/08/2026 | Mondi | Planned |  | 27937.31 | 25833.6 | 2103.71 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 191
Aug-26 | 31/08/2026 | Mondi | Planned |  | 447180.93 | 413507.66 | 33673.27 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 192
Aug-26 | 31/08/2026 | Mondi | Planned |  | 568974.48 | 526130 | 42844.48 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 200
Aug-26 | 31/08/2026 | Mondi | Planned |  | 421758.97 | 390000 | 31758.97 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 206
Aug-26 | 31/08/2026 | Mondi | Planned |  | 607883.84 | 562109.44 | 45774.4 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 209
Aug-26 | 31/08/2026 | Mondi | Planned |  | 154835.55 | 139058.15 | 15777.4 | 11/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 239
Aug-26 | 31/08/2026 | Mondi | Planned |  | 247736.89 | 222493.04 | 25243.85 | 25/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 240
Aug-26 | 31/08/2026 | Mondi | Planned |  | 92901.33 | 83434.89 | 9466.44 | 08/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 241
Aug-26 | 31/08/2026 | Mondi | Planned |  | 30967.11 | 27811.63 | 3155.48 | 31/08/2027 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 242
Aug-26 | 31/08/2026 | Mondi | Planned |  | 1210983.61 | 1087587.03 | 123396.58 | 14/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 250
Aug-26 | 31/08/2026 | Mondi | Planned |  | 454118.85 | 407845.14 | 46273.72 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 251
Aug-26 | 31/08/2026 | Mondi | Planned |  | 151372.95 | 135948.38 | 15424.57 | 31/08/2027 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 252
Aug-26 | 31/08/2026 | Mondi | Planned |  | 278627.17 | 250235.68 | 28391.5 | 14/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 260
Aug-26 | 31/08/2026 | Mondi | Planned |  | 104485.19 | 93838.38 | 10646.81 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 261
Aug-26 | 31/08/2026 | Mondi | Planned |  | 34828.4 | 31279.46 | 3548.94 | 31/08/2027 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 262
Aug-26 | 31/08/2026 | Mondi | Planned |  | 26435.62 | 23741.89 | 2693.73 | 15/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 268
Aug-26 | 31/08/2026 | Mondi | Planned |  | 2937.29 | 2637.99 | 299.3 | 31/08/2027 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 269
Aug-26 | 31/08/2026 | Mondi | Planned |  | 811722.26 | 1210921.44 | -399199.18 | 31/07/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 278
Aug-26 | 31/08/2026 | Mondi | Planned |  | 1298755.61 | 1937474.3 | -638718.69 | 14/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 279
Aug-26 | 31/08/2026 | Mondi | Planned |  | 487033.35 | 726552.86 | -239519.51 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 280
Aug-26 | 31/08/2026 | Mondi | Planned |  | 162344.45 | 242184.29 | -79839.84 | 31/08/2027 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 281
Aug-26 | 31/08/2026 | Mondi | Planned |  | 45965.79 | 68571.43 | -22605.64 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 286
Aug-26 | 31/08/2026 | Mondi | Planned |  | 3190.79 | 4760 | -1569.21 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 311
Aug-26 | 31/08/2026 | Mondi | Planned |  | 6703.34 | 10000 | -3296.66 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 322
Aug-26 | 31/08/2026 | Mondi | Planned |  | 155684.87 | 274906.22 | -119221.35 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 332
Aug-26 | 31/08/2026 | Mondi | Planned |  | 95171.22 | 141975.75 | -46804.53 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 350
Aug-26 | 31/08/2026 | Mondi | Planned |  | 8295.39 | 12375 | -4079.61 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 358
Aug-26 | 31/08/2026 | Mondi | Planned |  | 502.75 | 750 | -247.25 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 382
Aug-26 | 31/08/2026 | Mondi | Planned |  | 15082.52 | 22500 | -7417.48 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 386
Aug-26 | 31/08/2026 | Mondi | Planned |  | 4494.08 | 6500 | -2005.92 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 404
Aug-26 | 31/08/2026 | Mondi | Planned |  | 70522.56 | 102000 | -31477.44 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 413
Aug-26 | 31/08/2026 | Mondi | Planned |  | 12623.26 | 18257.6 | -5634.34 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 421
Aug-26 | 31/08/2026 | Mondi | Planned |  | 95537.33 | 138180 | -42642.67 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 432
Aug-26 | 31/08/2026 | Mondi | Planned |  | 5254.62 | 7600 | -2345.38 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 435
Aug-26 | 31/08/2026 | Mondi | Planned |  | 247900.63 | 358550 | -110649.37 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 437
Aug-26 | 31/08/2026 | Mondi | Planned |  | 345698.83 | 500000 | -154301.17 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 444
Aug-26 | 31/08/2026 | Mondi | Planned |  | 163349.71 | 236260.14 | -72910.43 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 446
Aug-26 | 31/08/2026 | Mondi | Planned |  | 1550500.31 | 923726.21 | 626774.09 | 30/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 453
Aug-26 | 31/08/2026 | Mondi | Planned |  | 112885.73 | 69362.12 | 43523.61 | 25/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 463
Aug-26 | 31/08/2026 | Mondi | Planned |  | 13983.04 | 25000 | -11016.96 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 474
Aug-26 | 31/08/2026 | Mondi | Planned |  | 17143.21 | 30650 | -13506.79 | 07/09/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 482
Aug-26 | 31/08/2026 | Mondi | Planned |  | 16769.24 | 50000 | -33230.76 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 510
Aug-26 | 31/08/2026 | Mondi | Planned |  | 37626.31 | 112188.43 | -74562.12 | 31/08/2026 |  |  | Mondi_Tracker_Rev02.xlsm | Expenditure Breakdown | 522
Aug-26 | 31/08/2026 | Swellengrebel | Planned |  | 6736.62 | 6732 | 4.62 | 12/08/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 39
Aug-26 | 31/08/2026 | Swellengrebel | Planned |  | 10298.09 | 4790 | 5508.09 | 12/08/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 65
Aug-26 | 31/08/2026 | Swellengrebel | Planned |  | 15275 | 18875 | -3600 | 12/08/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 97
Aug-26 | 31/08/2026 | Swellengrebel | Planned |  | 1239.45 | 6226.43 | -4986.98 | 12/08/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 113
Aug-26 | 31/08/2026 | Swellengrebel | Planned |  | 4568.65 | 3123.75 | 1444.9 | 07/09/2026 |  |  | Swellengrebel_Tracker.xlsx | Expenditure Breakdown | 138
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 4536.62 | 3206.14 | 1330.48 | 30/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 38
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 2171.2 | 4198.62 | -2027.42 | 30/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 71
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 11036.67 | 13204.61 | -2167.95 | 30/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 133
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 143.14 | 1160 | -1016.86 | 30/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 149
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 13717.03 | 11000 | 2717.03 | 05/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 155
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 7482.01 | 6000 | 1482.01 | 30/09/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 158
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 0 | 600 | -600 | 07/09/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 175
Aug-26 | 31/08/2026 | Unitrans Brackenfell | Planned |  | 0 | 150000 | -150000 | 31/08/2026 |  |  | Unitrans Brackenfell_Tracker.xlsm | Expenditure Breakdown | 184
|  |  |  | TOTAL | 238405936 | 216825559 | 21580377