## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2025 | Budgeted | Actual | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 59995000 |  | 59995000 |  |  | 59995000 | Start Date | Sales |  | 59995000 | 59995000 | 44416314.2604 | 37030035.4321 | 13731176.7404 | 11664162.9344 | 12424766.1438 | 8549413.1544
2 | Planned Expenditure | 56096452.0791 |  | 48694198.3664 | VO PM Limit | Current VO Total | 46345971.3212 | 2025-08-25 | COS |  | 48694198.3664 | 48694198.3664
3 | Planned Profit | 3898547.9209 |  | 11300801.6336 | 194927.396 | 0 | 13649028.6788 | End Date - PC | GP | 0 | 11300801.6336 | 11300801.6336
4 | Planned Margin | 6.498% |  | 18.84% |  |  | 22.75% | 2025-11-21
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Deposit - Coega Steel |  | 25% | 15000000 |  | 2025-05-31 | 004753 | 2025-05-28 | 2025-06-20
2 | Delivery of Panels - Batch 1 |  | 15% | 8998000 |  | 2025-08-29 | 004823 | 2025-08-26 | 2025-08-29
3 | Delivery of Panels - Batch 2 |  | 15% | 8999250 |  | 2025-09-22 | 004838 | 2025-09-12 | 2025-09-18
4 | Delivery of Inverters |  | 30% | 17998500 |  | 2025-07-24 | 004783 | 2025-07-14 | 2025-07-24
5 | Practical Completion |  | 10% | 29557.1478 |  | 2025-11-19 | 004933 | 2026-02-02 | 2025-12-11
5 | Practical Completion |  |  | 20283.5826 |  | 2025-11-19 | 004933 | 2026-02-02 | 2025-12-11
5 | Practical Completion |  |  | 5949659.2696 |  | 2025-11-19 | 004933 | 2026-02-02 | 2026-02-09 | Completion Certificate to be shared
6 | Handover |  | 5% | 2999750 |  | 2025-12-08 |  |  | 2026-04-25
7 | - |  | 0% | 0
|  |  | 100% | 59995000
KEY: | contains an error (in result or a check has failed)
| Red Font - IF TEXT : content not yet confirmed |  |  | 5999500
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
Formulas:
PLANNED PAYMENT DATE = [PAYMENT RECEIVED DATE]

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
Manual dates
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
2026-01-09 | Builders Break
2026-01-10 | Builders Break
2026-01-11 | Builders Break
2026-01-12 | Builders Break
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Project Plan
[9 empty] | 2026-02-09 | 2026-02-09
| PROJECT PLAN | Coega Steels Phase 2 | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 7080
| PROJECT DEVELOPER | Gordon Upton
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 59995000
| Phase: | QA
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (work days) | Planned End | Actual Start | Duration (work days) | Actual End | Status | Expected Status | Comment
|  |  | 160 |  |  | 240 |  | 88.19% | 93.48%
1 | Project Initiation | 2025-05-19 | 74 | 2025-08-01 | 2025-05-19 | 74 | 2025-08-01 | 100% | 100%
1.1 | PD Handover | 2025-05-19 | 1 | 2025-05-20 | 2025-05-19 | 1 | 2025-05-20 | 100% | 100%
1.2 | Financial Close | 2025-05-31 | 1 | 2025-06-02 | 2025-05-31 | 1 | 2025-06-02 | 100% | 100%
1.3 | Structural Assessment | 2025-05-19 | 1 | 2025-05-20 | 2025-05-19 | 1 | 2025-05-20 | 100% | 100%
1.4 | Project Introduction | 2025-07-29 | 1 | 2025-07-30 | 2025-07-29 | 1 | 2025-07-30 | 100% | 100% | [7 empty] | 0%
1.5 | Project Review | 2025-08-01 | 0 | 2025-08-01 | 2025-08-01 | 0 | 2025-08-01 | 100% | 100% | [7 empty] | 100%
2 | Site Establishment Preperation | 2025-06-07 | 6 | 2025-06-13 | 2025-06-07 | 95 | 2025-09-10 | 100% | 100% |  | Milestone | Start Date | Total Duration | Total WorkDays | End Date | Progress Percentage | Project Overall Progress Percentage
2.1 | HSE Requirements | 2025-06-07 | 5 | 2025-06-13 | 2025-06-07 | 5 | 2025-06-13 | 100% | 100% |  | Procurement & Contracting | 2025-05-19 | 193 | 124 | 2025-11-28 | 100% | 88.19%
2.2 | EE File | 2025-06-13 | 17 | 2025-07-09 | 2025-06-13 | 17 | 2025-07-09 | 100% | 100% |  | Extras & Civil Works | 2025-06-22 | 212 | 71 | 2026-01-20 | 100%
2.3 | Subcontractor File - Solar Contractor | 2025-07-09 | 8 | 2025-07-21 | 2025-07-09 | 31 | 2025-08-21 | 100% | 100% |  | DC Works - Rooftop | 2025-08-25 | 147 | 51 | 2026-01-19 | 100% |  | 2026-02-09 | 2026-02-09
2.4 | Subcontractor File - Civil Contractor (Bay View Construction & Engineering Hub) |  |  |  | 2025-08-06 | 25 | 2025-09-10 | 100% | 100% | Bayview file pending - awaiting Medical approvals | DC Works - Ground Mount | 2025-10-08 | 120 | 58 | 2026-02-05 | 99% |  | 1 | 0
2.5 | Subcontractor File - Anchor Point Contractor | 2025-07-09 | 8 | 2025-07-21 | 2025-07-09 | 31 | 2025-08-21 | 100% | 100% |  | AC Installation - Ground Mount | 2025-11-29 | 17 | 26 | 2025-12-16 | 100%
2.6 | HSE Permit Issued |  |  |  | 2025-07-09 | 33 | 2025-08-25 | 100% | 100% | CDC/Coega Delays | AC Installation - Rooftop | 2025-09-15 | 92 | 21 | 2025-12-16 | 100%
2.7 | Establishment of site entry & Exit points |  |  |  | 2025-07-29 | 0 | 2025-07-29 | 100% | 100% |  | Transformer Installation | 2025-11-25 | 22 | 43 | 2025-12-17 | 100%
2.8 | Laydown Area Demarcated |  |  |  | 2025-07-29 | 0 | 2025-07-29 | 100% | 100% |  | Commissioning | 2025-12-15 | 59 | 4 | 2026-02-12 | 89%
2.9 | Ground Mount Demarcated |  |  |  | 2025-07-29 | 0 | 2025-07-29 | 100% | 100% |  | QA Inspection & Snag Completion | 2026-01-26 | 22 | 58 | 2026-02-17 | 52%
2.1 | Designated area fencing |  |  |  | 2025-07-29 | 0 | 2025-07-29 | 100% | 100% |  | Project Closure | 2025-12-15 | 72 | 70 | 2026-02-25 | 18.33%
2.11 | Site Ablutions |  |  |  | 2025-07-29 | 21 | 2025-08-27 | 100% | 100% | Appointment finalised by eow
2.12 | Site Establishment Permit Issued |  |  |  | 2025-07-29 | 23 | 2025-08-21 | 100% | 100%
3 | Procurement & Contracting | 2025-05-18 | 124 | 2025-09-19 | 2025-05-19 | 193 | 2025-11-28 | 100% | 100%
3.1 | Huawei Transformers (16 weeks lead time) | 2025-05-18 | 89 | 2025-09-19 | 2025-05-18 | 138 | 2025-11-28 | 100% | 100% | Delay of shipping as of 14 Oct
3.2 | Panels (6 - 8 Weeks) | 2025-06-12 | 36 | 2025-08-04 | 2025-06-12 | 93 | 2025-10-23 | 100% | 100% | 30 pallets deliverd 26/08; 90 pallets 15 Oct; 185 pallets 20 Oct
3.3 | Ground Mount Structure (10 Weeks) | 2025-06-12 | 58 | 2025-09-03 | 2025-06-12 | 66 | 2025-09-15 | 100% | 100%
3.4 | Inverters (8 to 12 weeks) | 2025-06-12 | 18 | 2025-07-09 | 2025-06-12 | 18 | 2025-07-09 | 100% | 100%
3.5 | DC Cable | 2025-06-12 | 18 | 2025-07-09 | 2025-06-12 | 66 | 2025-09-15 | 100% | 100%
3.6 | LV Cable (2-4 Weeks) | 2025-07-17 | 10 | 2025-07-31 | 2025-07-17 | 10 | 2025-07-31 | 100% | 100%
3.7 | MV Cable (2-4 Weeks) | 2025-07-17 | 10 | 2025-07-31 | 2025-07-17 | 10 | 2025-07-31 | 100% | 100%
3.8 | Distribution Boards (6 - 8 Weeks) | 2025-07-10 | 20 | 2025-08-07 | 2025-07-10 | 34 | 2025-08-27 | 100% | 100% | ABB hold up on the breakers
4 | Extras & Civil Works | 2025-06-22 | 71 | 2025-09-01 | 2025-06-22 | 212 | 2026-01-20 | 100% | 100%
4.1 | Staircase Installation - Coega Scope |  |  |  | 2025-06-22 | 61 | 2025-09-15 | 100% | 100% | Follow up with Coega
4.2 | Ground Mount Fence - Coega Scope | 2025-06-22 | 42 | 2025-08-19 | 2025-06-22 | 135 | 2026-01-20 | 100% | 100% | Resuming 01 Oct
4.3 | Catladder Fabrication | 2025-07-16 | 15 | 2025-08-06 | 2025-07-16 | 31 | 2025-08-28 | 100% | 100%
4.4 | Catladder Installation | 2025-08-06 | 5 | 2025-08-13 | 2025-09-13 | 15 | 2025-10-06 | 100% | 100% | Awaiting sign off form Subbie
4.5 | Rooftop Inverter Cage Fabrication | 2025-08-04 | 15 | 2025-08-25 | 2025-10-17 | 19 | 2025-11-13 | 100% | 100%
4.6 | Rooftop Inverter Cage Installation | 2025-08-25 | 5 | 2025-09-01 | 2025-11-13 | 5 | 2025-11-20 | 100% | 100%
4.7 | Plinths - Casting & Curing | 2025-08-11 | 15 | 2025-09-01 | 2025-10-23 | 32 | 2025-12-08 | 100% | 100%
4.8 | Walkway Installation | 2025-08-09 | 5 | 2025-08-15 | 2025-08-30 | 10 | 2025-09-12 | 100% | 100% | Complete on Furnance, staring on mill
4.9 | Anchor Point Installation | 2025-08-04 | 5 | 2025-08-11 | 2025-08-25 | 7 | 2025-09-03 | 100% | 100%
4.1 | Optic Fiber Installation |  |  |  | 2025-12-03 | 2 | 2025-12-05 | 100% | 100%
4.11 | Trenching - Fiber | [6 empty] | 100% | 100%
4.12 | Directional Drilling | [6 empty] | 100% | 100%
4.13 | Trenching - Ground Mount to Mill | [6 empty] | 100% | 100%
4.14 | Trenching - Furnance & Mill - Coega Scope |  |  |  | 2025-12-01 | 12 | 2025-12-17 | 100% | 100% | Direct impact on pulling strings from the furnance to the mill. Impacts approx. 1,6MW
5 | DC Works - Rooftop | 2025-08-09 | 51 | 2025-09-29 | 2025-08-25 | 147 | 2026-01-19 | 100% | 100%
5.1 | Mounting Structure delivered | 2025-06-27 | 1 | 2025-06-30 | 2025-06-27 | 1 | 2025-06-30 | 100% | 100%
5.2 | Mounting Structure installation - Frunance | 2025-08-09 | 12 | 2025-08-26 | 2025-08-25 | 5 | 2025-09-01 | 100% | 100%
5.3 | Mounting Structure installation - Mill |  |  |  | 2025-09-01 | 5 | 2025-09-08 | 100% | 100%
5.4 | Panel Installation - Furnace | 2025-08-27 | 17 | 2025-09-19 | 2025-09-15 | 24 | 2025-10-20 | 100% | 100% | Waiting for delivery of panels
5.5 | Panel Installation - Mill |  |  |  | 2025-10-21 | 22 | 2025-11-20 | 100% | 100% | Roof risk delayed
5.6 | DC Stringing - Furnace | 2025-09-21 | 5 | 2025-09-29 | 2025-10-10 | 55 | 2026-01-19 | 100% | 100%
5.7 | DC Stringing - Mill |  |  |  | 2025-09-29 | 9 | 2025-10-10 | 100% | 100%
6 | DC Works - Ground Mount | 2025-08-25 | 58 | 2025-10-22 | 2025-10-08 | 120 | 2026-02-05 | 99% | 100%
6.1 | Drilling | 2025-08-25 | 7 | 2025-09-03 | 2025-10-08 | 34 | 2025-11-25 | 100% | 100% | 1. Top layer soil was building rubble. 2. Levelling and approval of installation took 4 weeks longer than intially communicated by Coega. 3. Baseline date was 12 Sept 2025, Bayview only started 08 Oct 2025. 4. This has caused a 4 week delay.
6.2 | Pillar Installation | 2025-09-03 | 7 | 2025-09-12 | 2025-10-26 | 37 | 2025-12-16 | 100% | 100% | Busy with the north facing pillars
6.3 | Structure Installation | 2025-09-15 | 14 | 2025-10-06 | 2025-11-02 | 42 | 2026-01-21 | 100% | 100%
6.4 | Panel Installation | 2025-10-08 | 10 | 2025-10-22 | 2025-11-24 | 33 | 2026-01-30 | 100% | 100%
6.5 | DC Stringing | 2025-10-24 | 10 | 2025-11-07 | 2026-01-01 | 18 | 2026-02-05 | 95% | 100%
7 | AC Installation - Ground Mount | 2025-10-15 | 26 | 2025-11-10 | 2025-11-29 | 17 | 2025-12-16 | 100% | 100%
7.1 | Inverters Delivered | 2025-07-10 | 1 | 2025-07-11 | 2025-07-10 | 1 | 2025-07-11 | 100% | 100%
7.2 | Inverters Mounted | 2025-10-15 | 6 | 2025-10-23 | 2025-11-29 | 4 | 2025-12-04 | 100% | 100%
7.3 | DB Placement | 2025-10-23 | 2 | 2025-10-27 | 2025-11-29 | 4 | 2025-12-04 | 100% | 100%
7.4 | Cabling - Inverter to DB | 2025-10-27 | 5 | 2025-11-03 | 2025-12-04 | 5 | 2025-12-11 | 100% | 100%
7.5 | Cabling - DB to Transformer | 2025-11-03 | 5 | 2025-11-10 | 2025-12-04 | 8 | 2025-12-16 | 100% | 100%
8 | AC Installation - Rooftop | 2025-10-20 | 21 | 2025-11-10 | 2025-09-15 | 92 | 2025-12-16 | 100% | 100%
8.1 | Inverters Delivered | 2025-07-10 | 1 | 2025-07-11 | 2025-07-10 | 1 | 2025-07-11 | 100% | 100%
8.2 | Inverters Mounted | 2025-10-20 | 4 | 2025-10-24 | 2025-09-15 | 3 | 2025-09-18 | 100% | 100%
8.3 | DB Placement | 2025-10-24 | 2 | 2025-10-28 | 2025-09-18 | 2 | 2025-09-22 | 100% | 100%
8.4 | Cabling - Inverter to DB | 2025-10-28 | 4 | 2025-11-03 | 2025-09-22 | 7 | 2025-10-02 | 100% | 100%
8.5 | Cabling - DB to Transformer | 2025-11-03 | 5 | 2025-11-10 | 2025-12-08 | 6 | 2025-12-16 | 100% | 100%
9 | Transformer Installation | 2025-09-22 | 43 | 2025-11-04 | 2025-11-25 | 22 | 2025-12-17 | 100% | 100%
9.1 | Transformer Offloading | 2025-09-22 | 2 | 2025-09-25 | 2025-11-27 | 1 | 2025-11-28 | 100% | 100%
| Transformer Rigging risk assessment and offloading plan |  |  |  | 2025-11-25 | 4 | 2025-12-01 | 100% | 100%
9.2 | Transformer 1 - MV - Install MV cabling | 2025-10-23 | 2 | 2025-10-27 | 2025-12-04 | 2 | 2025-12-08 | 100% | 100%
9.3 | Transformer 1 - MV - Terminate and connect cabling at RMU - Assuming Coega has the tie in breaker ready | 2025-10-27 | 0 | 2025-10-27 | 2025-12-11 | 0 | 2025-12-11 | 100% | 100%
9.4 | Transformer 1 - MV - Cable pressure testing and protection calibrations | 2025-10-27 | 2 | 2025-10-29 | 2025-12-11 | 2 | 2025-12-15 | 100% | 100%
9.5 | Transformer 2 - MV - Install MV cabling | 2025-10-29 | 2 | 2025-10-31 | 2025-12-15 | 2 | 2025-12-17 | 100% | 100%
9.6 | Transformer 2 - MV - Terminate and connect cabling at RMU | 2025-10-31 | 0 | 2025-10-31 | 2025-12-15 | 0 | 2025-12-15 | 100% | 100%
9.7 | Transformer 2 - MV - Cable pressure testing and protection calibrations | 2025-10-31 | 2 | 2025-11-04 | 2025-12-15 | 2 | 2025-12-17 | 100% | 100%
10 | Commissioning | 2025-11-10 | 4 | 2025-11-14 | 2025-12-15 | 59 | 2026-02-12 | 89% | 88.71%
10.1 | MV Signoff and COC | 2025-11-10 | 2 | 2025-11-12 | 2025-12-15 | 3 | 2025-12-18 | 100% | 100%
10.2 | Transformer Commissioning |  |  |  | 2025-12-15 | 2 | 2025-12-17 | 100% | 100%
10.3 | Inverter Commissioning |  |  |  | 2025-12-17 | 2 | 2025-12-19 | 100% | 100%
10.4 | Energy Flowing - Partial |  |  |  | 2025-12-18 | 1 | 2025-12-19 | 100% | 100% | Furnance strings to be energised
10.5 | Energy Flowing - Full |  |  |  | 2026-02-02 | 3 | 2026-02-05 | 90% | 50% | All strings to be energised
10.6 | Issue Compeltion Certificates |  |  |  | 2026-02-05 | 5 | 2026-02-12 | 0% | 57.14%
10.7 | Techsitter Installation |  |  |  | 2026-01-26 | 2 | 2026-01-28 | 100% | 100%
10.8 | Grid Meter Setup |  |  |  | 2026-01-12 | 10 | 2026-01-26 | 100% | 100%
10.9 | Inverter 4 Rolling Mill (Inverter 14) Faulty string |  |  |  | 2026-01-26 | 2 | 2026-01-28 | 100% | 100%
10.1 | Practical Completion | 2025-11-12 | 2 | 2025-11-14 | 2026-02-02 | 0 | 2026-02-02 | 100% | 80%
`
11 | QA Inspection & Snag Completion | 2025-09-29 | 58 | 2025-11-26 | 2026-01-26 | 22 | 2026-02-17 | 52% | 88.57%
11.1 | Pre Red-Team Inspection - Dean EE | 2025-09-29 | 1 | 2025-09-30 | 2026-01-26 | 1 | 2026-01-27 | 100% | 100%
11.2 | Schletter Sctructure Inspection - Dean Schletter | 2025-10-22 | 1 | 2025-10-23 | 2026-01-26 | 7 | 2026-02-04 | 50% | 100% | TBC
11.3 | Electrical Inspection - Renette | 2025-11-04 | 1 | 2025-11-05 | 2026-02-02 | 1 | 2026-02-03 | 10% | 100%
11.4 | Matriarch Inspection of the roofs |  |  |  | 2026-01-28 | 1 | 2026-01-29 | 100% | 100%
11.5 | Contractor Snag Completion | 2025-11-05 | 15 | 2025-11-26 | 2026-02-03 | 10 | 2026-02-17 | 0% | 42.86% | not started
12 | Project Closure | 2025-09-29 | 70 | 2025-12-08 | 2025-12-15 | 72 | 2026-02-25 | 18.33% | 44.44%
12.1 | Equipment serial numbers | 2025-11-10 | 5 | 2025-11-17 | 2025-12-15 | 5 | 2026-01-13 | 100% | 100%
12.2 | Client Snag List Completion | 2025-09-29 | 45 | 2025-12-01 | 2026-01-26 | 15 | 2026-02-16 | 0% | 66.67%
12.3 | System Performance Monitoring | 2025-11-14 | 5 | 2025-11-21 | 2026-02-02 | 5 | 2026-02-09 | 10% | 100%
12.4 | Handover documentation | 2025-11-10 | 15 | 2025-12-01 | 2026-02-17 | 5 | 2026-02-24 | 0% | 0%
12.5 | Handover to Client | 2025-12-01 | 2 | 2025-12-03 | 2026-02-24 | 1 | 2026-02-25 | 0% | 0%
12.6 | Handover to Matriarch | 2025-12-01 | 5 | 2025-12-08 | 2026-02-17 | 5 | 2026-02-24 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C41)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (work days)],1,Data!$C3:C41)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C41)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (work days)],1,Data!$C3:C41)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Note on O112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown has this been done by Schletter Reply: First one has been done , final one i am awaiting confirmation from Schletter , next week or so

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 56096452.0791 |  | 48694198.3664 | 7402253.7127
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 14537831.3 |  | 13735976 | 801855.3
2 | 2. Inverters | 2760000 |  | 2495176.2237 | 264823.7763
3 | 3. Mounting Structures | 7358785.9097 |  | 4071044.26 | 3287741.6497
4 | 4. DC Equipment | 8057942 |  | 3329187 | 4728755
5 | 5. Monitoring | 64000 |  | 241577.3 | -177577.3
6 | 6. AC Equipment | 2941866.9 |  | 2401487 | 540379.9
7 | 7.MV Substation | 12030860.6085 |  | 7046627.6127 | 4984232.9958
8 | 8. Product Add On | 2015000 |  | 2216118.21 | -201118.21
9 | 9. AC & DC installation | 4360411.237 |  | 8055680 | -3695268.763
10 | 10. Site Logistics | 394304.2333 |  | 936113.11 | -541808.8767
11 | 11. Due Dilligence | 420000 |  | 658656 | -238656
12 | 12. BDP Commission | 205449.8906 |  | 0 | 205449.8906
13 | 13. Engineering | 950000 |  | 984324.26 | -34324.26
14 | 14. General Expenses | 0 |  | 273188.38 | -273188.38
15 | 15. Service Add On | 0 |  | 2249043.01 | -2249043.01
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 56096452.0791 | 59995000 | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 48694198.3664
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 14537831.3 | 2025-06-19 | 14537831.3 | 15101045.6054 | 1 | 1. Panels | Jinko 620W - Deposit | 11420 | 10% | 1373597.6 | PO3993-CSPH2-20260610 - RV Approved | Menlo INV0003003 | 2025-07-31 | 1510104.5605 | 0 | 2025-06-19 | 13735976
1 |  | Delivery Budget | [6 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [8 empty] | 1 | 1. Panels | Jinko 620W - Ground Mount | 5112 | 1202.8 | 1457166.0522 |  | Menlo INV0003103 | 2025-07-31 | 6083790.7724 |  | 2025-09-25
[9 empty] | 1 | 1. Panels |  |  |  | 3897072 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2025-10-16
[9 empty] | 1 | 1. Panels |  |  |  | 179604.1878 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-09
1 | [8 empty] | 1 | 1. Panels | Jinko 620W - Rooftop | 6300 | 1202.8 | 869565.22 |  | Menlo INV0003103 | 2025-07-31 | 7497629.4731 |  | 2026-01-09
[9 empty] | 1 | 1. Panels |  |  |  | 637461.31 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-09
[9 empty] | 1 | 1. Panels |  |  |  | 1006679.1304 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-15
[9 empty] | 1 | 1. Panels |  |  |  | 1277597.209 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-23
[9 empty] | 1 | 1. Panels |  |  |  | 1304347.826 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-29
[9 empty] | 1 | 1. Panels |  |  |  | 1724225.3046 |  | Menlo INV0003103 | 2025-07-31 | 0 |  | 2026-01-29
1 | [8 empty] | 1 | 1. Panels | Spare | 8 | 1202.8 | 8660.16 |  | Menlo INV0003103 | 2025-07-31 | 9520.7993 |  | 2026-01-29 |  |  |  |  | Luken Solar
1 | [8 empty] | 1 | 1. Panels | Extra Pallet | 1 | 43292.88 | 43292.88 |  | Menlo INV0003160 | 2025-08-31 | 0 |  | 2025-10-16 |  | BUDGET | Installer Allocation
1 | [8 empty] | 1 | 1. Panels | Extra Pallet | 1 | -43292.88 | -43292.88 |  | MSA Energy: CRN0000262 | 2025-11-30 | 0 |  | 2026-01-29 |  | BUDGET | Installer Allocation
[22 empty] | AC Equipment | 2941866.9 |  | Installation of 4MW Roof Mount including electrical work, labour and logistics | 4000000 | 4MW | 1
2 | Inverters | Inverter Budget |  |  | 2760000 | 2025-06-12 | 2760000 | 2982470.7101 | 2 | 2. Inverters | Huawei 330KTL - Deposit 30% | 23 | 108018.0759 | 745324.7237 | PO3991-CSPH2-20250610 - JP Approved | Kathea S19625 | 2025-07-31 | 886426.7728 | -0.00028844 | 2025-06-12 | 2495176.2237 | DC Equipment | 4558110
2 | [8 empty] | 2 | 2. Inverters | Huawei 330KTL - Balance 70% |  |  | 1749851.5 |  | Kathea - 519704 | 2025-07-31 | 2081126.7475 |  | 2025-07-17 |  | AC Labour | 1062060 | 0.15001 | Special lifting equipment
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 3298351.237 | 0.46587 | Elctrical and installation small components (not provided by Emergent) | 550000
2 | [8 empty] | 2 | 2. Inverters | [6 empty] | 2025-08-31 | 14917.19 |  | 2025-06-12 |  | Offloading | 85000
2 | [8 empty] | 2 | 2. Inverters | Huawei SUN2000 HAV5-Inverter Accessories - 330KTL Inverters |  |  | 899.72 |  | Kathea - 500335 | 2025-12-31 | 0 |  | 2026-02-05 |  | Scaffolding | 133245.9 |  | Installation of Ground Mount system:
2 | [8 empty] | 2 | 2. Inverters |  |  |  | -899.72 |  | Kathea - 500335 | 2026-01-31 | 0 |  | 2026-01-31 |  | Storage | 176058.3333
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0 |  | Installation of 3MW Ground Mount including electrical work, labour and logistics (incl. Structures) | 2500000 | 3MW | 0.83333
3 | Mounting Structures | Structure Budget |  |  | 7358785.9097 | 2025-07-29 | 7358785.9097 | 7951943.2744 | 3 | 3. Mounting Structures | IBR short rail - Rooftop | 19830 | 22.88 | 453710.4 | PO3994-CSPH2-20260610 - RV Approved | Schletter - INV1895 | 2025-06-30 | 870407.9227 | 0 | 2025-07-29 | 4071044.26 | Other | 0 |  | Trenching and pipes
3 | [8 empty] | 3 | 3. Mounting Structures | Screws - Rooftop | 39660 | 5.87 | 232804.2 |  | Schletter - INV1895 | 2025-06-30 | 446616.6526 |  | 2025-07-29 |  | Total | 12254692.3703 |  | Elctrical and installation small components (not provided by Emergent) | 590000
[9 empty] | 3 | 3. Mounting Structures | Inner Clamp - 30mm - Rooftop | 18030 | 10.64 | 197183 |  | Schletter - INV1895 | 2025-06-30 | 378280.166 |  | 2025-07-29 |  | Less 15% | 10416488.5148
[9 empty] | 3 | 3. Mounting Structures | End Clamp - 30mm - Rooftop | 1820 | 10.96 | 20391.2 |  | Schletter - INV1895 | 2025-06-30 | 39118.9226 |  | 2025-07-29 |  | R/Wp | 1.4713
[9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[9 empty] | 3 | 3. Mounting Structures | IBR Mounting clamps - Cable Trays | 1983 | 22.88 | 45371.04 |  | Schletter - INV1895 | 2025-06-30 | 87040.7923 |  | 2025-07-29 |  | ACTUAL | Installer Price
[9 empty] | 3 | 3. Mounting Structures | Screws - Cable Trays | 3966 | 5.87 | 23280.42 |  | Schletter - INV1895 | 2025-06-30 | 44661.6653 |  | 2025-07-29 |  | AC Equipment | 2941866.9
[9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | DC Equipment | 4558110
[9 empty] | 3 | 3. Mounting Structures | Freight Charges |  |  | 17564 |  | Schletter - INV1895 | 2025-06-30 | 33695.1605 |  | 2025-07-29 |  | AC Labour | 1770000 | 0.25
[9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  | 2025-09-30 |  | DC Labour | 4602000 | 0.65
[9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  | 2025-09-30 |  | Offloading | 85000
[9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Scaffolding | 133245.9
3 | [8 empty] | 3 | 3. Mounting Structures | Ground mount - Deposit | 3169.44 | 0.97201 | 1540370 | PO3992-CSPH2-20250610 - RV Approved | Schletter : INV1887 | 2025-08-31 | 2955079.3896 |  | 2025-06-19 |  | Storage | 176058.3333
3 | [8 empty] | 3 | 3. Mounting Structures | Ground mount - Balance |  |  | 1540370 |  | Schletter: INV2113 | 2025-08-31 | 2955079.3896 |  | 2025-09-30 |  | Telehandler | 150000
[9 empty] | 3 | 3. Mounting Structures |  |  |  | -1540370 |  | Schletter - CRN0271 | 2025-09-30 | 0 |  | 2025-09-30
[9 empty] | 3 | 3. Mounting Structures |  |  |  | -1540370 |  | Schletter - CRN0272 | 2025-09-30 | 0 |  | 2025-09-30
[9 empty] | 3 | 3. Mounting Structures |  |  |  | 3006740 |  | Schletter - INV2231 | 2025-09-30 | 0 |  | 2025-09-30
3 | [8 empty] | 3 | 3. Mounting Structures | Engineering Signoff - deposit |  |  | 37000 |  | Schletter : INV1887 | 2025-06-30 | 70981.6066 |  | 2025-06-19 |  | HSE | 4500
3 | [8 empty] | 3 | 3. Mounting Structures | Engineering Signoff - balance |  |  | 37000 |  | Schletter: INV2113 | 2025-08-31 | 70981.6066 |  | 2025-09-30 |  | Other | 0
[22 empty] | Other | 0
4 | DC Equipment | DC Cable Budget | 249988 |  | 3499832 | 2025-09-01 | 8057942 | 8707455.0719 | 4 | 4. DC Equipment | DC Cable Budget | 24000 | 0 | 0 |  |  |  | 0 | -0.0047538 |  | 3329187 | Total | 14420781.1333
4 |  | DC Equipment Budget |  |  | 4558110 | 2025-09-01 |  |  | 4 | 4. DC Equipment | DC Cable - Balance to be delivered | 10% | 2376000 | 237600 | PO3993-CSPH2-20260610 - RV Approved | Menlo INV0003003 | 2025-06-30 | 465334.0167 |  | 2025-09-01 |  | R/Wp | 2.0368
[9 empty] | 4 | 4. DC Equipment | DC Cable | 90% |  | 2138400 |  | Menlo INV0003047 | 2025-06-30 | 4188006.1506 |  | 2025-09-01
4 | [8 empty] | 4 | 4. DC Equipment | Jinko Connectors - Male | 500 | 13 | 6500 | PO4154-COEGA-20250723 - RV Approved | Menlo INV0003096 | 2025-07-31 | 13627.7172 |  | 2025-09-25
4 | [8 empty] | 4 | 4. DC Equipment | Jinko Connectors - Female | 500 | 13 | 6500 |  | Menlo INV0003096 | 2025-07-31 | 13627.7172 |  | 2025-09-25
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[9 empty] | 4 | 4. DC Equipment | DC Cable Trays - As Per BOQ |  |  | 370187 | PO4126-CSPH2-20250716 - RV Approved | Advanced Strut INV IN152953 | 2025-07-31 | 1724074.1776 |  | 2025-09-04
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[9 empty] | 4 | 4. DC Equipment | [6 empty] | 2025-08-31 | 1117518.18 |  | 2025-08-31
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | Project Kick Off - Rooftop | 275000 | 50% | 137500 | PO4029-CSPH2-20250624 - RV Approved | Luken Solar Inv: 0654 | 2025-06-30 | 269290.5189 |  | 2025-06-26
4 | [8 empty] | 4 | 4. DC Equipment | DC Equipment Onsite - Rooftop |  | 40% | 110000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 230622.9067 |  | 2025-09-10
4 | [8 empty] | 4 | 4. DC Equipment | End of Defects Period - Rooftop |  | 10% | 27500 |  | Luken Solar Inv 0665 | 2025-08-31 | 71925.9731 |  | 2026-03-19
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | Project Kick Off - Ground Mount | 295000 | 50% | 147500 |  | Luken Solar Inv: 0654 | 2025-06-30 | 288875.284 |  | 2025-06-26
4 | [8 empty] | 4 | 4. DC Equipment | DC Equipment Onsite - Ground Mount |  | 40% | 118000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 247395.4817 |  | 2025-09-10
4 | [8 empty] | 4 | 4. DC Equipment | End of Defects Period - Ground Mount |  | 10% | 29500 |  | Luken Solar Inv 0665 | 2025-08-31 | 77156.9529 |  | 2026-03-19
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 26000 | 2025-07-24 | 64000 | 69158.7411 | 5 | 5. Monitoring | Metering Budget | [6 empty] | 0 | -4.6095 |  | 241577.3
5 |  | Comms DB |  |  | 8000 | 2025-07-24 |  |  | 5 | 5. Monitoring | Janitza UMG604 pro | 1 |  | 19205.5 | PO4129-CSPH2-2020717 - RV Approved | Harmonious Technical - QU100635 | 2025-07-31 | 3006.8452 |  | 2025-07-24
[9 empty] | 5 | 5. Monitoring | Delivery of Janitza |  |  | 264.26 |  | DSV Inv: 180140895 | 2025-07-31 | 41.373 |  | 2025-08-31
5 |  | Revenue Grade Meter |  |  | 30000 | 2025-08-31 |  |  | 5 | 5. Monitoring | Techsitter | 1 |  | 11169 |  | Matriarch - INV-4999 | 2025-08-31 | 26948.87 |  | 2025-08-31 |  | TC: Changed amount - 30k
[9 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 175.56 |  | DSV Inv: 180140895 | 2025-07-31 | 27.486 |  | 2025-08-31
[9 empty] | 5 | 5. Monitoring | Encombi controller complete kit | 1 |  | 95374 | PO4128-CSPH2-20250717 - RV Approved | Kathea Inv: 519753 + 519759 + 519762 | 2025-07-31 | 14931.9127 |  | 2025-09-30
[9 empty] | 5 | 5. Monitoring | Router and CTs |  |  | 15921 | PO4125-COEG-20250716 - RV Approved | AccuEnergy - ASAI-005973 | 2025-07-31 | 2492.6183 |  | 2025-08-30
[9 empty] | 5 | 5. Monitoring | Optic Fiber Installation |  |  | 83760 | PO4506-CSPH2-20251128 - RV Approve | Paul van Vuuren Inv: IOG090 | 2025-12-31 | 17237.1033 |  | 2026-01-15
[9 empty] | 5 | 5. Monitoring |  |  |  | -1980 |  | Paul van Vuuren - CN000217 | 2026-01-31 |  |  | 2026-01-31
[9 empty] | 5 | 5. Monitoring | Meanwell MDR-100-24 | 1 |  | 1060 | PO4259-CSHP2-20250821 - RV Approved | Mantech INV1078143 | 2025-09-30 | 335.8169 |  | 2025-09-04
[9 empty] | 5 | 5. Monitoring | [7 empty] | 0
[9 empty] | 5 | 5. Monitoring | Techsitter - Ground Mount |  |  | 11169 |  | Matriarch - INV-5207 | 2025-10-31 | 3469.3218 |  | 2025-11-13
[9 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 308.98 |  | DSV Inv: 180150385 | 2025-10-31 | 97.7491 |  | 2025-11-30
[9 empty] | 5 | 5. Monitoring | Supply & Delivery - Mode Duplex Fibre Modules |  |  | 1980 |  | Paul Van Vuuren - IOG122 | 2026-01-31 | 566.8343 |  | 2026-02-05
[9 empty] | 5 | 5. Monitoring | AcuRev Energy Meter |  |  | 3170 |  | AccuEnergy - ASAI-007302 | 2026-01-31 | 7.42 |  | 2026-02-28
[9 empty] | 5 | 5. Monitoring | [7 empty] | 0
[9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 2941866.9 | 2025-09-01 | 2941866.9 | 3178997.0515 | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0029871 |  | 2401487
6 | [5 empty] | 2025-09-01 |  |  | 6 | 6. AC Equipment | MCCB Boards |  | 27122.75 | 542455 | PO4115-COEG-20250710 - RV Approved | Eastern Switchgear: 16889 | 2025-07-31 | 819376.5308 |  | 2025-09-01
[9 empty] | 6 | 6. AC Equipment
[9 empty] | 6 | 6. AC Equipment | LV Cable |  |  | 111600 |  | Herholdts - INV1198397 | 2025-12-31 |  |  | 2026-01-29
[9 empty] | 6 | 6. AC Equipment | Contigency | [5 empty] | 2025-08-31 | 720273.72
[9 empty] | 6 | 6. AC Equipment
[9 empty] | 6 | 6. AC Equipment | AC - LV/MV/Earthing Cable |  | 1126388 | 602839 | PO4131-CSPH2-20250717 - RV Approved | ARB : PLZ-3079494 | 2025-07-31 | 586595.3374 |  | 2025-08-31
[9 empty] | 6 | 6. AC Equipment | AC - LV/MV/Earthing Cable - Delivery 1 |  |  | 517469.18 |  | ARB : PLZ-3079420 | 2025-07-31 | 460970.2506 |  | 2025-08-31
[9 empty] | 6 | 6. AC Equipment | AC - LV/MV/Earthing Cable - Delivery 2 |  |  | 6079.82 |  | ARB: PLZ-3079501 | 2025-07-31 | 5915.9976 |  | 2025-08-31
[9 empty] | 6 | 6. AC Equipment
6 | [8 empty] | 6 | 6. AC Equipment | AC Cable Trays |  |  | 51044 |  | Advanced Strut INV56863 | 2025-11-30 | - |  | 2026-01-07
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | Project Kick Off - Rooftop | 275000 | 50% | 137500 | PO4029-CSPH2-20250624 - RV Approved | Luken Solar Inv: 0654 | 2025-06-30 | 136570.2147 |  | 2025-06-26
6 | [8 empty] | 6 | 6. AC Equipment | AC Equipment Onsite - Rooftop |  | 40% | 110000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 107036.0197 |  | 2025-09-10
6 | [8 empty] | 6 | 6. AC Equipment | End of Defects Period - Rooftop |  | 10% | 27500 |  | Luken Solar Inv 0665 | 2025-08-31 | 39048.0346 |  | 2026-03-19
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | Project Kick Off - Ground Mount | 295000 | 50% | 147500 |  | Luken Solar Inv: 0654 | 2025-06-30 | 146502.5939 |  | 2025-06-26
6 | [8 empty] | 6 | 6. AC Equipment | AC Equipment Onsite - Ground Mount |  | 40% | 118000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 114820.4575 |  | 2025-09-10
6 | [8 empty] | 6 | 6. AC Equipment | End of Defects Period - Ground Mount |  | 10% | 29500 |  | Luken Solar Inv 0665 | 2025-08-31 | 41887.8917 |  | 2026-03-19
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | MV Substation | [5 empty] | 12030860.6085 | 12664063.7984 | 7 | 7.MV Substation | Huawei String Inverter Warranty Extensions to 10 years | 30% | 580994.9278 | 174298.4783 | PO3991-CSPH2-20250610 - JP Approved | Kathea S19625 | 2025-08-31 | 312323.7886 | 0.00073706 | 2025-06-12 | 7046627.6127
[9 empty] | 7 | 7.MV Substation | Huawei String Inverter Warranty Extensions to 10 years | 70% |  | 408046.32 |  | Kathea 500008 | 2025-08-31 | 731174.3269 |  | 2025-10-30
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | Huawei Smart Transformers - 6MVA 0.8/22kV - Deposit | 30% | 2874051.1598 | 862215.3479 |  | Kathea S19625 | 2025-11-30 | 1549556.8624 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | Huawei Smart Transformers - 6MVA 0.8/22kV - Balance | 70% |  | 2011835.8118 |  | Kathea 500247 | 2025-11-30 | 3615632.679 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | 6MVA 0.8/22kV - Warranty Extension 5 Years - Deposit | 30% | 247862 | 74358.6 |  | Kathea S19625 | 2025-11-30 | 133635.8477 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | 6MVA 0.8/22kV - Warranty Extension 5 Years - Balance | 70% |  | 173503.4 |  | Kathea 500247 | 2025-11-30 | 311816.9779 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | Huawei Smart Transformers - 3MVA 0.8/22kV - Deposit | 30% | 2317723.4648 | 695317.0394 |  | Kathea S19625 | 2025-11-30 | 1252691.1981 |  | 2025-06-12
7 |  | Huawei Smart Transformers - 6MVA 0.8/22kV |  |  | 12030860.6085 | 2025-10-16 |  |  | 7 | 7.MV Substation | Huawei Smart Transformers - 3MVA 0.8/22kV - Balance | 70% |  | 1622406.4253 |  | Kathea 500247 | 2025-11-30 | 2915757.6655 |  | 2025-11-27
7 |  | Huawei Smart Transformers - 3MVA 0.8/22kV |  |  |  | 2025-10-16 |  |  | 7 | 7.MV Substation | 3MVA 0.8/22kV - Warranty Extension 5 Years - Deposit | 30% | 192585.7416 | 57775.7225 |  | Kathea S19625 | 2025-11-30 | 103833.4187 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | 3MVA 0.8/22kV - Warranty Extension 5 Years - Balance | 70% |  | 134810.0191 |  | Kathea 500247 | 2025-11-30 | 242277.977 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 |  | Huawei String Inverter Warranty Extensions to 10 years |  |  |  | 2025-06-12 |  |  | 7 | 7.MV Substation | Inverter Assecories with Spares | 30% | 242310.0803 | 72693.0241 |  | Kathea S19625 | 2025-11-30 | 130642.5067 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | Transformer Assecories with Spares | 70% |  | 169617.0562 |  | Kathea 500247 | 2025-11-30 | 304832.5155 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | Transformer UPS - Deposit | 30% | 91404.5516 | 27421.3655 |  | Kathea S19625 | 2025-11-30 | 49281.1513 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | Transformer UPS - Balance | 70% |  | 63983.1861 |  | Kathea 500247 | 2025-11-30 | 114989.3531 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | Commissioning Services - Deposit - Kathea | 30% | 519149.9211 | 159507.7663 |  | Kathea S19625 | 2025-11-30 | 286664.2939 |  | 2025-06-12
[9 empty] | 7 | 7.MV Substation | Commissioning Services - Balance - Kathea | 70% |  | 338838.05 |  | Kathea 500247 | 2025-11-30 | 608953.2353 |  | 2025-11-27
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 |  | Huawei Comms Accessories |  |  |  | 2025-10-16 |  |  | 7 | 7.MV Substation | [7 empty] | 0
7 |  | Transformer MV Surge Arrestor |  |  |  | 2025-10-16 |  |  | 7 | 7.MV Substation | [7 empty] | 0
7 |  | Insulation Monitoring |  |  |  | 2025-10-16 |  |  | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
[9 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 | [8 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 | [8 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 | [8 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 | [8 empty] | 7 | 7.MV Substation | [7 empty] | 0
7 | [8 empty] | 7 | 7.MV Substation | [7 empty] | 0
8 | Product Add On | [5 empty] | 2015000 | 2177419.7394 | 8 | 8. Product Add On | [7 empty] | 0 | -0.0042484 |  | 2216118.21
8 |  | Cat Ladders |  |  | 25000 | 2025-08-30 |  |  | 8 | 8. Product Add On | Manufacture & Install Catladder | 78963 | 2 | 157926 | PO4124-COEG-20250716 - RV Approved | The Engineering Hub: INV/2025/07/0546 | 2025-07-31 | 159363.6411 |  | 2025-08-30
8 |  | Walkways |  |  | 540000 | 2025-08-30 |  |  | 8 | 8. Product Add On | Ground mount closure & cages |  |  | 416290 | PO4189-COEG-20250731 - RV Approved | The Engineering Hub - INV/2025/07/0576 | 2025-07-31 | 373906.9051 |  | 2025-08-30
[9 empty] | 8 | 8. Product Add On | Inverter Enclosure |  |  | 49639 |  | The Engineering Hub - INV/2025/07/0558 | 2025-07-31 | 50090.8766 |  | 2025-08-30
[9 empty] | 8 | 8. Product Add On | Inverter Enclosure |  |  | -49639 |  | The Engineering Hub - INV/2025/07/0558 | 2025-08-31 | 0 |  | 2025-08-31
[9 empty] | 8 | 8. Product Add On | Plinths - Deposit | 376996 | 50% | 188498 | PO4179-COEG-20250729 - RV Approved | Bayview Construction: Inv 338202502 | 2025-07-31 | 190213.9459 |  | 2025-11-28
[9 empty] | 8 | 8. Product Add On | Plinths - Balance | 188498 | 50% | 188498 |  | Bayview Construction: Inv 338202502 | 2025-07-31 | 190213.9459 |  | 2025-11-28
[9 empty] | 8 | 8. Product Add On | Walkways |  |  | 264744.74 | PO4030-CSPH2-20250624 - RV Approved | Onvlee - Inv 1050589 | 2025-06-30 | 311742.4606 |  | 2025-06-26
[9 empty] | 8 | 8. Product Add On | Walkway Mounting Kit |  |  | 8911.2 |  | Onvlee - Inv 1050589 | 2025-06-30 | 10493.1241 |  | 2025-06-26
[9 empty] | 8 | 8. Product Add On | Transport |  |  | 500 |  | Onvlee - Inv 1050589 | 2025-06-30 | 588.7604 |  | 2025-06-26
[9 empty] | 8 | 8. Product Add On | Change in scope - Additional Walkway | 5 | 2900 | 56604 | PO4284-CSPH2-20250827 - RV Approved | Onvlee - Inv 01051083 | 2025-08-31 | 37374.0555 |  | 2025-08-28
[9 empty] | 8 | 8. Product Add On
[9 empty] | 8 | 8. Product Add On
[9 empty] | 8 | 8. Product Add On | Anchor Points - Deposit | 282770 | 50% | 141385 | PO4097-COEG-20250708 - RV Approved | EZI Systems - VIN2793 | 2025-07-31 | 142672.0641 |  | 2025-07-17
[9 empty] | 8 | 8. Product Add On | Anchor Points - Balance |  | 50% | 141385 |  | Ezi Systems - VIN2863 | 2025-08-31 | 139002.4202 |  | 2025-09-10
8 |  | Transformer - Consumption Metering |  |  | 250000 | 2025-08-30 |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Cages on stands and plinth for inverters x4 |  |  | 600000 | 2025-08-30 |  |  | 8 | 8. Product Add On | Waterpoints - Ground Mount & Roof |  |  | 50000 |  |  | 2026-02-28 | 47805.1861 |  | 2026-02-28
8 |  | Upfront Fedgroup Fee |  |  | 600000 | 2025-08-30 |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [8 empty] | 8 | 8. Product Add On | Poder forFire Extinguisher |  |  | 1376.27 |  | Transfire Eastern Cape - IN-18217 | 2025-10-31 | 1352.2372 |  | 2025-10-10
8 | [8 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [8 empty] | 8 | 8. Product Add On | Upfront Fedgroup Fee |  |  | 600000 |  | Fedgroup Green - SPVL000487_250731 | 2025-08-31 | 522600.1208 |  | 2026-02-12
9 | AC & DC Installation | AC Installation Budget |  | 0.15172 | 1062060 | 2025-06-26 | 4360411.237 | 5129895.5729 | 9 | 9. AC & DC installation | Rooftop - DC | [6 empty] | 0 | 0.0024784 |  | 8055680
9 |  | DC Installation Budget |  | 0.47119 | 3298351.237 | 2025-06-26 |  |  | 9 | 9. AC & DC installation | Project Kick Off | 2400000 | 17.5% | 420000 | PO4029-CSPH2-20250624 - RV Approved | Luken Solar Inv: 0654 | 2025-06-30 | 326447.9001 |  | 2025-06-26
9 | [8 empty] | 9 | 9. AC & DC installation | Site Establishment | 0.6 | 20% | 480000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 242313.0569 |  | 2025-09-04
9 | [8 empty] | 9 | 9. AC & DC installation | Mounting Structure Installed |  | 20% | 480000 |  | Luken Solar Inv 0665 | 2025-08-31 | 242313.0469 |  | 2025-12-04
9 | [8 empty] | 9 | 9. AC & DC installation | Cable Trays Installed |  | 10% | 240000 |  | Luken Solar Inv 0665 | 2025-08-31 | 152833.1485 |  | 2025-12-04
9 | [8 empty] | 9 | 9. AC & DC installation | Panel Installation Complete |  | 20% | 480000 |  | Luken Solar - INV-0701 | 2026-01-31 | 305666.2969 |  | 2026-01-23
9 | [8 empty] | 9 | 9. AC & DC installation | Stringing Complete |  | 5% | 120000 |  | Luken Solar - INV-0701 | 2026-01-31 | 76416.5742 |  | 2026-01-23
9 | [8 empty] | 9 | 9. AC & DC installation | Snag Completion |  | 5% | 120000 |  | Luken Solar - INV-0701 | 2026-01-31 | 76416.5742 |  | 2026-02-17
9 | [8 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 2.5% | 60000 |  | Luken Solar - INV-0701 | 2026-01-31 | 38208.2871 |  | 2026-03-19
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
[9 empty] | 9 | 9. AC & DC installation | Ground Mount - DC | [6 empty] | 0
[9 empty] | 9 | 9. AC & DC installation | Project Kick Off | 1500000 | 17.5% | 262500 |  | Luken Solar Inv: 0654 | 2025-06-30 | 204029.9376 |  | 2025-06-26
[9 empty] | 9 | 9. AC & DC installation | Site Establishment | 0.5 | 20% | 300000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 191041.4356 |  | 2025-09-04
[9 empty] | 9 | 9. AC & DC installation | Mounting Structure Installed |  | 20% | 300000 |  | Luken Solar Inv 0665 | 2025-08-31 | 191041.4356 |  | 2026-01-22
[9 empty] | 9 | 9. AC & DC installation | Cable Trays Installed |  | 10% | 150000 |  | Luken Solar Inv 0665 | 2025-08-31 | 95520.7178 |  | 2026-01-22
[9 empty] | 9 | 9. AC & DC installation | Panel Installation Complete 75% |  | 15% | 225000 |  | Luken Solar Inv 0665 | 2025-08-31 | 191041.4356 |  | 2025-12-17
[10 empty] | 9. AC & DC installation | Panel Installation Complete - 25% |  | 5% | 75000 |  | Luken Solar Inv 0665 | 2025-08-31 | - |  | 2025-12-24
[9 empty] | 9 | 9. AC & DC installation | Stringing Complete75% |  | 3.75% | 56250 |  | Luken Solar Inv 0665 | 2025-08-31 | 47760.3589 |  | 2025-12-18
[10 empty] | 9. AC & DC installation | Stringing Complete 25% |  | 1.25% | 18750 |  | Luken Solar Inv 0665 | 2025-08-31 |  |  | 2025-12-24
[9 empty] | 9 | 9. AC & DC installation | Snag Completion |  | 5% | 75000 |  | Luken Solar - INV-0701 | 2026-01-31 | 47760.3589 |  | 2026-02-17
[9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 2.5% | 37500 |  | Luken Solar - INV-0701 | 2026-01-31 | 23880.1794 |  | 2026-03-19
[9 empty] | 9 | 9. AC & DC installation
[9 empty] | 9 | 9. AC & DC installation | AC Installation - LV
[9 empty] | 9 | 9. AC & DC installation | Project Kick Off | 1950000 | 17.5% | 341250 |  | Luken Solar Inv: 0654 | 2025-06-30 | 265238.9188 |  | 2025-06-26
[9 empty] | 9 | 9. AC & DC installation | Site Establishment | 0.27857 | 20% | 390000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 248353.8663 |  | 2025-09-04
[9 empty] | 9 | 9. AC & DC installation | Inverter Installation Complete |  | 20% | 390000 |  | Luken Solar Inv 0665 | 2025-08-31 | 248353.8663 |  | 2025-10-09
[9 empty] | 9 | 9. AC & DC installation | PVDB Installation Complete |  | 10% | 195000 |  | Luken Solar Inv 0665 | 2025-08-31 | 124176.9331 |  | 2025-12-18
[9 empty] | 9 | 9. AC & DC installation | AC Cabling & Racking Complete |  | 10% | 195000 |  | Luken Solar Inv 0665 | 2025-08-31 | 248353.8663 |  | 2025-12-24
[9 empty] | 9 | 9. AC & DC installation | AC Cabling & Racking Complete |  | 10% | 195000 |  | Luken Solar Inv 0665 | 2025-08-31 |  |  | 2026-01-29
[9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 5% | 97500 |  | Luken Solar Inv 0665 | 2025-08-31 | 62088.4666 |  | 2026-01-30
[9 empty] | 9 | 9. AC & DC installation | Snag Completion |  | 5% | 97500 |  | Luken Solar - INV-0701 | 2026-01-31 | 62088.4666 |  | 2026-02-17
[9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 2.5% | 48750 |  | Luken Solar - INV-0701 | 2026-01-31 | 31044.2333 |  | 2026-03-28
[9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
[9 empty] | 9 | 9. AC & DC installation | Ground Mount - Pillar Installation | [6 empty] | 0
[9 empty] | 9 | 9. AC & DC installation | Project Kick Off | 2205680 | 25% | 551420 | PO4178-COEG-20250728 - RV Approved | Bayview Construction: Inv 338202501 | 2025-07-31 | 351146.8947 |  | 2025-10-02
[9 empty] | 9 | 9. AC & DC installation | Site Establishment | 3.1154 | 25% | 551420 |  | Bayview Construction: Inv 338202501 | 2025-07-31 | 351146.8947 |  | 2025-10-02
[9 empty] | 9 | 9. AC & DC installation | Installation Complete |  | 20% | 441136 |  | Bayview Construction: Inv 338202501 | 2025-08-31 | 561835.0315 |  | 2025-12-18
[9 empty] | 9 | 9. AC & DC installation |  |  | 10% | 220568 |  | Bayview Construction: Inv 338202501 | 2025-08-31 |  |  | 2025-12-24
[9 empty] | 9 | 9. AC & DC installation |  |  | 10% | 220568 |  | Bayview Construction: Inv 338202501 | 2025-08-31 |  |  | 2025-12-31
[9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 10% | 220568 |  | Bayview Construction: Inv 338202501 | 2025-08-31 | 123377.3879 |  | 2026-01-07
[9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 85000 | 2025-09-25 | 394304.2333 | 463887.3333 | 10 | 10. Site Logistics | [7 empty] | 0 | 0.00059089 |  | 936113.11
10 |  | Scaffolding |  |  | 133245.9 | 2025-09-25 |  |  | 10 | 10. Site Logistics | Omega Security | 82020 | 50% | 41010 | PO4248-CSPH2-20250820 - RV Approved | Omega OM038568 | 2025-08-31 | 0 |  | 2025-09-25
10 |  | Security |  |  | 0 |  |  |  | 10 | 10. Site Logistics |  |  |  | 41010 |  | Omega OM038568 | 2025-08-31 | 0 |  | 2025-11-06
[9 empty] | 10 | 10. Site Logistics |  |  |  | 41010 |  | Omega - OM040496 | 2025-11-30 | 0 |  | 2026-01-15
[9 empty] | 10 | 10. Site Logistics |  |  |  | 41010 |  | Omega - OM040593 | 2025-12-31 | 0 |  | 2026-01-09
10 |  | Storage |  |  | 176058.3333 | 2025-09-25 |  |  | 10 | 10. Site Logistics | Omega Security - January |  |  | 41470 |  | Omega - OM040944 | 2025-12-31 | 790.55 |  | 2026-01-31
[9 empty] | 10 | 10. Site Logistics | Installation of Fuard Secure |  |  | 460 |  | Omega - OMO40594 | 2025-12-31 | 0 |  | 2026-01-09
[9 empty] | 10 | 10. Site Logistics | Installation of Guard Secure
10 | [8 empty] | 10 | 10. Site Logistics | Project Kick Off - Rooftop | 400000 | 50% | 200000 | PO4029-CSPH2-20250624 - RV Approved | Luken Solar Inv: 0654 | 2025-06-30 | 130552.9679 |  | 2025-06-26
10 | [8 empty] | 10 | 10. Site Logistics | Lifting Equipment Onsite - Rooftop |  | 40% | 160000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 105639.017 |  | 2025-09-04
10 | [8 empty] | 10 | 10. Site Logistics | Site De-establisment - Rooftop |  | 10% | 40000 |  | Luken Solar Inv 0665 | 2025-08-31 | 16629.7723 |  | 2026-03-19
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[9 empty] | 10 | 10. Site Logistics | Project Kick Off - Ground Mount | 250000 | 50% | 125000 |  | Luken Solar Inv: 0654 | 2025-06-30 | 81595.605 |  | 2025-06-26
[9 empty] | 10 | 10. Site Logistics | Lifting Equipment Onsite - Ground Mount |  | 40% | 100000 |  | Luken Solar Inv: 0660 | 2025-07-31 | 68657.9656 |  | 2025-09-04
[9 empty] | 10 | 10. Site Logistics | Site De-establisment - Ground Mount |  | 10% | 25000 |  | Luken Solar Inv 0665 | 2025-08-31 | 22162.2102 |  | 2026-03-19
[9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | Container Hire - June |  |  | 10400 |  | Container World PFP9167 | 2025-06-30 | 6788.7543 |  | 2025-06-27
10 | [8 empty] | 10 | 10. Site Logistics | Container Hire - July |  |  | 10400 |  | Container World PFP9174 | 2025-07-31 | 6743.2861 |  | 2025-07-07
10 | [8 empty] | 10 | 10. Site Logistics | Container Hire - August |  |  | 1550 |  | Container World P587568 | 2025-07-31 | 1023.378 |  | 2025-09-01
[9 empty] | 10 | 10. Site Logistics | Container Hire - August |  |  | 11850 |  | Container World PFP911 | 2025-08-31 | 6908.7492 |  | 2025-08-21
10 | [8 empty] | 10 | 10. Site Logistics | Container Hire - September |  |  | 1500 |  | Container World P591046 | 2025-08-31 | 874.5252 |  | 2025-09-30
[9 empty] | 10 | 10. Site Logistics | Container Hire - September - Container 2 |  |  | 1500 |  | Container World P591048 | 2025-08-31 | 874.5252 |  | 2025-09-30
[9 empty] | 10 | 10. Site Logistics | Container Hire |  |  | 250 |  | Container World - P584103 | 2025-06-30 | 163.1912 |  | 2025-08-07
[9 empty] | 10 | 10. Site Logistics | Container Hire |  |  | 2635 |  | Container World - P594608 | 2025-09-30 | 0 |  | 2025-09-30
[9 empty] | 10 | 10. Site Logistics | Container Hire |  |  | 1550 |  | Container World - P594597 | 2025-09-30 | 0 |  | 2025-09-30
[9 empty] | 10 | 10. Site Logistics | Container Hire |  |  | 1550 |  | Container World - P594595 | 2025-09-30 | 0 |  | 2025-09-30
[9 empty] | 10 | 10. Site Logistics | Office Container - Rental |  |  | 595 |  | Container World - PF591061 | 2025-08-31 | 346.895 |  | 2025-09-01
[9 empty] | 10 | 10. Site Logistics | Office Container - Rental |  |  | 1250 |  | Container World - P587570 | 2025-08-31 | 728.771 |  | 2025-09-01
[9 empty] | 10 | 10. Site Logistics | Container Hire - November- Container |  |  | 1500 |  | Container World - P598167 | 2025-10-31 | 865.4216 |  | 2025-11-13
[9 empty] | 10 | 10. Site Logistics | Container Hire - November- Container |  |  | 1500 |  | Container World - P598169 | 2025-10-31 | 865.4216 |  | 2025-11-13
[9 empty] | 10 | 10. Site Logistics | Container Hire - November- Container |  |  | 2550 |  | Container World - P598179 | 2025-10-31 | 1471.2167 |  | 2025-11-13
[9 empty] | 10 | 10. Site Logistics | Container Hire - December - Container 1 |  |  | 1550 |  | Container World - P601672 | 2025-11-30 | 1770.4386 |  | 2025-12-04
[9 empty] | 10 | 10. Site Logistics | Container Hire - December - Container 2 |  |  | 1550 |  | Container World - P601674 | 2025-11-30 | 1770.4386 |  | 2025-12-04
[9 empty] | 10 | 10. Site Logistics | Container Hire - December - Office Container |  |  | 2635 |  | Container World P601684 | 2025-11-30 | 988.1107 |  | 2025-12-04
[9 empty] | 10 | 10. Site Logistics | Container Hire - January - Container 1 |  |  | 1550 |  | Container World P605064 | 2025-12-31 | 0 |  | 2026-01-09
[9 empty] | 10 | 10. Site Logistics | Container Hire - January - Container 2 |  |  | 1550 |  | Container World P605066 | 2025-12-31 | 0 |  | 2026-01-09
[9 empty] | 10 | 10. Site Logistics | Container Hire - January - Office Container |  |  | 2635 |  | Container World P605075 | 2025-12-31 | 0 |  | 2026-01-09
[9 empty] | 10 | 10. Site Logistics | Container Hire - February - Office Container |  |  | 1400 |  | Container World P608429 | 2026-01-31 | 0 |  | 2026-02-05
[9 empty] | 10 | 10. Site Logistics | Container Hire - February - Office Container |  |  | 1400 |  | Container World P608431 | 2026-01-31 | 0 |  | 2026-02-05
[9 empty] | 10 | 10. Site Logistics | Container Hire - February - Office Container |  |  | 2380 |  | Container World P608440 | 2026-01-31 | 0 |  | 2026-02-05
[9 empty] | 10 | 10. Site Logistics
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - August |  |  | 652.17 |  | Talisman Hire:Inv 00211311 | 2025-08-31 | 380.2261 |  | 2025-10-02
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - September |  |  | 2173.92 |  | Talisman Hire:Inv 212767 | 2025-09-30 | 1258.8741 |  | 2025-10-09
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - October |  |  | 3086.97 |  | Talisman Hire:Inv 00214681 + 00214480 | 2025-10-31 | 1781.0204 |  | 2025-11-06
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - November |  |  | 2434.8 |  | Talisman Hire - 00216276 | 2025-11-30 | 1343.3634 |  | 2025-12-04
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - December |  |  | 1217.4 |  | Talisman Hire - 00217594 | 2025-12-31 | 608.425 |  | 2026-01-07
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - December |  |  | 608.7 |  | Talisman Hire - 00217616 | 2025-12-31 | 304.2125 |  | 2026-01-07
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - January |  |  | 1826.1 |  | Talisman Hire - 00218837 | 2026-01-31 | 0 |  | 2026-02-05
[9 empty] | 10 | 10. Site Logistics | Site Ablutions - January |  |  | 913.05 |  | Talisman Hire - 00218853 | 2026-01-31 | 0 |  | 2026-02-05
[9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 300000 | 2025-11-30 | 420000 | 494117.6471 | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 236000 |  |  | 2026-02-28 | 177552.1 | -0.0016991 | 2026-02-28 | 658656
[9 empty] | 11 | 11. Due Dilligence | Technical Review - Onsite inspection and reporting - Final Inspection |  |  | 35600 | PO4372-CSPH2-20251020 - RV Approved |  | 2026-02-28 | 27213.8712 |  | 2026-03-14
[9 empty] | 11 | 11. Due Dilligence | Prelim Onsite Inspection & Snag Reporting |  |  | 28400 | PO4400-CSPH2-20251030 - RV Approved | 2Xtwo - 785 | 2025-11-30 | 21812.4977 |  | 2025-12-04
[9 empty] | 11 | 11. Due Dilligence
[9 empty] | 11 | 11. Due Dilligence | [6 empty] | 2026-01-31 |  |  | 2026-01-31
[9 empty] | 11 | 11. Due Dilligence
[9 empty] | 11 | 11. Due Dilligence
11 |  | Structural Sign Off |  |  | 40000 | 2025-07-03 |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 10400 | PO4075-COEG-20250630 - RV Approved | L&B Consulting INV-2013 | 2025-06-30 | 12174.422 |  | 2025-07-03
11 |  | Grid Study |  |  | 80000 | 2025-07-03 |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 79700 | PO4078-COEG-20250701 - RV Approved | Okusha - EE18 | 2025-10-31 | 58776.0438 |  | 2026-01-09
11 | [8 empty] | 11 | 11. Due Dilligence | Protection Design |  |  | 252556 | PO4180-COEG-20250730 - RV Approved | Okusha EE21 | 2025-07-31 | 184585.6619 |  | 2026-01-31
[9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
[9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
[9 empty] | 11 | 11. Due Dilligence | Red Team Inspection - Dec - 1 |  |  | 8000 |  |  | 2026-02-28 | 6001.5261 |  | 2026-02-28
11 | [8 empty] | 11 | 11. Due Dilligence | Red Team Inspection - Dec - 2 |  |  | 8000 |  |  | 2026-02-28 | 6001.5261 |  | 2026-02-28
12 | BDP Commission | [5 empty] | 205449.8906 | 0 | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | PD Fee |  |  | 205449.8906 | 2025-11-30 |  |  | 12 | 12. BDP Commission | PD Fee |  |  | 0
13 | Engineering | Matriarch Defects Period |  |  | 950000 | 2025-12-31 | 950000 | 1079545.4545 | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 950000 |  |  | 2026-02-28 | 1041836.387 | -195.4771 | 2026-03-31 | 984324.26
13 | [8 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 |  |  | 11372 |  | Matriarch Inv: 5015 | 2025-08-31 | 12657.5711 |  | 2025-08-31
13 | [8 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 - Sept |  |  | 2843 |  | Matriarch Inv: 5050 | 2025-09-30 | 3164.3928 |  | 2025-08-31
13 | [8 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 - Oct |  |  | 2843 |  | Matriarch Inv: 5241 | 2025-10-31 | 3108.9043 |  | 2025-11-28
13 | [8 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 - Nov |  |  | 2843 |  | Matriarch - INV-5464 | 2025-11-30 | 3155.1443 |  | 2025-12-30
[9 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 - Dec |  |  | 2843 |  | Matriarch - INV-5801 | 2025-12-31 | 3118.0251 |  | 2026-01-29
[9 empty] | 13 | 13. Engineering | Matriarch O & M Fee - Phase 1 - Jan |  |  | 2843 |  | Matriarch - INV-6102 | 2026-01-31 | 3118.0251 |  | 2026-02-28
[9 empty] | 13 | 13. Engineering | Panel Clean |  |  | 8737.26 |  | Matriarch - INV-6216 | 2026-01-31 | 9582.4818 |  | 2026-02-28
13 | [8 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 0 | 2025-06-09 | 0 | 0 | 14 | 14. General Expenses | Travel |  |  | 6509.86 |  | Expense Claim | 2025-05-31 | 0 | 0 | 2025-06-09 | 273188.38
14 | [5 empty] | 2025-07-04 |  |  | 14 | 14. General Expenses | Travel |  |  | 5770.84 |  | Expense Claim | 2025-06-30 | 0 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  | 14 | 14. General Expenses | Travel |  |  | 21295.98 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-08-07
14 | [5 empty] | 2025-09-05 |  |  | 14 | 14. General Expenses | Travel |  |  | 50534.6 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 32154.96 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 20629.91 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 15266.94 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 59700.29 |  | Expense Claim | 2025-12-31 | 0 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 30662.5 |  |  | 2026-01-31 | 0 |  | 2026-01-31
14 | [5 empty] | 2026-02-28 |  |  | 14 | 14. General Expenses | Travel |  |  | 30662.5 |  |  | 2026-02-28 | 0 |  | 2026-02-28
14 | [8 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [8 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 | 15 | 15. Service Add On | [8 empty] | 0 |  | 2249043.01
15 | [8 empty] | 15 | 15. Service Add On | CDC Fee | [5 empty] | 2025-12-31 |  |  | 2025-12-31
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 140.75 | PO4554-CSPH2-20260116 - RV Approved | Coega Development Corporation INV78403 | 2026-01-31 |  |  | 2026-01-19
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 3127.77 | PO4216-COEG-20250812 - RV Approved | Coega Development Corporation INV 76004 | 2025-08-31 |  |  | 2025-08-14
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 1495.89 | PO4232-COEG-20250818 - RV Approved | Coega Development Corporation - QUO0005126 | 2025-08-31 |  |  | 2025-08-19
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 407.97 | PO4249-CSPH2-20250820 - RV Approved | Coega Development Corporation INV 76087 | 2025-08-31 |  |  | 2025-08-21
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 951.93 | PO4281-CSPH2-20250826 - RV Approved | Coega Development Corporation INV 76267 | 2025-08-31 |  |  | 2025-09-01
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 135.99 | PO4303-CSPH2-20250909 - RV Approved | Coega Development Corporation INV76502 | 2025-09-30 |  |  | 2025-09-10
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 2719.8 | PO4323-CSPH2-20250922 - RV Approved | Coega Development Corporation INV76691 | 2025-09-30 |  |  | 2025-09-23
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 271.98 | PO4324-CSPH2-20250925 - RV Approved | Coega Development Corporation INV76718 | 2025-09-30 |  |  | 2025-09-30
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 271.98 | PO4344-CSPH2-20250930 - RV Approved | Coega Development Corporation INV76726 | 2025-09-30 |  |  | 2025-09-30
15 | [8 empty] | 15 | 15. Service Add On | Evaluation of fitness certificates |  |  | 271.98 | PO4351-CSPH2-20251002 - RV Approved | Coega Development Corporation INV76801 | 2025-10-31 |  |  | 2025-10-02
15 | [8 empty] | 15 | 15. Service Add On | Labour Management Fee |  |  | 12722.45 | PO4399-CSPH2-20251023 - RV Approved | Coega Development Corporation INV76861 | 2025-10-31 |  |  | 2025-10-30
15 | [8 empty] | 15 | 15. Service Add On | Labour Management Fee |  |  | 14381.9 | PO4446-CSPH2-20251106 - RV Approved | Coega Development Corporation - INV77241 | 2025-11-30 |  |  | 2025-12-18
[9 empty] | 15 | 15. Service Add On | Labour Management Fee |  |  | 9126.98 |  | Coega Development Corporation - INV77755 | 2025-11-30 |  |  | 2025-12-04
[9 empty] | 15 | 15. Service Add On | Labour Management Fee |  |  | 1936.03 | PO4550-CSPH2-20260112 - RV Approved | Coega Development Corporation - INV78326 | 2026-01-31 |  |  | 2026-01-29
[9 empty] | 15 | 15. Service Add On | Labour Management Fee |  |  | 5215.61 | PO4613-CSPH2-20260206 - RV Approved |  | 2026-02-28 |  |  | 2026-02-28
[9 empty] | 15 | 15. Service Add On
[9 empty] | 15 | 15. Service Add On
[9 empty] | 15 | 15. Service Add On | courier of Utility Meter |  |  | 319.09 |  | DSV Inv: 180157893 | 2025-12-31 |  |  | 2026-01-29
[9 empty] | 15 | 15. Service Add On
[9 empty] | 15 | 15. Service Add On
15 | [8 empty] | 15 | 15. Service Add On
15 | [8 empty] | 15 | 15. Service Add On | Directional Drilling |  |  | 160210.05 | PO4417-CSPH2-20251028 - RV Approved | Alpha Omega Inv 102784 | 2025-11-30 |  |  | 2025-12-12
15 | [8 empty] | 15 | 15. Service Add On | 5000L Water |  |  | 1200 | PO4371-CSPH2-20251015 - RV Approved | Ultimate Soltions INV 2636 | 2025-10-31 |  |  | 2025-10-16
15 | [8 empty] | 15 | 15. Service Add On | 5000L Water |  |  | 1200 | PO4419-CSPH2-20251029 - RV Approved | Ultimate Soltions INV 2647 | 2025-12-31 |  |  | 2025-12-12
15 | [8 empty] | 15 | 15. Service Add On | 5000L Water |  |  | 1200 | PO4473-CSPH2-20251114 - RV Approved | Ultimate Soltions INV 2667 | 2026-01-31 |  |  | 2026-01-29
15 | [8 empty] | 15 | 15. Service Add On | 5000L Water |  |  | 1200 | PO4512-CSPH2-20251201 - RV Approved |  | 2026-02-28 |  |  | 2026-01-31
[9 empty] | 15 | 15. Service Add On | 5000L Water |  |  | 1200 | PO4531-CSPH2-20251209 - RV Approved |  | 2026-02-28 |  |  | 2026-02-14
15 | [8 empty] | 15 | 15. Service Add On | 240mm Alu XLPE 22kV - Tie In - TBC | 270 | 1005.8 | 271566 |  |  | 2026-03-31 |  |  | 2026-03-31
15 | [8 empty] | 15 | 15. Service Add On | 240mm Alu XLPE 22kV - Ground Mount Transforme - TBC | 85 | 1005.8 | 85493 |  |  | 2026-03-31 |  |  | 2026-03-31
15 | [8 empty] | 15 | 15. Service Add On | Labour - TBC |  |  | 250000 |  |  | 2026-03-31 |  |  | 2026-03-31
[9 empty] | 15 | 15. Service Add On
15 | [8 empty] | 15 | 15. Service Add On | Delay Damages |  |  | 1151150.17 |  |  | 2026-02-28 |  |  | 2026-02-28
15 | [8 empty] | 15 | 15. Service Add On | Coega Steel PH2 - December 2025 Interest |  |  | 271125.69 |  | Fedgroup - LT000589_251231 | 2026-01-31 |  |  | 2026-01-29
15 | [8 empty] | 15 | 15. Service Add On
15 | [8 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 14537831.3 |  | 15101045.6054
| Inverter Procurement Budget | 2760000 |  | 2982470.7101
| Mounting Structure Budget | 7358785.9097 |  | 7951943.2744
| DC Equipment Budget | 8057942 |  | 8707455.0719
| AC Equipment Budget | 2941866.9 |  | 3178997.0515
| Monitoring Budget | 64000 |  | 69158.7411 | [7 empty] | Target Comm Date | 2025-11-21
| Optional Extras Budget | 565000 |  | 610542.0113 | [7 empty] | Updated Comm Date | 2025-12-15
| MV Metering Budget | 250000 |  | 270151.3324 | [7 empty] | Delayed Days | 24
| ADD ON | 1200000 |  | 1296726.3957
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 1062060 |  | 1249482.3529
| DC Installer Budget | 3298351.237 |  | 3880413.22
| In-House Expense Budget | 950000 |  | 1079545.4545
| Compliance Budget | 420000 |  | 494117.6471
| Offloading Budget | 85000 |  | 100000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 176058.3333 |  | 207127.451
| On Site Security | 0 |  | 0
| Roof Access Budget for Installers | 133245.9 |  | 156759.8824
| EPC Management Fee | 0 |  | 0
| MV Substation Budget | 12030860.6085 |  | 12664063.7984
Expenses
| Total EE Expense Budget | 0 |  | 0
Note on Q25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown, fiollowing the discussion in December, was this returned to Kathea?
Note on W64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter is this payment date correct?
Note on W69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter same here
Note on Q87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown when is this due for payment?
Note on W112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter same here
Note on W117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter same here
Note on H177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @mizelda, please update the payment date
Note on W188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter has these been achieved last week?
Note on W190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: This should move out @Roedolph Venter
Note on W196: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter lets please pay only 7 days after completion
Note on W202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter this needs to move out
Note on W211: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter these can move out as well
Note on S232: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter what is happening here
Note on H236: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W236: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on H277: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs please add payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 59995000 | 59995000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17998500 | 0 | 0 | 0 | 0 | 8998000 | 0 | 0 | 0 | 8999250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999500 | 0 | 0 | 2999750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 32998500 | 32998500 | 32998500 | 32998500 | 32998500 | 41996500 | 41996500 | 41996500 | 41996500 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 56995250 | 56995250 | 56995250 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000
| Planned Expenditure | 56096452.0791 | 56096452.0791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760000 | 14537831.3 | 4360411.237 | 120000 | 0 | 0 | 34000 | 7358785.9097 | 0 | 0 | 0 | 2045000 | 10999808.9 | 0 | 0 | 394304.2333 | 0 | 0 | 12030860.6085 | 0 | 0 | 0 | 0 | 0 | 505449.8906 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760000 | 17297831.3 | 21658242.537 | 21778242.537 | 21778242.537 | 21778242.537 | 21812242.537 | 29171028.4467 | 29171028.4467 | 29171028.4467 | 29171028.4467 | 31216028.4467 | 42215837.3467 | 42215837.3467 | 42215837.3467 | 42610141.5801 | 42610141.5801 | 42610141.5801 | 54641002.1886 | 54641002.1886 | 54641002.1886 | 54641002.1886 | 54641002.1886 | 54641002.1886 | 55146452.0791 | 55146452.0791 | 55146452.0791 | 55146452.0791 | 55146452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791 | 56096452.0791
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 12240000 | -2297831.3 | -6658242.537 | -6778242.537 | -6778242.537 | -6778242.537 | 11186257.463 | 3827471.5533 | 3827471.5533 | 3827471.5533 | 3827471.5533 | 10780471.5533 | -219337.3467 | -219337.3467 | -219337.3467 | 8385608.4199 | 8385608.4199 | 8385608.4199 | -3645252.1886 | -3645252.1886 | -3645252.1886 | -3645252.1886 | -3645252.1886 | 2354247.8114 | 1848797.9209 | 1848797.9209 | 4848547.9209 | 4848547.9209 | 4848547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209 | 3898547.9209
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 59995000 | 59995000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 17998500 | 0 | 0 | 0 | 0 | 8998000 | 0 | 0 | 8999250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49840.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5949659.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 32998500 | 32998500 | 32998500 | 32998500 | 32998500 | 41996500 | 41996500 | 41996500 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 50995750 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 51045590.7304 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 56995250 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000 | 59995000
| Actual + Planned Expenditure | 48694198.3664 | 48694198.3664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875421.9278 | 2950967.6 | 2203305.94 | 16170.84 | 10400 | 1891236.5 | 19205.5 | 990304.26 | 21545.98 | 3127.77 | 13753.86 | 1798952.82 | 4774583.53 | 597520.99 | 0 | 1513895.8522 | 2711787.11 | 425705.15 | 3941564.88 | 0 | 420768.77 | 64726.88 | 16719 | 0 | 4895141.9286 | 780963.72 | 161410.05 | 931767.9 | 509318 | 223411 | 2146674.1078 | 1131449.1304 | 2327737.959 | 3998473.0006 | 10798.87 | 601200 | 292500 | 1503778.54 | 0 | 35600 | 276500 | 48750 | 1557059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875421.9278 | 5826389.5278 | 8029695.4678 | 8045866.3078 | 8056266.3078 | 9947502.8078 | 9966708.3078 | 10957012.5678 | 10978558.5478 | 10981686.3178 | 10995440.1778 | 12794392.9978 | 17568976.5278 | 18166497.5178 | 18166497.5178 | 19680393.37 | 22392180.48 | 22817885.63 | 26759450.51 | 26759450.51 | 27180219.28 | 27244946.16 | 27261665.16 | 27261665.16 | 32156807.0886 | 32937770.8086 | 33099180.8586 | 34030948.7586 | 34540266.7586 | 34763677.7586 | 36910351.8664 | 38041800.9969 | 40369538.9559 | 44368011.9564 | 44378810.8264 | 44980010.8264 | 45272510.8264 | 46776289.3664 | 46776289.3664 | 46811889.3664 | 47088389.3664 | 47137139.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664 | 48694198.3664
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2875421.9278 | 9173610.4722 | 6970304.5322 | 6954133.6922 | 6943733.6922 | 5052497.1922 | 23031791.6922 | 22041487.4322 | 22019941.4522 | 22016813.6822 | 22003059.8222 | 29202107.0022 | 24427523.4722 | 23830002.4822 | 32829252.4822 | 31315356.63 | 28603569.52 | 28177864.37 | 24236299.49 | 24236299.49 | 23815530.72 | 23750803.84 | 23734084.84 | 23734084.84 | 18838942.9114 | 18057979.1914 | 17946409.8718 | 17014641.9718 | 16505323.9718 | 16281912.9718 | 14135238.864 | 13003789.7336 | 10676051.7746 | 6677578.774 | 6666779.904 | 12015239.1736 | 11722739.1736 | 10218960.6336 | 10218960.6336 | 10183360.6336 | 9906860.6336 | 9858110.6336 | 8301051.6336 | 8301051.6336 | 8301051.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336 | 11300801.6336
|  | CHECK | CHECK
| Revenue Recognition | -5200.0907 | 60000200.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8815197.7095 | 0 | 0 | 0 | 25270274.7904 | 0 | 0 | 0 | 12183550.8504 | 0 | 0 | 0 | 0 | 4759.0838 | 0 | 0 | 0 | 71787.3366 | 0 | 0 | 0 | 11651405.6756 | 0 | 0 | 0 | 0 | 22058.3159 | 0 | 0 | 0 | 674755.732 | 0 | 0 | 0 | 1306410.5966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 60000200.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8815197.7095 | 8815197.7095 | 8815197.7095 | 8815197.7095 | 34085472.4999 | 34085472.4999 | 34085472.4999 | 34085472.4999 | 46269023.3504 | 46269023.3504 | 46269023.3504 | 46269023.3504 | 46269023.3504 | 46273782.4342 | 46273782.4342 | 46273782.4342 | 46273782.4342 | 46345569.7707 | 46345569.7707 | 46345569.7707 | 46345569.7707 | 57996975.4463 | 57996975.4463 | 57996975.4463 | 57996975.4463 | 57996975.4463 | 58019033.7622 | 58019033.7622 | 58019033.7622 | 58019033.7622 | 58693789.4942 | 58693789.4942 | 58693789.4942 | 58693789.4942 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907 | 60000200.0907

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  |  | 15101045.6054 | 0 |  |  | 0 |  | 0 |  |  |  | 15101045.6054
2. Inverters |  |  |  | 2967553.5203 | 14917.19 |  |  |  | 0 | 0 |  |  |  | 2982470.7103
3. Mounting Structures | 0 |  | 1970802.8886 |  | 5981140.3858 | 0 |  |  |  | 0 |  |  |  | 7951943.2744
4. DC Equipment | 0 |  | 5211505.9702 | 2229348.0004 | 1266601.106 |  |  |  |  | 0 |  |  |  | 8707455.0766
5. Monitoring | 0 |  |  | 20500.2352 | 26948.87 | 335.8169 | 3567.0709 |  | 17982.3133 | 0 | 0 |  |  | 69334.3062
6. AC Equipment | 0 |  | 283072.8086 | 2094714.5937 | 801209.6463 |  |  | 0 |  | 0 |  |  |  | 3178997.0485
8. Product Add On |  |  | 322824.3452 | 1106461.3786 | 698976.5966 |  | 1352.2372 |  |  | 0 | 47805.1861 |  |  | 2177419.7437
9. AC & DC installation | 0 |  | 795716.7565 | 1384002.1482 | 2288695.695 |  |  |  |  | 0 | 568348.2709 | 62088.4666 | 31044.2333 | 5129895.5705
10. Site Logistics | 0 |  | 219100.5184 | 182063.6467 | 48905.6742 | 1258.8741 | 4983.0804 | 5872.3514 | 1703.1875 | 0 |  |  |  | 463887.3327
11. Due Dilligence | 0 |  | 12174.422 | 184585.6619 |  |  | 58776.0438 | 21812.4977 |  |  | 1369.983 | 12003.0522 |  | 290721.6606
13. Engineering |  |  |  |  | 12657.5711 | 3164.3928 | 3108.9043 | 3155.1443 | 3155.1443 | 0 |  | 1054304.2998 |  | 1079545.4568
14. General Expenses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
15. Service Add On
12. BDP Commission
7.MV Substation | 0 |  |  |  | 1043498.1155 |  |  | 11620565.6821 |  | 0 |  |  |  | 12664063.7977
Grand Total | 0 | 0 | 8815197.7095 | 25270274.7904 | 12183550.8504 | 4759.0838 | 71787.3366 | 11651405.6756 | 22840.6452 | 0 | 617523.44 | 1128395.8186 | 31044.2333 | 59796779.5833
|  |  | 8815197.71 | 25270274.79 | 12183550.85
|  |  | -0.00050674 | 0.00043057 | 0.00043024

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  |  | 13735976 | 43292.88 |  |  | -43292.88 | [5 empty] | 13735976
2. Inverters |  |  |  | 2495176.2237 |  |  |  |  | 899.72 |  |  |  |  | 2496075.9437
3. Mounting Structures |  |  | 1027304.26 |  | 3117740 | -74000 | [7 empty] | 4071044.26
4. DC Equipment | 0 |  | 2661000 | 611187 | 57000 | [8 empty] | 3329187
5. Monitoring |  |  |  | 130940.32 | 11169 | 1060 | 11477.98 |  | 83760 |  | 1980 |  |  | 240387.3
6. AC Equipment |  |  | 285000 | 1896843 | 57000 |  |  | 51044 | 111600 |  |  |  |  | 2401487
8. Product Add On |  |  | 274155.94 | 1142236 | 748350 |  | 1376.27 |  |  |  | 50000 |  |  | 2216118.21
9. AC & DC installation |  |  | 1023750 | 2272840 | 3720340 | [5 empty] | 892500 | 97500 | 48750 | 8055680
10. Site Logistics |  |  | 335650 | 271950 | 164367.17 | 7908.92 | 8636.97 | 49179.8 | 90501.1 |  |  |  |  | 928193.96
11. Due Dilligence |  |  | 10400 | 252556 |  |  | 79700 | 28400 |  |  | 271600 | 16000 |  | 658656
13. Engineering |  |  |  |  | 11372 | 2843 | 2843 | 2843 | 2843 |  |  | 950000 |  | 972744
14. General Expenses |  | 6509.86 | 5770.84 | 21295.98 | 50534.6 | 32154.96 | 20629.91 | 15266.94 | 59700.29 |  | 30662.5 | 30662.5 |  | 273188.38
15. Service Add On | 607059 |  |  |  | 5983.56 | 3399.75 | 14194.43 | 183718.93 | 1519.09 |  | 1158806.95 |  |  | 1974681.71
12. BDP Commission | [9 empty] | 0 |  |  |  | 0
7.MV Substation |  |  |  |  | 582344.7983 |  |  | 6464282.8144 | [5 empty] | 7046627.6127
Grand Total | 607059 | 6509.86 | 5623031.04 | 22831000.5237 | 8569494.0083 | -26633.37 | 138858.56 | 6751442.6044 | 350823.2 | 0 | 2405549.45 | 1094162.5 | 48750 | 48400047.3764
4704545
918486.04

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Coega Steels Phase 2
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.03925 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.020079 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.013584 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.032508 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Coega Steels Phase 2 |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Coega Steels Phase 2 | 0 | 0 | 0