## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-01-26 | 2026-01-26
| PROJECT PLAN | Meraki Phase 3 |  |  | 3. Construction | 3. Construction |  |  |  | 0 | 1
| PROJECT SIZE (kWp) | 90
| PROJECT DEVELOPER | Kirsten Marwick
| PROJECT MANAGERS | Kashmil Samuel
| CONTRACT VALUE | 1044632.7242
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status |  | Comment
|  |  | 15 |  |  | 29 |  | 100% | 100%
1 | Project Initiation | 2025-01-27 | 30 | 2025-02-26 | 2025-01-27 | 23 | 2025-02-19 | 100% | 100% | 23
1.1 | BD Handover | 2025-01-27 | 1 | 2025-01-28 | 2025-01-27 | 1 | 2025-01-28 | 100% | 100%
1.2 | Project Introduction | 2025-02-10 | 1 | 2025-02-11 | 2025-02-10 | 1 | 2025-02-11 | 100% | 100%
1.3 | HSE | 2025-02-10 | 12 | 2025-02-26 | 2025-02-10 | 7 | 2025-02-19 | 100% | 100%
1.4 | Installer Kick Off | 2025-02-10 | 1 | 2025-02-11 | 2025-02-10 | 1 | 2025-02-11 | 100% | 100%
1.5 | Project Review | 2025-02-10 | 1 | 2025-02-11 | 2025-02-10 | 1 | 2025-02-11 | 100% | 100%
2 | Site Establishment | 2025-02-17 | 1 | 2025-02-18 | 2025-02-17 | 1 | 2025-02-18 | 100% | 100% | 1
2.1 | Installer on site & Roof Assessment | 2025-02-17 | 1 | 2025-02-18 | 2025-02-17 | 1 | 2025-02-18 | 100% | 100% | 1 |  | 22 | Net Work Days
3 | AC Installation | 2025-02-10 | 16 | 2025-02-26 | 2025-02-10 | 23 | 2025-03-05 | 100% | 100% | 23 |  | 4.4 | Total Weeks
3.1 | Inverters delivered | 2025-02-18 | 1 | 2025-02-19 | 2025-02-18 | 1 | 2025-02-19 | 100% | 100% |  |  | 20.4545 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-02-18 | 5 | 2025-02-25 | 2025-02-20 | 1 | 2025-02-21 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-02-10 | 10 | 2025-02-24 | 2025-02-10 | 10 | 2025-02-24 | 100% | 100%
3.4 | AC Works | 2025-02-19 | 5 | 2025-02-26 | 2025-02-19 | 10 | 2025-03-05 | 100% | 100%
3.5 | AC Tie-In | 2025-02-19 | 1 | 2025-02-20 | 2025-02-19 | 1 | 2025-02-20 | 100% | 100%
4 | DC Works | 2025-02-17 | 9 | 2025-02-26 | 2025-02-18 | 15 | 2025-03-05 | 100% | 100% | 15
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-02-18 | 1 | 2025-02-19 | 2025-02-18 | 1 | 2025-02-19 | 100% | 100%
4.2 | Mounting Structure installation | 2025-02-17 | 4 | 2025-02-21 | 2025-02-20 | 2 | 2025-02-24 | 100% | 100%
4.3 | DC Cable delivered | 2025-02-18 | 1 | 2025-02-19 | 2025-02-18 | 1 | 2025-02-19 | 100% | 100%
4.3 | DC Stringing | 2025-02-24 | 2 | 2025-02-26 | 2025-03-03 | 2 | 2025-03-05 | 100% | 100%
5 | Module installation | 2025-02-17 | 10 | 2025-02-27 | 2025-02-17 | 17 | 2025-03-06 | 100% | 100% | 1900-01-16
5.1 | Module delivery | 2025-02-17 | 1 | 2025-02-18 | 2025-02-17 | 1 | 2025-02-18 | 100% | 100%
5.2 | Module mounting | 2025-02-21 | 4 | 2025-02-27 | 2025-02-24 | 8 | 2025-03-06 | 100% | 100%
6 | Commissioning | 2025-02-27 | 5 | 2025-03-04 | 2025-03-06 | 12 | 2025-03-18 | 100% | 100% | 12
6.1 | Commissioning | 2025-02-27 | 1 | 2025-02-28 | 2025-03-06 | 4 | 2025-03-12 | 100% | 100%
6.2 | Practical Completion | 2025-02-28 | 2 | 2025-03-04 | 2025-03-12 | 4 | 2025-03-18 | 100% | 100%
7 | QA Inspections | 2025-03-04 | 2 | 2025-03-06 | 2025-03-18 | 2 | 2025-03-20 | 100% | 100% | 1900-01-01
7.1 | Red-Team Inspection | 2025-03-04 | 2 | 2025-03-06 | 2025-03-18 | 2 | 2025-03-20 | 100% | 100%
8 | Project Closure | 2025-03-06 | 32 | 2025-04-07 | 2025-03-20 | 180 | 2025-09-16 | 100% | 100% | 1900-06-28
8.1 | Equipment serial numbers | 2025-03-06 | 2 | 2025-03-10 | 2025-03-20 | 2 | 2025-03-25 | 100% | 100%
8.2 | Snags completion | 2025-03-06 | 5 | 2025-03-13 | 2025-05-26 | 70 | 2025-09-02 | 100% | 100% |  | Solar Edge issues dragging this out
8.3 | System Performance Monitoring | 2025-03-13 | 5 | 2025-03-20 | 2025-09-02 | 5 | 2025-09-09 | 100% | 100%
8.4 | Handover documentation | 2025-03-20 | 10 | 2025-04-04 | 2025-09-09 | 5 | 2025-09-16 | 100% | 100%
8.5 | Handover to Client | 2025-04-04 | 1 | 2025-04-07 | 2025-09-09 | 1 | 2025-09-02 | 100% | 100%
8.6 | Handover to Matriarch | 2025-03-15 | 5 | 2025-03-24 | 2025-09-04 | 5 | 2025-09-11 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]+14
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]+14
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 1044632.7242 |  | 1057829.0842 |  |  | 1044632.7242 | Start Date | 1044632.7292 | 927180.2791 | 0 | 75367.05 | 0 | 135478.44
2 | Planned Expenditure | 847370.2249 |  | 1002547.3291 | VO PM Limit | Current VO Total | 787579.3091 | 2025-02-17
3 | Planned Profit | 197262.4994 |  | 55281.7552 | 9863.125 | 204098.11 | 257053.4152 | End Date - PC
4 | Planned Margin | 18.88% |  | 5.226% |  |  | 24.61% | 2025-03-04
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 50% | 522316.3621 |  | 2025-02-28 | 004673 | 2025-02-10 | 2025-03-04
2 | Delivery of Panels |  | 10% | 104463.2724 |  | 2025-03-19 | 004673 | 2025-02-10 | 2025-03-04
3 | Delivery of Inverters |  | 25% | 261158.1811 |  | 2025-03-20 | 004673 | 2025-02-10 | 2025-03-04
4 | Practical Completion |  | 10% | 104463.2724 |  | 2025-04-03 | 004673 | 2025-02-10 | 2025-04-25
5 | Handover |  | 5% | 52231.6362 |  | 2025-05-07 | 004673 | 2025-02-10 | 2025-06-06
6 | VO - Panels |  | 0% | 13196.36 |  |  | 004859 | 2025-10-28 | 2025-11-13
7 | - |  | 0% | 0
|  |  | 100% | 1057829.0842
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 370240.1795
2 | Delivery of Panels |  | 30% | 317348.7253
3 | Delivery of Inverters |  | 20% | 211565.8168
4 | Practical Completion |  | 10% | 105782.9084
5 | Handover |  | 5% | 52891.4542
| Total |  | 100% | 1057829.0842
|  |  | 100% | 1057829.0842

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | ACTUAL | Difference from costed
| EXPENDITURE |  | 847370.2249 |  | 1002547.3291 | -155177.1042
| No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 253134.902 |  | 195122.27 | 58012.632
| 2 | Inverters | 170482 |  | 153956.99 | 16525.01
| 3 | Mounting Structures | 36036 |  | 29609.2 | 6426.8
| 4 | DC Equipment | 71361.4 |  | 84100 | -12738.6
| 5 | Monitoring | 0 |  | 7644.95 | -7644.95
| 6 | AC Equipment | 140010.5522 |  | 128120 | 11890.5522
| 7 | Battery Systems | 0 |  | 0 | 0
| 8 | Product Add On | 0 |  | 37066.62 | -37066.62
| 9 | AC & DC Installation | 73727.5 |  | 97233 | -23505.5
| 10 | Site Logistics | 49813.3 |  | 33725.02 | 16088.28
| 11 | Due Dilligence | 11000 |  | 22160 | -11160
| 12 | BDP Commission | 0 |  | 0 | 0
| 13 | Engineering | 40229.5707 |  | 13057.9091 | 27171.6616 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 1575 |  | 14965.26 | -13390.26
| 15 | Service Add On | 0 |  | 185786.11 | -185786.11
|  | check: | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 847370.2249 | 1044632.7242 | ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | FINANCE ONLY |  |  |  |  | 1002547.3291
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | COMMENTS
1 | Panels | Longi 555W | 154 | 1513.863 | 233134.902 | 2025-03-19 | 253134.902 | 316418.6275 | 1 | 1. Panels | Longi 605W | 149 | 1203.95 | 179388.55 | PO3604-MER-20250130 - RV Approved | Krannich Inv 15-10011770 | 2025-02-28 | 316418.6275 | 0 | 2025-04-24 | 195122.27 |  | 19
1 | [8 empty] | 1 | 1. Panels |  |  | 1.99 |  |  |  |  | 0 |  |  |  |  | BUDGET | Installer Allocation
1 |  | Delivery |  |  | 20000 | 2025-03-19 |  |  | 1 | 1. Panels |  |  |  | 1217.72 |  | Krannich - 15-10013493 | 2025-08-31 | 0 |  | 2025-10-31 |  |  | AC Equipment | 140010.5522
1 | [8 empty] | 1 | 1. Panels |  |  |  | 14516 |  | Krannich -15-10013950 | 2025-09-30 | 0 |  | 2025-11-28 |  |  | DC Equipment | 48261.4
1 | [8 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | AC Labour | 22522.5
1 | [8 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | DC Labour | 51205
[23 empty] | Offloading | 8500
2 | Inverters | Solar Edge 100kW | 1 | 72384 | 72384 | 2025-03-20 | 170482 | 213102.5 | 2 | 2. Inverters | Solar Edge 100kW (Inverter) | 1 | 19380 | 19380 | PO3651-MER-20250212 - RV Approved | Herholdts - INV1004506 | 2025-02-28 | 25962.95 | 0 | 2025-03-28 | 153956.99 |  | Roof Access/Scaffolding | 19713.3
2 | [8 empty] | 2 | 2. Inverters | Synergy Units | 3 | 16020 | 48060 |  | Herholdts - INV1004506 | 2025-02-28 | 64384.9007 |  | 2025-03-28 |  |  | Storage | 0
2 |  | S1200 Optimisers | 77 | 1274 | 98098 | 2025-03-20 |  |  | 2 | 2. Inverters | S1200 Optimisers | 77 | 1190 | 91630 |  | Herholdts - INV1004506 | 2025-02-28 | 122754.6494 |  | 2025-03-28 |  |  | Telehandler | 0
[9 empty] | 2 | 2. Inverters | Delivery of Optimizers |  |  | 296.99 |  | DSV Inv: 180130292 | 2025-05-31 | 0 |  | 2025-06-27
[9 empty] | 2 | 2. Inverters | RMA 100kW Inverter |  |  | -67440 |  |  | 2026-01-31 |  |  | 2026-01-31
[9 empty] | 2 | 2. Inverters | New 100KW Inverter |  |  | 52730 | PO4158-MER-20250724 - RV Approved | Herholdt's Inv: INV1106843 | 2025-07-31 |  |  | 2025-08-30
[9 empty] | 2 | 2. Inverters | S1200 Optimisers |  |  | 9500 | PO4190-MER-20250731 - RV Approved | Herholdt's - INV1111496 | 2025-07-31 |  |  | 2025-08-30
[9 empty] | 2 | 2. Inverters |  |  |  | -200 |  | Herholdts - CN102297 | 2025-07-31 |  |  | 2025-07-31
2 | [8 empty] | 2 | 2. Inverters | Replacement Synergy Unit |  |  | 19380 | PO3847-MER-20250505 - RV Approved | Herholdts - INV1055010 | 2025-05-31 | 0 |  | 2025-05-31
2 | [8 empty] | 2 | 2. Inverters |  |  |  | -19380 |  | Herholdts - CN092803 | 2025-05-31 | 0 |  | 2025-05-31 |  |  | Other | 0
[23 empty] | Total | 290212.7522
3 | Mounting Structures | Lumax Pitch Roof |  |  | 36036 | 2025-03-20 | 36036 | 45045 | 3 | 3. Mounting Structures | Schletter |  |  | 19322.8 | PO3646-MER-20250211 - RV Approved | SCHLETTER - INV1434 | 2025-02-28 | 29396.1176 | 0 | 2025-03-28 | 29609.2 |  | Less 15% | 246680.8393 | [SM: Target Installation Price]
3 | [8 empty] | 3 | 3. Mounting Structures | Additional Clamps - VO |  |  | 10286.4 | PO3690-MER-20250220 - RV Approved | SCHLETTER - INV1453 | 2025-02-28 | 15648.8824 |  | 2025-03-28 |  |  | R/Wp | 2.7409
3 | [8 empty] | 3 | 3. Mounting Structures
3 | [8 empty] | 3 | 3. Mounting Structures | [12 empty] | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 128120
4 | DC Equipment | DC Cabling (Total Cable Length) | 1650 | 14 | 23100 | 2025-03-20 | 71361.4 | 89201.75 | 4 | 4. DC Equipment | [7 empty] | 0 | 0 |  | 84100 |  | DC Equipment | 56320
4 | [8 empty] | 4 | 4. DC Equipment | DC Cable | 2000 | 13.89 | 27780 | PO3604-MER-20250130 - RV Approved | Krannich Inv 15-10011770 | 2025-02-28 | 29465.2154 |  | 2025-04-24 |  |  | AC Labour | 25000
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | DC Labour | 72233
4 |  | Project Kick Off |  | 10% | 4826.14 | 2025-02-10 |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | Offloading | 23225
4 | 48261.4 | Site Establishment |  | 15% | 7239.21 | 2025-02-24 |  |  | 4 | 4. DC Equipment | Project Kick Off | 56320 | 10% | 5632 | PO3645-MER-20250211 - RV Approved | Thula Moya IN04614 | 2025-02-28 | 5973.6535 |  | 2025-02-20 |  |  | Roof Access/Scaffolding | 0
4 |  | AC Installation Complete |  | 20% | 9652.28 | 2025-03-05 |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 8448 |  | Thula Moya IN04625 | 2025-02-28 | 8960.4802 |  | 2025-03-06 |  |  | Storage | 0
4 |  | DC Installation Complete |  | 25% | 12065.35 | 2025-03-05 |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 11264 |  | Thula Moya IN04648 | 2025-03-31 | 11947.3069 |  | 2025-03-13 |  |  | Telehandler | 0
4 |  | Commissioning Complete |  | 10% | 4826.14 | 2025-03-11 |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 14080 |  | Thula Moya IN04649 | 2025-03-31 | 14934.1337 |  | 2025-03-13 |  |  | HSE | 10500
4 |  | Site De-establisment |  | 10% | 4826.14 | 2025-09-09 |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 5632 |  | Thula Moya IN04650 | 2025-03-31 | 5973.6535 |  | 2025-04-03 |  |  | Other | 0
4 |  | Handover Document Complete |  | 5% | 2413.07 | 2025-03-17 |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 5632 |  | Thula Moya IN04651 | 2025-03-31 | 5973.6535 |  | 2025-04-10 |  |  | Other | 0
4 |  | End of Defects Period |  | 5% | 2413.07 | 2025-04-16 |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 2816 |  | Thula Moya IN04731 | 2025-05-31 | 2986.8267 |  | 2025-06-18 |  |  | Total | 315398
4 | [8 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 2816 |  | Thula Moya IN04731 | 2025-05-31 | 2986.8267 |  | 2025-07-03 |  |  | R/Wp | 3.5044
5 | Monitoring | [5 empty] | 0 | 0 | 5 | 5. Monitoring | [7 empty] | 0 | 0 |  | 7644.95
5 | [8 empty] | 5 | 5. Monitoring | CTs |  |  | 1860 | PO3647-MER-20250211 - RV Approved | AccuEnergy - ASAI-004803 | 2025-02-28 | 0 |  | 2025-03-28
5 | [8 empty] | 5 | 5. Monitoring | Courier of Sim card & CT's |  |  | 294.95 |  | DSV Inv: 180121124 | 2025-03-31 | 0 |  | 2025-04-30
5 | [8 empty] | 5 | 5. Monitoring | Techsitter CTs |  |  | 5490 | PO4132-MER-20250717 - RV Approved | AccuEnergy ASAI-005991 | 2025-07-31 | 0 |  | 2025-08-30
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | [5 empty] | 140010.5522 | 175013.1902 | 6 | 6. AC Equipment | [8 empty] | 0 |  | 128120
6 |  | Project Kick Off |  | 10% | 14001.0552 | 2025-02-10 |  |  | 6 | 6. AC Equipment | Project Kick Off | 128120 | 10% | 12812 | PO3645-MER-20250211 - RV Approved | Thula Moya IN04614 | 2025-02-28 | 17501.319 |  | 2025-02-20
6 | 140010.5522 | Site Establishment |  | 15% | 21001.5828 | 2025-02-24 |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 19218 |  | Thula Moya IN04625 | 2025-02-28 | 26251.9785 |  | 2025-03-06
6 |  | AC Installation Complete |  | 20% | 28002.1104 | 2025-03-05 |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 25624 |  | Thula Moya IN04648 | 2025-03-31 | 35002.638 |  | 2025-03-13
6 |  | DC Installation Complete |  | 25% | 35002.638 | 2025-03-05 |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 32030 |  | Thula Moya IN04649 | 2025-03-31 | 43753.2976 |  | 2025-03-13
6 |  | Commissioning Complete |  | 10% | 14001.0552 | 2025-03-11 |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 12812 |  | Thula Moya IN04650 | 2025-03-31 | 17501.319 |  | 2025-04-03
6 |  | Site De-establisment |  | 10% | 14001.0552 | 2025-09-09 |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 12812 |  | Thula Moya IN04651 | 2025-03-31 | 17501.319 |  | 2025-04-10
6 |  | Handover Document Complete |  | 5% | 7000.5276 | 2025-03-17 |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 6406 |  | Thula Moya IN04731 | 2025-05-31 | 8750.6595 |  | 2025-06-18
6 |  | End of Defects Period |  | 5% | 7000.5276 | 2025-04-16 |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 6406 |  | Thula Moya IN04731 | 2025-05-31 | 8750.6595 |  | 2025-07-03
7 | Battery Systems | [5 empty] | 0 | 0 | 7 | Battery Systems | [8 empty] | 0 |  | 0
7 | [8 empty] | 7
7 | [8 empty] | 7
7 | [8 empty] | 7
7 | [8 empty] | 7
7 | [8 empty] | 7
7 | [8 empty] | 7
7 | [8 empty] | 7
8 | Product Add On | [5 empty] | 0 | 0 | 8 | 8. Product Add On | Techsitter Control Meter |  |  | 11169 |  | Matriarch Inv: 4742 | 2025-07-31 | 0 | 0 | 2025-07-31 | 37066.62
8 | [8 empty] | 8 | 8. Product Add On | Techsitter Solar Meter |  |  | 11169 | PO3941-MER-20250520 - RV Approved | Matriarch Inv: 4742 | 2025-07-31 | 0 |  | 2025-07-31
8 | [8 empty] | 8 | 8. Product Add On | Delivery of Meters |  |  | 1428.62 |  | DSV Inv: 180139213 | 2025-07-31 | 0 |  | 2025-08-29
8 | [8 empty] | 8 | 8. Product Add On | EnergiTrack Waveshare Industrial Converter |  |  | 1500 | PO4122-MER-20250714 - RV Approved | Herholdts - INV1120605 | 2025-08-31 | 0 |  | 2025-09-30
[9 empty] | 8 | 8. Product Add On | Thula Moya - DC Cable - VO |  |  | 11800 | PO4346-MER-20250930 - RV Approved | Thula Moya IN04946 | 2025-11-30 |  |  | 2025-12-18
8 | [8 empty] | 8 | 8. Product Add On | [7 empty] | 0
9 | AC & DC Installation | Project Kick Off |  | 10% | 7372.75 | 2025-02-10 | 73727.5 | 86738.2353 | 9 | 9. AC & DC installation | Project Kick Off | 97233 | 10% | 9723.3 | PO3645-MER-20250211 - RV Approved | Thula Moya IN04614 | 2025-02-28 | 8673.8235 | 0 | 2025-02-20 | 97233
9 | 22522.5 | Site Establishment |  | 15% | 11059.125 | 2025-02-24 |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 14584.95 |  | Thula Moya IN04625 | 2025-02-28 | 13010.7353 |  | 2025-03-06
9 | 51205 | AC Installation Complete |  | 20% | 14745.5 | 2025-03-05 |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 19446.6 |  | Thula Moya IN04648 | 2025-03-31 | 17347.6471 |  | 2025-03-13
9 |  | DC Installation Complete |  | 25% | 18431.875 | 2025-03-05 |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 24308.25 |  | Thula Moya IN04649 | 2025-03-31 | 21684.5588 |  | 2025-03-13
9 |  | Commissioning Complete |  | 10% | 7372.75 | 2025-03-11 |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 9723.3 |  | Thula Moya IN04650 | 2025-03-31 | 8673.8235 |  | 2025-04-03
9 |  | Site De-establisment |  | 10% | 7372.75 | 2025-09-09 |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 9723.3 |  | Thula Moya IN04651 | 2025-03-31 | 8673.8235 |  | 2025-04-10
9 |  | Handover Document Complete |  | 5% | 3686.375 | 2025-03-17 |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 4861.65 |  | Thula Moya IN04731 | 2025-05-31 | 4336.9118 |  | 2025-06-18
9 |  | End of Defects Period |  | 5% | 3686.375 | 2025-04-16 |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 4861.65 |  | Thula Moya IN04731 | 2025-05-31 | 4336.9118 |  | 2025-07-03
10 | Site Logistics | Security |  |  | 21600 | 2025-04-16 | 49813.3 | 58603.8824 | 10 | 10. Site Logistics | Security | [6 empty] | 0 | -0.0012786 |  | 33725.02
10 |  | Scaffolding |  |  | 19713.3 | 2025-03-11 |  |  | 10 | 10. Site Logistics | Project Kick Off | 33725 | 10% | 3372.5 | PO3645-MER-20250211 - RV Approved | Thula Moya IN04614 | 2025-02-28 | 5860.3882 |  | 2025-02-20
10 | [8 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 5058.75 |  | Thula Moya IN04625 | 2025-02-28 | 8790.5824 |  | 2025-03-06
10 | [8 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 6745 |  | Thula Moya IN04648 | 2025-03-31 | 11720.7765 |  | 2025-03-13
10 | [8 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 8431.25 |  | Thula Moya IN04649 | 2025-03-31 | 14650.9706 |  | 2025-03-13
10 |  | Offloading |  |  | 8500 | 2025-03-11 |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 3372.5 |  | Thula Moya IN04650 | 2025-03-31 | 5860.3882 |  | 2025-04-03
10 | [8 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 3372.5 |  | Thula Moya IN04651 | 2025-03-31 | 5860.3882 |  | 2025-04-10
10 | [8 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1686.25 |  | Thula Moya IN04731 | 2025-05-31 | 2930.1624 |  | 2025-06-18
10 | [8 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1686.27 |  | Thula Moya IN04731 | 2025-05-31 | 2930.2271 |  | 2025-07-03
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-03-18 | 11000 | 12941.1765 | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 16160 | PO3780-MER-20250328 - RV Approved | Sunspot IN E017 | 2025-03-31 | 9437.2478 | 0 | 2025-04-10 | 22160
11 | [8 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 6000 |  | Matriarch Inv: 4068 | 2025-03-31 | 3503.9286 |  | 2025-03-31
11 | [8 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [8 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [8 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 | 12 | BDP Commission | [10 empty] | 0
12 | BDP Commission | [7 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 10069.5707 | 2025-04-07 | 40229.5707 | 45715.4212 | 13 | 13. Engineering | Matriarch Defects Period |  |  | 13057.9091 |  | Matriarch - INV-4067 | 2025-03-31 | 45715.4212 | 0 | 2025-03-31 | 13057.9091
13 |  | Management |  |  | 7200 | 2025-04-07 |  |  | 13 | 13. Engineering | Management | [5 empty] | 2025-03-31 | 0 |  | 2025-03-31
13 |  | Project manager |  |  | 6800 | 2025-04-07 |  |  | 13 | 13. Engineering | Project manager | [5 empty] | 2025-03-31 | 0 |  | 2025-03-31
13 |  | Planner time |  |  | 9360 | 2025-04-07 |  |  | 13 | 13. Engineering | Planner time | [5 empty] | 2025-03-31 | 0 |  | 2025-03-31
13 |  | De Snagging |  |  | 6800 | 2025-04-07 |  |  | 13 | 13. Engineering | De Snagging | [5 empty] | 2025-03-31 | 0 |  | 2025-03-31
13 | [8 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [8 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Car travel to site |  |  | 1575 | 2025-04-07 | 1575 | 1852.9412 | 14 | 14. General Expenses | Car travel to site |  |  | 1015.63 |  | Expense Claims | 2025-01-31 | 95.2109 | -0.0036468 | 2025-02-07 | 14965.26
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 5525.96 |  | Expense Claims | 2025-02-28 | 541.3523 |  | 2025-03-06
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 0 |  | Expense Claims | 2025-03-31 | 0 |  | 2025-04-07
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 2740.7 |  | Expense Claims | 2025-04-30 | 1216.3816 |  | 2025-05-08
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 2167.79 |  | Expense Claims | 2025-05-31 |  |  | 2025-06-06
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 1567.41 |  | Expense Claims | 2025-07-31 | 0 |  | 2025-08-07
14 | [8 empty] | 14 | 14. General Expenses |  |  |  | 1947.77 |  | Expense Claims | 2025-10-31 | 0 |  | 2025-11-06
15 | Service Add On | [5 empty] | 0 | 0 | 15 | 15. Service Add On | Service Fee |  |  | 3774.4 |  | Herholdt's Inv: INV978839 | 2025-01-31 |  | 0 | 2025-02-27 | 185786.11
15 | [8 empty] | 15 | 15. Service Add On | Callout - Replace Comms board - VO |  |  | 2598 |  | Thula Moya - IN07401 | 2025-05-31 |  |  | 2025-05-29 |  | TC: Added cost
15 | [8 empty] | 15 | 15. Service Add On | Call out - Attess - Isolation error - VO |  |  | 41038.57 | PO4214-MER-20250812 - RV Approved | Thula Moya - IN04819 | 2025-08-31 |  |  | 2025-08-14
[9 empty] | 15 | 15. Service Add On | Callout for Inverter Replacement - VO |  |  | 7548.83 |  | Thula Moya IN04734 | 2025-05-31 | 0 |  | 2025-07-03
[9 empty] | 15 | 15. Service Add On | Call-out and assessment - VO |  |  | 15800 |  | Thula Moya IN04769 | 2025-07-31 | 0 |  | 2025-07-11
[9 empty] | 15 | 15. Service Add On | Optimiser Replacment - VO |  |  | 30339 | PO2918-MER-20251024 - RV Approved | Thula Moya - IN04942 | 2025-10-31 | 0 |  | 2025-11-13
[9 empty] | 15 | 15. Service Add On | Courier of Sonnel Meter - VO |  |  | 483.03 |  | DSV Inv: 180139892 +180139213 | 2025-07-31 |  |  | 2025-08-29
[9 empty] | 15 | 15. Service Add On | Courier of Seward Meter - VO |  |  | 223.56 |  | DSV Inv: 180142244 | 2025-09-30 |  |  | 2025-10-31
[9 empty] | 15 | 15. Service Add On | New Scope - Replacement of optimisers incl material - VO |  |  | 69571.56 |  | Thula Moya IN04906 | 2025-09-30 |  |  | 2025-10-02
[9 empty] | 15 | 15. Service Add On | Labour and Travel - VO |  |  | 7328.61 | PO4559-MER-20260120 - RV Apporved |  | 2026-01-31 |  |  | 2026-02-28
[9 empty] | 15 | 15. Service Add On | support and locate the issue with support from ATESS - VO |  |  | 6542.61 | PO4557-MER-20260119 - RV Apporved | Thula Moya - IN04998 | 2026-01-31 |  |  | 2026-02-28
15 | [8 empty] | 15 | 15. Service Add On | Courier of Optimzers - VO |  |  | 537.94 |  | DSV Inv: 180152208 | 2025-10-31 |  |  | 2025-11-28
| Panel Procurement Budget | 316418.6275 | [15 empty] | 1044632.7292
| Inverter Procurement Budget | 213102.5
| Mounting Structure Budget | 45045
| DC Equipment Budget | 89201.75
| AC Equipment Budget | 175013.1902
| Monitoring Budget | 0
| Optional Extras Budget | 0
| MV Metering Budget | 0
| ADD ON | 0
| Battery System | 0
| Generator | 0
Services
| AC Installer Budget | 26497.0588
| DC Installer Budget | 60241.1765
| In-House Expense Budget | 45715.4212
| Compliance Budget | 12941.1765
| Offloading Budget | 10000
| Roof Access Budget for Equipment | 0
| Site storage | 0
| On Site Security | 25411.7647
| Roof Access Budget for Installers | 23192.1176
| EPC Management Fee | 0
| ADD ON | 0
Expenses
| Total EE Expense Budget | 1852.9412

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2026-09-28
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1044632.7242 | 1044632.7242 | 0 | 0 | 0 | 0 | 0 | 522316.3621 | 0 | 0 | 365621.4535 | 0 | 104463.2724 | 0 | 0 | 0 | 0 | 52231.6362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 522316.3621 | 522316.3621 | 522316.3621 | 887937.8156 | 887937.8156 | 992401.088 | 992401.088 | 992401.088 | 992401.088 | 992401.088 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242
| Planned Expenditure | 847370.2249 | 847370.2249 | 0 | 0 | 0 | 26199.9452 | 0 | 39299.9178 | 117899.7535 | 54413.2452 | 506852.8746 | 0 | 0 | 41804.5707 | 34699.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26199.9452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 26199.9452 | 26199.9452 | 65499.863 | 183399.6165 | 237812.8617 | 744665.7363 | 744665.7363 | 744665.7363 | 786470.307 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 821170.2796 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249 | 847370.2249
| PLANNED CashFlow |  |  | 0 | 0 | 0 | -26199.9452 | -26199.9452 | 456816.4991 | 338916.7456 | 284503.5004 | 143272.0793 | 143272.0793 | 247735.3517 | 205930.781 | 171230.8084 | 171230.8084 | 171230.8084 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 223462.4446 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994 | 197262.4994
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1057829.0842 | 1057829.0842 | 0 | 0 | 0 | 0 | 0 | 0 | 887937.8156 | 0 | 0 | 0 | 0 | 0 | 0 | 104463.2724 | 0 | 0 | 0 | 0 | 0 | 52231.6362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13196.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 887937.8156 | 887937.8156 | 887937.8156 | 887937.8156 | 887937.8156 | 887937.8156 | 887937.8156 | 992401.088 | 992401.088 | 992401.088 | 992401.088 | 992401.088 | 992401.088 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1044632.7242 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842 | 1057829.0842
| Actual + Planned Expenditure | 1002547.3291 | 1002547.3291 | 0 | 0 | 1015.63 | 0 | 31539.8 | 3774.4 | 52835.66 | 141929.1 | 0 | 190539.2 | 50597.7091 | 47699.8 | 0 | 207168.55 | 294.95 | 2740.7 | 0 | 0 | 2598 | 2167.79 | 0 | 15769.9 | 296.99 | 23318.75 | 15800 | 0 | 0 | 22138 | 1567.41 | 41038.57 | 0 | 69631.65 | 0 | 0 | 0 | 0 | 71071.56 | 0 | 0 | 0 | 1441.28 | 1947.77 | 30339 | 0 | 15053.94 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | -67440 | 0 | 0 | 0 | 13871.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 1015.63 | 1015.63 | 32555.43 | 36329.83 | 89165.49 | 231094.59 | 231094.59 | 421633.79 | 472231.4991 | 519931.2991 | 519931.2991 | 727099.8491 | 727394.7991 | 730135.4991 | 730135.4991 | 730135.4991 | 732733.4991 | 734901.2891 | 734901.2891 | 750671.1891 | 750968.1791 | 774286.9291 | 790086.9291 | 790086.9291 | 790086.9291 | 812224.9291 | 813792.3391 | 854830.9091 | 854830.9091 | 924462.5591 | 924462.5591 | 924462.5591 | 924462.5591 | 924462.5591 | 995534.1191 | 995534.1191 | 995534.1191 | 995534.1191 | 996975.3991 | 998923.1691 | 1029262.1691 | 1029262.1691 | 1044316.1091 | 1044316.1091 | 1044316.1091 | 1056116.1091 | 1056116.1091 | 1056116.1091 | 1056116.1091 | 1056116.1091 | 1056116.1091 | 988676.1091 | 988676.1091 | 988676.1091 | 988676.1091 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291 | 1002547.3291
| ACTUAL CashFlow |  |  | 0 | 0 | -1015.63 | -1015.63 | -32555.43 | -36329.83 | 798772.3256 | 656843.2256 | 656843.2256 | 466304.0256 | 415706.3165 | 368006.5165 | 368006.5165 | 265301.239 | 265006.289 | 262265.589 | 262265.589 | 262265.589 | 259667.589 | 309731.4352 | 309731.4352 | 293961.5352 | 293664.5452 | 270345.7952 | 254545.7952 | 254545.7952 | 254545.7952 | 232407.7952 | 230840.3852 | 189801.8152 | 189801.8152 | 120170.1652 | 120170.1652 | 120170.1652 | 120170.1652 | 120170.1652 | 49098.6052 | 49098.6052 | 49098.6052 | 49098.6052 | 47657.3252 | 45709.5552 | 28566.9152 | 28566.9152 | 13512.9752 | 13512.9752 | 13512.9752 | 1712.9752 | 1712.9752 | 1712.9752 | 1712.9752 | 1712.9752 | 1712.9752 | 69152.9752 | 69152.9752 | 69152.9752 | 69152.9752 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552 | 55281.7552
|  | CHECK | CHECK
| Revenue Recognition | -0.0049254 | 1044632.7292 | 0 | 95.2109 | 0 | 0 | 0 | 699595.6559 | 0 | 0 | 0 | 0 | 305716.2953 | 0 | 0 | 0 | 1216.3816 | 0 | 0 | 0 | 38009.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1044632.7292 | 0 | 95.2109 | 95.2109 | 95.2109 | 95.2109 | 699690.8667 | 699690.8667 | 699690.8667 | 699690.8667 | 699690.8667 | 1005407.162 | 1005407.162 | 1005407.162 | 1005407.162 | 1006623.5436 | 1006623.5436 | 1006623.5436 | 1006623.5436 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292 | 1044632.7292
| Installer Expenditure |  | 281673 | 0 | 0 | 0 | 0 | 28167.3 | 0 | 42250.95 | 126752.85 | 0 | 0 | 28167.3 | 28167.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14083.65 | 0 | 14083.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 28167.3 | 28167.3 | 70418.25 | 197171.1 | 197171.1 | 197171.1 | 225338.4 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 253505.7 | 267589.35 | 267589.35 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673 | 281673

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-01-31 | 2025-02-28 | 2025-04-30 | 2025-03-31 | 2025-05-31 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-30 | Grand Total
Battery Systems
BDP Commission
(blank)
1. Panels |  |  | 179388.55 |  |  |  |  | 1217.72 | 14516 |  |  |  | 195122.27
2. Inverters |  |  | 159070 |  |  | 296.99 | 62030 |  |  |  |  | -67440 | 153956.99
3. Mounting Structures |  |  | 29609.2 | [9 empty] | 29609.2
4. DC Equipment |  |  | 41860 |  | 36608 | 5632 | [6 empty] | 84100
5. Monitoring |  |  | 1860 |  | 294.95 |  | 5490 | [5 empty] | 7644.95
6. AC Equipment |  |  | 32030 |  | 83278 | 12812 | [6 empty] | 128120
8. Product Add On | [6 empty] | 23766.62 | 1500 |  |  | 11800 |  | 37066.62
9. AC & DC installation |  |  | 24308.25 |  | 63201.45 | 9723.3 | [6 empty] | 97233
10. Site Logistics |  |  | 8431.25 |  | 21921.25 | 3372.52 | [6 empty] | 33725.02
11. Due Dilligence |  |  |  |  | 22160 | [7 empty] | 22160
13. Engineering |  |  |  |  | 13057.9091 | [7 empty] | 13057.9091
14. General Expenses |  | 1015.63 | 5525.96 | 2740.7 | 0 | 2167.79 | 1567.41 |  |  | 1947.77 |  |  | 14965.26
15. Service Add On |  | 3774.4 |  |  |  | 10146.83 | 16283.03 | 41038.57 | 69795.12 | 30876.94 |  |  | 171914.89
Grand Total |  | 4790.03 | 482083.21 | 2740.7 | 240521.5591 | 44151.43 | 109137.06 | 43756.29 | 84311.12 | 32824.71 | 11800 | -67440 | 988676.1091

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-30 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels | 0 |  |  | 316418.6275 |  |  |  |  | 0 | 0 |  |  |  | 316418.6275
2. Inverters |  |  |  | 213102.5 |  |  | 0 | [6 empty] | 213102.5
3. Mounting Structures |  |  |  | 45045 | [9 empty] | 45045
4. DC Equipment |  | 0 |  | 44399.349 | 38828.7475 |  | 5973.6535 | [6 empty] | 89201.75
5. Monitoring | 0 | 0 |  | 0 | 0 |  |  | 0 | [5 empty] | 0
6. AC Equipment |  |  |  | 43753.2976 | 113758.5736 |  | 17501.319 | [6 empty] | 175013.1902
8. Product Add On |  | 0 | [5 empty] | 0 | 0 |  |  |  |  | 0
9. AC & DC installation |  |  |  | 21684.5588 | 56379.8529 |  | 8673.8235 | [6 empty] | 86738.2353
10. Site Logistics |  | 0 |  | 14650.9706 | 38092.5235 |  | 5860.3895 | [6 empty] | 58603.8836
11. Due Dilligence | 0 |  |  |  | 12941.1765 | [8 empty] | 12941.1765
13. Engineering | 0 |  |  |  | 45715.4212 | [8 empty] | 45715.4212
14. General Expenses |  |  | 95.2109 | 541.3523 | 0 | 1216.3816 |  | 0 |  |  | 0 |  |  | 1852.9448
15. Service Add On | [6 empty] | 0 | 0 |  |  | 0 |  |  | 0
Grand Total | 0 | 0 | 95.2109 | 699595.6559 | 305716.2953 | 1216.3816 | 38009.1855 | 0 | 0 | 0 | 0 |  |  | 1044632.7292

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Meraki Phase 3
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 72384 | 0 | 72384 | 0 | 72384
Inverters | 72384
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 36036 | 0 | 36036 | 0 | 36036
Mounting Structure | 36036
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 23100 | 0 | 23100 | 0 | 23100
DC Cable | 23100
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
0 | 0
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 140010.5522 | 1.5557 | 277892.91 | 3.0877 | -137882.3578 |  | 0 | 140010.5522
DC Equipment | 48261.4 | 0.53624 | 142158.25 | 1.5795 | -93896.85 |  | 0 | 48261.4
AC Labour | 22522.5 | 0.25025 | 96174 | 1.0686 | -73651.5 |  | 0 | 22522.5
DC Labour | 51205 | 0.56894 | 230160 | 2.5573 | -178955 |  | 0 | 51205
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 19713.3 |  | 29257.61 |  | -9544.31 |  |  | 19713.3
Storage | 0 |  |  |  | 0 |  |  | 0
Telehandler | 0
HSE | 0
Totals | 290212.7522 |  | 775642.77 |  | -485430.0178 | 0 |  | 290212.7522
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 140010.5522
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 48261.4
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 22522.5
DC equipment | 4826.14 | 0.053624 |  |  | 4826.14 |  |  | 51205
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 49813.3 |  |  |  | 49813.3 |  |  | 19713.3
Offloading | 0 |  |  |  | 0 |  |  | 0
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 290212.7522
Budget Summary
Budget | 290212.7522
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 290212.7522
All amounts are exc VAT

## Decision Register (hidden)
Meraki Phase 3 |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Meraki Phase 3 | 0 | 0 | 0